# TMNAS RapidSure - Fixed Fee Delivery Framework

Version 1.0 | March 2024 | Project Start: April 1, 2024

# EXECUTIVE SUMMARY

This Fixed Fee Delivery Framework outlines the approach for TMNAS RapidSure Platform Modernization. The project aims to modernize the legacy insurance platform, establish EPAM as a trusted partner, and create a foundation for scalable Personal Lines product delivery.

| Project | TMNAS RapidSure Platform Modernization |
| --- | --- |
| Client | TMNAS (7-year EPAM relationship) |
| Start Date | April 1, 2024 |
| Duration | 6 months ($1M) or 11 months ($2M) |
| Delivery Model | Hybrid Agile-Waterfall (Fixed Fee) |
| Team Size | 17 people (4 pods) |
| Sprint Length | 2 weeks |
| Contingency | 20% (high-risk project) |
| Warranty | 60 days post go-live |

# PROJECT SCOPE

## In Scope (6-Month Option)

Business Layer API implementation (US-008)

Database optimization for high concurrency (US-010)

UI modernization JSF/IceFaces → React/Angular (US-011)

Product Configuration API (US-009)

CI/CD pipeline automation (US-017)

Environment automation (US-018)

Governance & process improvements (US-001-003)

Requirements quality framework (US-004-005)

QA shift-left with AI (US-006)

Technical debt management (US-007)

AI agents: Code analysis, Knowledge base, Coverage analysis (US-012-014)

Platform upgrade to support SV product (migration only)

## Out of Scope

SV product implementation (separate team)

Historical data migration (11-month option)

End user training

Production support post-warranty

UAT/Performance/Security testing execution (TMNAS responsibility)

# TEAM STRUCTURE

Total: 17 people across 4 pods (Pod 2 removed - SV out of scope)

| Pod | Size | Roles | Focus |
| --- | --- | --- | --- |
| Pod 1: Platform | 6 | 1 Arch, 3 BE, 1 DBA, 1 QA | Business API, DB, Tech Debt |
| Pod 3: UI/Frontend | 4 | 1 FE Arch, 2 FE Dev, 1 QA | UI Modernization |
| Pod 4: Process/AI | 4 | 1 PM, 1 BA, 2 AI Eng | Governance, AI Agents |
| Pod 5: Infrastructure | 3 | 1 DevOps Lead, 2 DevOps | CI/CD, Automation |

Key Personnel (must remain stable):

Delivery/Program Manager

Senior Solution Architect

Senior Team/Tech Lead

# BUDGET & ESTIMATION

## 6-Month Option ($1M)

| Component | Amount | Notes |
| --- | --- | --- |
| Base Effort | $826,000 | 236 SP × $3,500/SP |
| Contingency (20%) | $165,000 | High-risk buffer |
| Infrastructure | $0 | Customer-provided |
| TOTAL | $991,000 | ≈ $1,000,000 |

## 11-Month Option ($2M)

Structure: PI-based phases, billing every 4 months (~$450K per phase)

PI 1 (Months 1-4): Foundation & Core Modernization - $450K

PI 2 (Months 5-8): Platform Complete & AI Agents - $450K

PI 3 (Months 9-11): Additional Scope (TBD) + Warranty - $1.1M

# DELIVERY APPROACH

Hybrid Model: Agile execution + Waterfall governance

Agile Elements:

2-week sprints with daily standups

Sprint planning, review, retrospective

Continuous integration/deployment

Rolling wave planning (3 sprints ahead)

Waterfall Elements:

Fixed payment milestones (M0-M4)

Formal change control process

Quality gates at milestones

Baseline scope documentation

# QUALITY MANAGEMENT

## Definition of Ready (DoR)

Clear user story with INVEST criteria

Detailed acceptance criteria (Given-When-Then)

Functional flows documented

Technical requirements specified

Dependencies identified

Story points estimated

No open questions

## Definition of Done (DoD)

All acceptance criteria met

Code reviewed and approved

Unit tests with 85% coverage

Integration tests passed

No P1/P2 defects

Technical documentation updated

Code merged to main

Deployed to QA

Client BA/PO sign-off

## Test Strategy

| Test Type | Owner | Details |
| --- | --- | --- |
| Unit Testing | EPAM | 85% coverage, JUnit/Mockito |
| Integration Testing | EPAM | DEV→QA, mock-based |
| UAT | TMNAS (3rd party) | EPAM: triage, prioritization, fixes |
| Performance Testing | TMNAS (vendor) | EPAM: ad-hoc support, target ownership |
| Security Testing | TMNAS (TBD) | Standards & pen testing TBD |

# CHANGE MANAGEMENT

Formal CR process based on EPAM templates (to be negotiated with TMNAS)

| Type | Impact | Handling |
| --- | --- | --- |
| Type 1: Clarification | No impact | Free - absorbed in project |
| Type 2: Minor Change | <5% budget (<$50K) | Absorbed in contingency, CR Board approval |
| Type 3: Major Change | >5% budget (>$50K) | Contract amendment + payment |

CR Board: EPAM (DM, Architect, BA) + TMNAS (CIO, CTO, POs)

# RISK MANAGEMENT

| Category | Level | Key Risks | Mitigation |
| --- | --- | --- | --- |
| Technical | HIGH | Legacy complexity, DB performance | 20% contingency, POCs |
| Organizational | HIGH | Immature processes, trust deficit | Formal CR, quick wins |
| Schedule | HIGH | SV deadline, UAT bottleneck | Parallel execution, buffers |
| Scope | MEDIUM | Requirements quality, scope creep | DoR enforcement, CR process |
| Commercial | MEDIUM | FF uncertainty, rate card TBD | Milestone payments, clear scope |

# NEXT STEPS

Internal Workshop:

Review & refine 16 user stories

Answer architecture questions (Q35-Q40)

Define 11-month additional scope

Finalize payment milestones

Create RAID Log & CR Process

Client Workshop:

Validate business context & stakeholders

Review & approve DoD/DoR

Define UAT entry/exit criteria

Clarify NFRs (performance, security)

Negotiate CR process & governance

Agree on payment milestones