## TMNAS - PROJECT RAMBO

## OPEN QUESTIONS FOR INTERNAL & CLIENT WORKSHOPS

Version: 3.0
Date: January 2025
Status: Draft - For Workshop Discussion

### DOCUMENT PURPOSE

This document consolidates all open questions that require clarification before finalizing the Project Charter, Statement of Work (SOW), and project execution plan. Questions are organized by category, prioritized by impact, and assigned to specific workshop sessions (Internal Workshop Day 1/2/3 or Client Workshop).

Total Open Questions: 60

### HOW TO USE THIS DOCUMENT

Priority Levels:

- 🔴 CRITICAL - Must be answered before contract signing; blocks project start or execution

- 🟠 HIGH - Significantly impacts scope, budget, timeline, or quality; should be answered during workshops

- 🟡 MEDIUM - Impacts planning and execution; can be answered during early sprints if necessary

Workshop Assignment:

- IW1 / IW2 / IW3 - Internal Workshop Day 1, 2, or 3

- CW - Client Workshop (with TMNAS stakeholders)

## CATEGORY 1: COMMERCIAL & CONTRACTUAL (7 Questions)

### OQ-001: Rate Card / Blended Rate

Question: What is the agreed rate card or blended hourly rate for this project?

Context:
Budget calculations assume ~$60/hour blended rate across all roles (CEE2, Ukraine, GUKKA mix). Actual rate card may differ based on contract negotiations, client agreements, or specific role rates (e.g., Solution Architect at $85/hr, Junior Dev at $45/hr).

Impact if Unanswered:
Budget estimates ($675K for 6-month, $1.8M for 9-month) may be inaccurate; could lead to budget overruns or underpricing.

EPAM Framework Reference:
EPAM FF Commercial Framework requires clear rate structure before contract signing.

Priority: 🔴 CRITICAL
Workshop: IW1 (Day 1) - EPAM leadership must provide rate card
Owner: EPAM Account Manager + Commercial Team

### OQ-002: Budget Validation (6-Month & 9-Month Options)

Question: Are the proposed budgets acceptable to TMNAS and EPAM leadership?

- 6-month option: $675,000 (aligned with $450K per 4 months)

- 9-month option: $1,800,000 ($600K per phase × 3 phases)

Context:
Initial guidance was $1M for 6-month and $2M for 11-month. We've adjusted to 6-month ($675K) and 9-month ($1.8M) to align with TMNAS fiscal structure and scope reductions (Pod 2 removed).

Impact if Unanswered:
Budget misalignment may delay contract negotiations or require re-scoping.

Priority: 🔴 CRITICAL
Workshop: IW1 (Day 1) + CW (Client Workshop)
Owner: EPAM Account Manager + TMNAS Finance

### OQ-003: L3 MSP Team Conversion - Scope & Timing

Question: Is the conversion of the existing OPEX development team to a formal L3 Managed Services (MSP) team in scope for this project, or is it a separate initiative?

Context:
You mentioned: "We want to convert existing OPEX development team to normal L3 MSP team. But it is outcome of the initiative and not in scope of current SOW."

Clarification Needed:

- Is MSP team setup included in Phase 3 of 9-month option?

- If out of scope, when does MSP transition occur (post-project)?

- What deliverables are expected to enable MSP transition (e.g., operational runbooks, SLA definitions, support processes)?

Impact if Unanswered:
Unclear scope boundary; may lead to scope creep if MSP-related work is requested mid-project.

Priority: 🟠 HIGH
Workshop: IW2 (Day 2) + CW
Owner: EPAM Delivery Manager + TMNAS Operations Lead

### OQ-004: Payment Terms & Milestone Acceptance Criteria

Question: Are the proposed payment milestones and acceptance criteria acceptable to TMNAS?

Proposed 6-Month Payment Milestones:

- M0 (Sprint 0): 10% ($67.5K) - Project Charter signed, Team onboarded

- M1 (Sprint 4): 30% ($202.5K) - Business API, DB Optimization, CI/CD, Governance

- M2 (Sprint 7): 30% ($202.5K) - UI Modernization (2+ modules), Product Config API, Code Analysis Agent

- M3 (Sprint 10): 20% ($135K) - UI Complete, AI Agents, QA/Tech Debt

- M4 (60 days post go-live): 10% ($67.5K) - Warranty complete, zero P1/P2 defects

Clarification Needed:

- Are acceptance criteria clear and measurable?

- What is the invoice-to-payment timeline (e.g., 30 days net)?

- Who signs off on milestone acceptance (Product Owner, CTO, both)?

- What happens if milestone is partially met (e.g., 80% complete)?

Impact if Unanswered:
Payment delays, disputes over acceptance criteria, cash flow issues for EPAM.

Priority: 🔴 CRITICAL
Workshop: CW (Client Workshop)
Owner: EPAM Account Manager + TMNAS Finance / Procurement

### OQ-005: Penalties & Liquidated Damages

Question: Are there penalties or liquidated damages for late delivery, quality issues, or SLA breaches in the Fixed Fee contract?

Context:
EPAM FF framework recommends negotiating penalty clauses carefully. Common penalty structures:

- Late delivery: X% of milestone payment per week of delay

- Quality issues: X% penalty if defect thresholds exceeded (e.g., >5% defect rate)

- SLA breaches: X% penalty if availability or performance SLAs not met

Clarification Needed:

- Does TMNAS require penalties in the contract?

- What are acceptable penalty thresholds and caps (e.g., max 10% of contract value)?

- Are there "act of God" or force majeure exclusions (e.g., TMNAS delays, 3rd party delays)?

Impact if Unanswered:
Financial risk to EPAM; may require higher contingency buffer or risk premium in pricing.

Priority: 🟠 HIGH
Workshop: IW1 (Day 1) - EPAM leadership decision
Owner: EPAM Legal + Commercial Team

### OQ-006: Warranty Period Scope & Exclusions

Question: What is the agreed warranty period, scope, and exclusions?

Proposed:

- Duration: 60 days post go-live

- Scope: P1/P2 defects (Critical and High severity) only

- Exclusions:

  - New features or enhancements (require new SOW)

  - Defects caused by TMNAS environment issues (infrastructure, network, 3rd party systems)

  - Defects caused by changes made by TMNAS team post-deployment

  - Issues outside EPAM-delivered scope (e.g., SV product implementation by other team)

Clarification Needed:

- Is 60 days acceptable, or does TMNAS require 90 days?

- What is the SLA during warranty (e.g., P1 response time: 4 hours)?

- Who determines defect severity (EPAM or TMNAS)?

- What is the escalation path for warranty disputes?

Impact if Unanswered:
Scope creep during warranty; EPAM may be asked to fix issues outside contract scope.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: EPAM Delivery Manager + TMNAS Product Owner

### OQ-007: Infrastructure & Cloud Costs - Who Pays?

Question: Who is responsible for infrastructure and cloud costs (DEV, QA, UAT environments)?

Context:
Project Charter assumes TMNAS pays for all infrastructure (VDIs, environments, cloud hosting, databases). Budget does not include infrastructure costs.

Clarification Needed:

- Confirm TMNAS pays for all infrastructure (DEV, QA, UAT environments, cloud hosting, Azure costs)

- If EPAM is responsible for any infrastructure costs, how much budget should be allocated?

- Are there any infrastructure procurement lead times that could delay project (e.g., new Azure resources)?

Impact if Unanswered:
Budget may be insufficient if EPAM is expected to pay for infrastructure; could delay project if procurement takes weeks.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: EPAM Delivery Manager + TMNAS Infrastructure Team

## CATEGORY 2: STAKEHOLDERS & GOVERNANCE (7 Questions)

### OQ-008: Complete Stakeholder List with Names & Contact Info

Question: Who are the complete list of stakeholders with names, titles, contact information (email, phone)?

Known Stakeholders:

- TMNAS: Lana (CIO), Prashant (CTO), [Product Owner - TBD], [BA - TBD], [Technical Lead - TBD], [UAT Lead - TBD]

- EPAM: [DM - TBD], [Architect - TBD], [Tech Lead - TBD], [BA - TBD], [QA Lead - TBD], [DevOps Lead - TBD], [Account Manager - TBD]

Clarification Needed:

- Fill in all TBD names and contact information

- Identify additional stakeholders (e.g., TMNAS Finance, Procurement, Security, Compliance, Operations)

- Confirm reporting relationships (who reports to whom)

- Confirm availability and time allocation (e.g., Product Owner 50% allocated to this project)

Impact if Unanswered:
Communication gaps, delayed decisions, unclear escalation paths.

Priority: 🔴 CRITICAL
Workshop: IW1 (Day 1) for EPAM team + CW for TMNAS team
Owner: EPAM Delivery Manager + TMNAS CTO

### OQ-009: Change Request (CR) Approval Process

Question: What is the formal Change Request approval process, and who are the CR Board members?

Proposed CR Process:

- CR submitted via template (by TMNAS or EPAM)

- EPAM analyzes impact within 3 business days (scope, schedule, cost)

- Weekly CR Board meeting (EPAM DM/BA + TMNAS PO/Prashant/BA)

- Approval/rejection by both parties

- Approved CRs added to backlog with priority

- CR tracking log updated and shared

Proposed CR Categories:

- Type 1 (Clarification): No impact, EPAM DM approval only

- Type 2 (Minor, <5% budget impact): Absorbed in contingency, CR Board approval

- Type 3 (Major, >5% budget impact): Requires contract amendment, Executive Sponsor approval

Clarification Needed:

- Is this CR process acceptable to TMNAS?

- Who are the CR Board members (roles and names)?

- How often do CR Board meetings occur (weekly recommended)?

- What is the CR approval authority threshold (e.g., Prashant can approve up to $50K, Lana approval required for >$50K)?

Impact if Unanswered:
Uncontrolled scope creep, budget overruns, disputes over what's in/out of scope.

Priority: 🔴 CRITICAL
Workshop: IW2 (Day 2) + CW
Owner: EPAM Delivery Manager + TMNAS Product Owner

### OQ-010: Budget Approval Process at TMNAS

Question: What is TMNAS's internal budget approval process for this project and Change Requests?

Context:
Understanding TMNAS's budget approval process helps EPAM anticipate delays and plan accordingly.

Clarification Needed:

- Who has budget authority for this project (Lana, Prashant, Finance Director)?

- What is the approval process for the initial contract ($675K or $1.8M)?

- What is the approval process for Change Requests (e.g., Type 3 CRs requiring additional budget)?

- What are typical approval timelines (days or weeks)?

- Are there fiscal year constraints (e.g., budget must be spent by Dec 31, 2026)?

Impact if Unanswered:
Delays in CR approvals, unexpected budget freezes, fiscal year-end rush or project suspension.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: TMNAS Finance / Procurement

### OQ-011: UAT Entry & Exit Criteria

Question: What are the formal UAT entry and exit criteria?

Proposed UAT Entry Criteria:

- All in-scope user stories completed and accepted in Sprint Review

- Code coverage ≥85%

- No P1/P2 defects open

- Technical documentation complete

- Deployment runbook validated

- EPAM quality gates passed

Proposed UAT Exit Criteria:

- All UAT test cases executed

- UAT pass rate ≥95% (≤5% defects found)

- All P1/P2 defects resolved and verified

- P3/P4 defects documented and prioritized for post-go-live or deferred

- Product Owner sign-off on UAT results

- Go-live readiness confirmed

Clarification Needed:

- Are these criteria acceptable to TMNAS?

- Who defines UAT test cases (TMNAS, 3rd party vendor)?

- What is acceptable UAT pass rate (95%? 98%? 100%)?

- What happens if UAT fails (re-test cycles, delay go-live)?

- Who signs off on UAT exit (Product Owner, CTO, UAT vendor)?

Impact if Unanswered:
Disputes over UAT readiness, unclear go-live decision criteria, extended UAT cycles.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: TMNAS UAT Lead + EPAM QA Lead

### OQ-012: Governance Meeting Attendance & Availability

Question: Can TMNAS stakeholders commit to the proposed meeting cadence and attendance?

Proposed Meeting Cadence:

- Sprint Planning (bi-weekly, 2 hours) - TMNAS PO required

- Sprint Review (bi-weekly, 1 hour) - TMNAS PO + stakeholders

- Backlog Grooming (weekly, 1 hour) - TMNAS PO required

- Change Control Board (weekly, 30 min) - TMNAS PO + Prashant

- Steering Committee (monthly, 1 hour) - TMNAS CIO + CTO

- Risk Review (bi-weekly, 30 min) - TMNAS Prashant

Clarification Needed:

- Can TMNAS Product Owner commit to 50% time allocation (20 hours/week)?

- Are proposed meeting times and durations acceptable?

- Are there any blackout periods (holidays, fiscal year-end, insurance renewal season)?

- What is the escalation process if stakeholders cannot attend (delegate, reschedule, asynchronous decision)?

Impact if Unanswered:
Delayed decisions, blocked sprints, reduced team velocity, missed milestones.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: TMNAS Product Owner + CTO

### OQ-013: Decision-Making Authority & Escalation

Question: Who has decision-making authority for different types of decisions, and what is the escalation path?

Proposed Decision Authority Matrix:

| Decision Type | Authority | Escalation if Deadlocked |
| --- | --- | --- |
| Sprint backlog prioritization | TMNAS Product Owner | TMNAS CTO |
| Technical architecture choices | EPAM Architect + TMNAS CTO | Steering Committee |
| Type 1 CR (Clarification) | EPAM DM | N/A |
| Type 2 CR (Minor, <5%) | CR Board (EPAM DM + TMNAS PO) | TMNAS CTO |
| Type 3 CR (Major, >5%) | TMNAS CIO + CTO | Contract amendment negotiation |
| Go-live decision | TMNAS CIO + CTO | N/A (executive authority) |
| Defect severity classification | EPAM QA Lead + TMNAS UAT Lead | CR Board |

Clarification Needed:

- Is this decision authority matrix acceptable?

- Are there any decisions requiring additional approvals (e.g., Security, Compliance, Legal)?

- What is the escalation timeline (e.g., if no decision in 2 days, auto-escalate)?

Impact if Unanswered:
Decision paralysis, delayed escalations, team idle time, missed milestones.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: EPAM Delivery Manager + TMNAS CTO

### OQ-014: Risk Ownership & Mitigation Approval

Question: Who owns each risk, and who approves risk mitigation plans?

Context:
Project Charter identifies Top 10 risks (R-001 to R-010). Each risk has a proposed owner and mitigation strategy.

Clarification Needed:

- Confirm risk owners (EPAM DM, TMNAS PO, etc.) are acceptable and have authority to execute mitigation plans

- Who approves risk mitigation plans that require budget (e.g., adding buffer resources, extra testing cycles)?

- What is the risk escalation threshold (e.g., if risk probability or impact increases, escalate to Steering Committee)?

- Who approves risk acceptance (e.g., if mitigation is too costly, accept the risk)?

Impact if Unanswered:
Risks may not be mitigated effectively; unclear accountability for risk outcomes.

Priority: 🟡 MEDIUM
Workshop: IW2 (Day 2) + CW
Owner: EPAM Delivery Manager + TMNAS CTO

## CATEGORY 3: ARCHITECTURE & TECHNICAL (12 Questions)

### OQ-015: Architecture Modernization Strategy

Question: What is the approved architecture modernization strategy: Strangler Pattern, Big Bang, or Hybrid?

Options:

A) Strangler Pattern (Recommended):

- Gradually replace legacy components with modern equivalents

- Old and new systems coexist during transition

- Lower risk, incremental value delivery

- Example: Migrate UI module-by-module (Policy Management first, then Underwriting, then Claims)

B) Big Bang:

- Replace entire system at once

- High risk, long development cycle, single cutover

- Example: Rewrite entire RapidSure in React + Spring Boot microservices, deploy all at once

C) Hybrid:

- New features built on modern stack (React, REST APIs)

- Legacy features remain on old stack (JSF, SOAP) until business justifies migration

- Lower risk but creates technical complexity (maintaining two stacks)

Clarification Needed:

- Which strategy is approved for UI modernization (US-011)?

- Which strategy is approved for API layer (US-008)?

- Are there any architectural constraints that dictate strategy (e.g., regulatory requirements for gradual migration)?

Impact if Unanswered:
Technical approach may not align with TMNAS risk tolerance or business priorities; may require rework if strategy is rejected mid-project.

Priority: 🔴 CRITICAL
Workshop: IW2 (Day 2) + CW
Owner: EPAM Solution Architect + TMNAS CTO

### OQ-016: Technology Stack Constraints - What Must Stay vs. Can Change

Question: For each technology component, what is mandatory vs. negotiable?

Current Technology Stack:

| Component | Current State | Can Modernize? | Clarification Needed |
| --- | --- | --- | --- |
| App Server | JBoss/WildFly | ? | Can we migrate to Spring Boot standalone (embedded Tomcat), or must we keep JBoss? |
| Database | MS SQL Server | ? | Must we keep MS SQL Server, or can we consider Azure SQL, PostgreSQL? |
| UI Framework | JSF/IceFaces | ✅ YES (US-011) | Confirmed: Migrate to React/Angular |
| Integration Protocol | SOAP (primary) | ? | Can we migrate SOAP integrations to REST, or must SOAP be maintained? |
| API Gateway | Azure API Management | ? | Must we use Azure API Management, or can we consider alternatives (e.g., Kong, Apigee)? |
| Caching | Redis (Redisson) | ? | Keep Redis, or consider alternatives (e.g., Hazelcast, Memcached)? |
| Messaging | Azure Service Bus, JMS | ? | Keep Azure Service Bus, or modernize to Kafka, RabbitMQ? |
| Build Tools | Maven | ? | Keep Maven, or migrate to Gradle? |
| CI/CD | TBD (currently manual?) | ✅ YES (US-017) | Confirmed: Implement Jenkins/GitLab CI |

Clarification Needed:

- For each "?" component, confirm: Must keep, can modernize with approval, or can freely modernize?

- Are there any licensing, compliance, or vendor lock-in constraints?

Impact if Unanswered:
Technical decisions may be rejected mid-project, requiring rework; team may make assumptions that don't align with TMNAS constraints.

Priority: 🔴 CRITICAL
Workshop: IW2 (Day 2) + CW
Owner: EPAM Solution Architect + TMNAS CTO

### OQ-017: SOAP to REST Migration - In Scope or Out?

Question: Is migration of existing SOAP integrations to REST in scope for this project?

Current SOAP Integrations (from architecture diagram):

- CV Payment Portal → RapidSure (SOAP)

- CV Portal → RapidSure (SOAP, REJB, Rating Policy Info)

- FW Portal → RapidSure (SOAP)

- ODEN → RapidSure (SOAP)

- Producer Sync → RapidSure (SOAP)

- RapidSure → Configurator (SOAP)

Clarification Needed:

- Should US-008 (Business Layer API) include REST endpoints to replace SOAP integrations?

- Or should SOAP integrations remain as-is, and new Business Layer API is additive (doesn't replace SOAP)?

- If migration is in scope, which integrations are priority (all? subset)?

Impact if Unanswered:
Scope ambiguity for US-008; may lead to underestimation of effort if SOAP-to-REST migration is expected but not planned.

Priority: 🟠 HIGH
Workshop: IW2 (Day 2) + CW
Owner: EPAM Solution Architect + TMNAS Integration Team

### OQ-018: Business Layer API (US-008) - Detailed Scope

Question: What business capabilities should the Business Layer API (US-008) expose, and how many API endpoints approximately?

Possible Business Capabilities:

- Policy Management (create policy, update policy, cancel policy, renew policy)

- Rating (get quote, calculate premium, apply discounts)

- Underwriting (submit application, underwriting decision, risk assessment)

- Claims (file claim, update claim status, claim payment)

- Customer Management (create customer, update customer, search customer)

- Product Configuration (get product details, list available products)

Clarification Needed:

- Which business capabilities are priority for Phase 1 (6-month project)?

- How many API endpoints approximately (10? 50? 100+)? This impacts effort estimate.

- What is the primary use case: External partner integration? Mobile app backend? Internal system integration?

- What authentication/authorization is required (OAuth2, JWT, API keys)?

Impact if Unanswered:
US-008 effort (21 SP) may be significantly underestimated or overestimated; scope ambiguity may lead to scope creep.

Priority: 🔴 CRITICAL
Workshop: IW2 (Day 2) + CW
Owner: EPAM Solution Architect + TMNAS Product Owner

### OQ-019: UI Modernization (US-011) - Technology Choice

Question: Should UI be modernized to React or Angular (or other framework)?

Options:

A) React:

- Pros: Large ecosystem, flexible, good for complex UIs, EPAM has strong React expertise

- Cons: More opinionated setup required, JSX learning curve

B) Angular:

- Pros: Full-featured framework, TypeScript-native, good for enterprise apps, strong structure

- Cons: Steeper learning curve, more opinionated (less flexible)

C) Vue.js:

- Pros: Easy to learn, gentle learning curve, good documentation

- Cons: Smaller ecosystem than React/Angular, less enterprise adoption

Clarification Needed:

- What is TMNAS preference (React, Angular, other)?

- Are there any existing frontend standards at TMNAS (e.g., other projects using React)?

- Are there any constraints (e.g., must integrate with existing TMNAS design system, component library)?

Impact if Unanswered:
Team cannot start UI modernization work; technology choice impacts team composition (need React or Angular experts).

Priority: 🔴 CRITICAL
Workshop: IW2 (Day 2) + CW
Owner: EPAM Solution Architect + TMNAS CTO

### OQ-020: Database Optimization (US-010) - Performance Targets

Question: What are the current baseline and target performance metrics for database optimization?

Metrics to Define:

| Metric | Current Baseline | Target | How to Measure |
| --- | --- | --- | --- |
| Average Query Response Time | ? ms | ? ms | Database profiling tools |
| P95 Response Time | ? ms | ? ms | 95th percentile latency |
| Throughput (Transactions Per Second) | ? TPS | ? TPS | Load testing |
| Concurrent Users Supported | ? users | ? users | Load testing |
| Database CPU Utilization | ?% average | ?% | Redis monitoring |

Clarification Needed:

- Provide current baseline metrics (requires profiling current production system)

- Define target metrics (what performance improvement is acceptable? 20%? 50%? 2x?)

- Are there specific performance pain points (e.g., slow policy search, slow premium calculation)?

Impact if Unanswered:
US-010 success criteria are undefined; cannot validate if optimization is successful; may lead to disputes over "done".

Priority: 🔴 CRITICAL
Workshop: IW2 (Day 2) + CW
Owner: EPAM DBA + TMNAS DBA / Infrastructure Team

### OQ-021: SV Product Platform Upgrade - What's Actually In Scope?

Question: You said "SV implementation is out of scope, leave only upgrade SV to new platform." What does "upgrade SV to new platform" mean specifically?

Possible Interpretations:

A) Platform Readiness Only:

- Ensure Business Layer API (US-008) can support SV product business logic

- Ensure database schema can accommodate SV product data model

- Ensure UI framework (React/Angular) can support SV product UI screens

- No SV-specific development by EPAM; SV team migrates their code to new platform independently

B) SV Migration Support:

- EPAM helps SV team migrate their code from old platform to new platform

- Includes: Code refactoring, testing, deployment support

- Significant effort if this is in scope (was this captured in 202 SP estimate?)

C) Something else?

Clarification Needed:

- What exactly does "upgrade SV to new platform" entail?

- Is EPAM responsible for any SV-specific code changes, or only platform readiness?

- Are there specific deliverables related to SV support (e.g., API endpoints for SV, database tables for SV, UI components for SV)?

Impact if Unanswered:
Major scope ambiguity; US-015 and US-016 were removed, but unclear if SV-related work is lurking elsewhere in backlog.

Priority: 🔴 CRITICAL
Workshop: IW1 (Day 1) + CW
Owner: EPAM Delivery Manager + TMNAS SV Product Manager

### OQ-022: CCD System - What Is It?

Question: What does "CCD" stand for, and what is this system?

Context:
US-016 (CCD Integration) was removed from scope, but CCD is mentioned in architecture diagrams and discussions.

Clarification Needed:

- What does CCD stand for? (Central Claims Database? Customer Contact Database? Something else?)

- Is CCD an internal TMNAS system or external vendor system?

- Is CCD integration truly out of scope, or will it resurface as a dependency for other user stories (e.g., US-008 Business Layer API)?

- If out of scope now, when is CCD integration planned (Phase 2? Separate project)?

Impact if Unanswered:
Risk that CCD integration is assumed out of scope but later requested as "clarification" (Type 1 CR), leading to scope creep.

Priority: 🟡 MEDIUM
Workshop: CW (Client Workshop)
Owner: TMNAS Integration Team

### OQ-023: API Contracts for External Systems - When Provided?

Question: When will TMNAS provide API contracts (Swagger/OpenAPI specs) for external systems?

External Systems Requiring API Contracts:

- Salesforce RS Sync (REST API)

- Azure API Management (gateway configuration, policies)

- CCD (if applicable)

- Common Services

- Image Right

- Path

- Apps (Access PHLY)

Clarification Needed:

- Target date for API contract delivery: Sprint 2, Week 4 (April 29, 2026)?

- Who is responsible for providing contracts (TMNAS Integration Team, external vendors)?

- What if contracts are not ready by target date? (Use mocks? Delay integration development?)

- Are contracts stable, or do they change frequently (version control)?

Impact if Unanswered:
Integration development (US-008, US-009) may be blocked or developed based on assumptions that don't match actual APIs.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: TMNAS Integration Team

### OQ-024: Enterprise Architecture Landscape

Question: Can TMNAS provide a comprehensive enterprise architecture diagram showing RapidSure's place in the broader TMNAS system ecosystem?

Context:
Architecture diagrams provided show RapidSure and immediate integrations, but unclear how RapidSure fits in the bigger picture.

Clarification Needed:

- What other systems interact with RapidSure (directly or indirectly)?

- What are upstream systems (systems that call RapidSure)?

- What are downstream systems (systems that RapidSure calls)?

- Are there data flows, batch jobs, event streams we should be aware of?

- Are there enterprise standards (e.g., ESB, API gateway, data warehouse) that RapidSure must comply with?

Impact if Unanswered:
Risk of overlooking integration dependencies; may design APIs that don't align with enterprise architecture standards.

Priority: 🟡 MEDIUM
Workshop: CW (Client Workshop)
Owner: TMNAS Enterprise Architect

### OQ-025: Non-Functional Requirements (NFRs) - Complete Targets

Question: What are the complete non-functional requirements (performance, scalability, availability, disaster recovery, security, compliance)?

NFR Categories Needing Definition:

a) Performance:

- Response time targets (average, P95, P99)

- Throughput targets (TPS, concurrent users)

- Page load time targets (especially for UI modernization)

b) Scalability:

- Concurrent user targets (current, peak, future growth)

- Data volume targets (policies, transactions, records per year)

- Geographic scale (single region, multi-region?)

c) Availability:

- Uptime SLA (99%? 99.9%? 99.99%?)

- Maintenance windows (allowed downtime for deployments?)

- Zero-downtime deployment required?

d) Disaster Recovery:

- RPO (Recovery Point Objective): How much data loss is acceptable? (1 hour? 24 hours?)

- RTO (Recovery Time Objective): How quickly must system recover? (4 hours? 24 hours?)

- Backup frequency (daily? real-time replication?)

e) Security & Compliance:

- Data privacy requirements (PII handling, GDPR, CCPA)

- Insurance regulatory compliance (state-specific regulations?)

- Audit logging requirements (what must be logged and retained?)

- Penetration testing requirements

Clarification Needed:

- Provide specific, measurable targets for each NFR category

- Who is responsible for validating NFRs (EPAM, TMNAS, 3rd party)?

Impact if Unanswered:
System may not meet TMNAS expectations for performance, availability, or compliance; may require costly rework post-deployment.

Priority: 🔴 CRITICAL
Workshop: CW (Client Workshop)
Owner: TMNAS CTO + TMNAS Architecture Team

### OQ-026: Performance Testing - Who Executes, When, How?

Question: Who is responsible for performance testing execution, when does it occur, and what are the pass/fail criteria?

Context:
Project Charter states TMNAS is responsible for performance testing execution (likely with external vendor).

Clarification Needed:

- Who executes performance tests (TMNAS team, 3rd party vendor, EPAM ad-hoc support)?

- When does performance testing occur (before every release? before UAT? before go-live only)?

- What is EPAM's role (create performance test scripts? provide support during test execution? fix performance issues found)?

- What are pass/fail criteria (e.g., must support 500 concurrent users with <2 sec response time)?

- What happens if performance tests fail (EPAM fixes issues within warranty? Requires additional budget?)

Impact if Unanswered:
Unclear accountability for performance; risk that performance issues are found late and blamed on EPAM, requiring unplanned effort to fix.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: TMNAS QA Manager + EPAM DevOps Lead

### OQ-027: Security Testing - Who Executes, Standards, Requirements?

Question: Who is responsible for security testing, what security standards must be met, and is penetration testing required?

Context:
Project Charter states TMNAS is responsible for security testing execution.

Clarification Needed:

- Who executes security testing (TMNAS Security Team, 3rd party vendor, EPAM)?

- What security standards must be met (OWASP Top 10, PCI-DSS for payment data, state insurance regulations)?

- Is penetration testing required? If yes, when (before UAT? before go-live?)

- What is EPAM's role (follow secure coding practices? fix security vulnerabilities found? provide security documentation)?

- What are pass/fail criteria for security (e.g., zero critical vulnerabilities, all OWASP Top 10 mitigated)?

Impact if Unanswered:
Risk of security vulnerabilities in production; unclear who pays to fix security issues found post-deployment.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: TMNAS Security Team + EPAM Solution Architect

## CATEGORY 4: BUSINESS CONTEXT & SUCCESS METRICS (5 Questions)

### OQ-028: Company Background Validation

Question: Validate our understanding of TMNAS company background and business context.

Current Understanding (from market research):

- TMNAS is a regional/national insurance carrier specializing in Personal Lines (auto, home, renters, etc.)

- RapidSure is TMNAS's core policy administration platform for Personal Lines

- SV Product is a new product line (possibly specialty vehicle insurance?) currently delayed due to platform limitations

- Business Challenge: Need to accelerate time-to-market for new products to remain competitive

Clarification Needed:

- Is this understanding accurate?

- What is TMNAS's market position (top 10 in region? niche player?)?

- Who are TMNAS's main competitors, and how do they compare in digital capabilities?

- What is the strategic importance of SV product to TMNAS (revenue target, market share goal)?

Impact if Unanswered:
Misalignment with TMNAS business priorities; may deliver technically sound solution that doesn't address key business pain points.

Priority: 🟡 MEDIUM
Workshop: CW (Client Workshop)
Owner: TMNAS CIO / Business Strategy Team

### OQ-029: Top 3 Business Outcomes

Question: What are the top 3 business outcomes TMNAS wants to achieve with this platform modernization project?

Possible Outcomes:

- Launch SV product within 6 months of project completion

- Reduce time-to-market for new products by 40%

- Reduce operational costs by 25% through automation and reduced technical debt

- Improve customer satisfaction scores by 20% through better UX

- Enable digital distribution channels (mobile app, online portal, partner portals)

- Support business growth (target: $X revenue, X% market share increase)

Clarification Needed:

- What are the top 3 outcomes in priority order?

- Are these outcomes measurable (with specific targets and timelines)?

- How will success be measured (KPIs, metrics, reporting)?

Impact if Unanswered:
Project may deliver technical excellence but miss business objectives; unclear how to prioritize trade-offs (e.g., speed vs. quality).

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: TMNAS CIO + EPAM Delivery Manager

### OQ-030: Success Metrics & KPIs - Baselines & Targets

Question: What are the specific, measurable success metrics with current baselines and target values?

Proposed Success Metrics (from Project Charter):

| Metric Category | Metric | Current Baseline | Target | Measurement Method |
| --- | --- | --- | --- | --- |
| Technical | Business Layer API operational | N/A (doesn't exist) | ≥85% test coverage | Automated tests |
| Technical | UI modernization complete | JSF/IceFaces (100%) | React/Angular (100% in-scope modules) | Module migration tracker |
| Technical | Database performance | ? (TBD) | ? (TBD) | Load testing |
| Technical | CI/CD pipeline | Manual deployment (? hours) | <30 min build-to-deploy | Pipeline monitoring |
| Technical | Production defects | ? defects per release | Zero P1/P2 for 30 days | Defect tracking |
| Business | Delivery velocity | ? SP per sprint | +25% (? SP per sprint) | Velocity chart |
| Business | Time-to-market | ? months per product | -40% (? months) | Release tracking |
| Business | Cost of change | $? per feature | -25% ($?) | Cost tracking |
| AI Adoption | Team AI adoption | 0% (no AI tools) | ≥70% active usage | Usage analytics |
| AI Adoption | Code review time | ? hours per review | -30% (? hours) | Time tracking |
| Partnership | Client satisfaction | ? (current score) | ≥4.5/5.0 | Monthly surveys |

Clarification Needed:

- Fill in all "?" with actual baseline and target values

- Confirm measurement methods are acceptable

- Define reporting frequency (weekly, monthly, quarterly)

Impact if Unanswered:
Cannot demonstrate project success objectively; risk of disputes over whether project met expectations.

Priority: 🔴 CRITICAL
Workshop: CW (Client Workshop)
Owner: TMNAS Product Owner + EPAM Delivery Manager

### OQ-031: Time-to-Market Baseline & Target

Question: What is the current time-to-market for launching a new insurance product, and what is the target after platform modernization?

Clarification Needed:

- Current baseline: How long does it take today to launch a new product (e.g., SV product)? From concept to production? (6 months? 12 months? 18 months?)

- Breakdown: How much time is spent in each phase (requirements, development, testing, regulatory approval, deployment)?

- Target: What is acceptable time-to-market after modernization? (50% reduction? 60%? Specific target like 3 months?)

- Bottlenecks: What are the main bottlenecks today (technical platform limitations, regulatory approval, testing, deployment)?

Impact if Unanswered:
Cannot demonstrate business value of modernization; unclear if project is addressing the right bottlenecks.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: TMNAS Product Owner + Business Strategy Team

### OQ-032: Competitive Landscape & Digital Maturity

Question: How does TMNAS compare to competitors in digital capabilities and platform maturity?

Clarification Needed:

- Who are TMNAS's top 3-5 competitors in the Personal Lines insurance market?

- How do competitors' platforms compare (modern cloud-native? legacy monoliths like RapidSure? hybrid)?

- What digital capabilities do competitors have that TMNAS lacks (e.g., mobile apps, AI-powered underwriting, instant quotes)?

- What is TMNAS's digital maturity level (Gartner scale: Level 1 Initial, Level 2 Managed, Level 3 Defined, Level 4 Quantitatively Managed, Level 5 Optimizing)?

Impact if Unanswered:
May not prioritize modernization initiatives that provide competitive advantage; may focus on wrong areas.

Priority: 🟡 MEDIUM
Workshop: CW (Client Workshop)
Owner: TMNAS Business Strategy Team

## CATEGORY 5: DEPENDENCIES & RISKS (6 Questions)

### OQ-033: Program Dependencies - What Other Projects Impact RapidSure Modernization?

Question: You mentioned "it is part of bigger program. But we must design and implement as separate project and SOW, but it will have dependencies to projects in the program." What are those dependencies?

Clarification Needed:

- What is the broader program that RapidSure modernization is part of (e.g., "TMNAS Digital Transformation Program")?

- What other projects are in the program?

- What are the specific dependencies (e.g., shared infrastructure, shared data, integration points, resource sharing)?

- What is the governance structure (program steering committee, program manager, dependency tracking)?

- What happens if other projects are delayed (impact on RapidSure modernization timeline)?

Impact if Unanswered:
Risk of unexpected delays due to dependencies on other projects; may need to adjust timeline or scope.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: TMNAS Program Manager

### OQ-034: SV Product Release Schedule - Detailed Timeline

Question: What is the detailed SV product release schedule, and how must RapidSure modernization align with it?

Context:
Project Charter states: "Must align delivery milestones with TMNAS SV product release schedule (6-week release cadence)."

Clarification Needed:

- What is the SV product release schedule for 2026 (specific dates)?

- What is the release cadence (6 weeks = ~8-9 releases per year)?

- Which RapidSure modernization milestones must align with SV releases (e.g., US-008 Business Layer API must be ready by Release X)?

- What are the integration points between RapidSure modernization and SV product (API contracts, database schema, deployment coordination)?

- What happens if RapidSure modernization is delayed (impact on SV product launch)?

Impact if Unanswered:
Risk of deployment conflicts, integration issues, or SV product delays blamed on RapidSure modernization team.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: TMNAS SV Product Manager + EPAM Delivery Manager

### OQ-035: Known Risks from Previous TMNAS Projects

Question: What are known risks or lessons learned from previous EPAM-TMNAS projects that we should consider?

Context:
EPAM has a 7-year relationship with TMNAS but has not yet achieved "trusted partnership" status. There may be historical issues that inform risk management for this project.

Clarification Needed:

- What went wrong in previous projects (scope creep, budget overruns, quality issues, communication gaps)?

- What went well in previous projects (best practices to replicate)?

- Are there specific stakeholders who are skeptical of EPAM (how to address concerns)?

- Are there any "third rail" topics or sensitive areas to avoid?

Impact if Unanswered:
May repeat past mistakes; may not build on past successes; may not address stakeholder concerns proactively.

Priority: 🟡 MEDIUM
Workshop: IW1 (Day 1) - EPAM Account Manager provides history
Owner: EPAM Account Manager

### OQ-036: TMNAS Stakeholder Availability - Realistic Assessment

Question: What is the realistic availability of TMNAS stakeholders for this project, given their current workload and priorities?

Context:
Project Charter assumes:

- Product Owner: 50% allocation (20 hours/week)

- SMEs: 10-20 hours/month per domain

- CTO (Prashant): Bi-weekly architecture reviews + CR Board

- CIO (Lana): Monthly steering committee

Clarification Needed:

- Is 50% PO allocation realistic, given other responsibilities?

- What are other competing priorities for key stakeholders (other projects, operational issues, fiscal year-end activities)?

- Are there any blackout periods (holidays, insurance renewal season, fiscal year-end, board meetings)?

- What is the backup plan if key stakeholders are unavailable (delegates, escalation, asynchronous decisions)?

Impact if Unanswered:
Risk of over-optimistic assumptions about stakeholder availability; may lead to blocked decisions and delayed sprints.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: TMNAS Product Owner + CTO

### OQ-037: Access Requirements - What Clearances, VPNs, Training Needed?

Question: What access requirements, security clearances, background checks, or training are needed for EPAM team members?

Clarification Needed:

- Do EPAM team members require background checks (credit check, criminal background check)?

- Are there any security clearances required (especially for insurance data, PII)?

- What VPN or network access is required (how is it provisioned, how long does it take)?

- Are there any mandatory training courses (TMNAS onboarding, security training, compliance training)?

- Are there any geographic restrictions (e.g., data cannot leave US, EU data residency requirements)?

Impact if Unanswered:
Delays in team onboarding (weeks or months for background checks); risk of team members being unable to access systems.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: TMNAS IT Security + HR

### OQ-038: Third-Party Vendor Coordination - Who, What, When?

Question: What third-party vendors are involved, and how do we coordinate with them?

Known Third-Party Vendors:

- UAT Testing Vendor (name TBD) - Executes UAT

- Performance Testing Vendor (name TBD, possibly same as UAT vendor) - Executes performance/load testing

- Security Testing / Penetration Testing Vendor (name TBD) - Executes security assessments

- External System Vendors (Salesforce, Azure, CCD, Common Services, Image Right, Path, etc.) - Provide API contracts and system availability

Clarification Needed:

- Who are these vendors (names, contact info)?

- What is the coordination process (EPAM contacts vendors directly, or TMNAS coordinates)?

- What are vendor SLAs and response times (e.g., API contract delivery within 2 weeks of request)?

- What is the escalation process if vendors are unresponsive or delayed?

Impact if Unanswered:
Risk of delays due to vendor issues; unclear accountability for vendor management.

Priority: 🟡 MEDIUM
Workshop: CW (Client Workshop)
Owner: TMNAS Procurement + Integration Team

## CATEGORY 6: SCOPE VALIDATION (5 Questions)

### OQ-039: Backlog Review - Are 16 User Stories Correct & Complete?

Question: Review the 16 user stories (202 SP) in the product backlog. Are they correct, complete, and aligned with TMNAS priorities?

Current Backlog (16 Stories, 202 SP):

- US-001: Strategic Planning & Roadmap (13 SP)

- US-002: Unified Delivery Framework (13 SP)

- US-003: AI-Enhanced Estimation & Change Control (8 SP)

- US-004: Requirements Quality Improvement (8 SP)

- US-005: Centralized Knowledge Library (8 SP)

- US-006: QA Shift-Left (13 SP)

- US-007: Technical Debt Management (8 SP)

- US-008: Business Layer API Implementation (21 SP) - CRITICAL

- US-009: Product Configuration API (13 SP)

- US-010: Database Optimization (21 SP) - CRITICAL

- US-011: UI Modernization (21 SP)

- US-012: Code Analysis Agent (13 SP)

- US-013: Knowledge Base Agent (13 SP)

- US-014: Coverage Analysis Agent (8 SP)

- US-017: CI/CD Pipeline (13 SP)

- US-018: Environment Automation (8 SP)

Clarification Needed:

- Are there any missing user stories (gaps in scope)?

- Are there any user stories that are lower priority and can be deferred to Phase 2?

- Are story point estimates reasonable (need refinement workshops to validate)?

- Are dependencies between stories correct?

Impact if Unanswered:
Risk of scope gaps or misaligned priorities; may deliver wrong things or miss critical functionality.

Priority: 🔴 CRITICAL
Workshop: IW2 (Day 2) - Internal backlog review + CW - Client validation
Owner: EPAM Delivery Manager + TMNAS Product Owner

### OQ-040: MVP Definition - 6-Month vs. 9-Month Scope

Question: What is the Minimum Viable Product (MVP) for the 6-month option, and what additional scope is included in the 9-month option?

Current Assumption:

- 6-month MVP: All 16 user stories (202 SP)

- 9-month additional scope: ~148 SP TBD (possible items: historical data migration, additional UI modules, MSP team setup, more AI agents)

Clarification Needed:

- Is the 16-story backlog truly MVP (minimum to achieve business objectives), or can some stories be deferred?

- What are the "must-have" vs. "nice-to-have" stories for 6-month option?

- What specific additional scope should be included in 9-month option (provide user story ideas for workshop discussion)?

Impact if Unanswered:
Risk of over-scoping 6-month option (may not deliver on time); unclear value proposition for 9-month option.

Priority: 🔴 CRITICAL
Workshop: IW2 (Day 2) + CW
Owner: EPAM Delivery Manager + TMNAS Product Owner

### OQ-041: Out-of-Scope Validation

Question: Review the out-of-scope list. Are there any items that TMNAS expects to be in scope but are currently listed as out-of-scope?

Current Out-of-Scope List (from Project Charter):

- SV Product implementation

- CCD integration

- Historical data migration (6-month; possible in 9-month)

- End-user training

- Production L1/L2/L3 support post-warranty (6-month; possible MSP setup in 9-month)

- Performance test execution (TMNAS responsibility)

- Security test execution (TMNAS responsibility)

- UAT test execution (TMNAS responsibility)

- Infrastructure provisioning (TMNAS responsibility)

- License procurement (TMNAS provides via VDI)

- Integration with systems beyond those specified

- Salesforce customization

- Third-party vendor system modifications

Clarification Needed:

- Are there any surprises in this list (items TMNAS expected to be in scope)?

- Are there any items that should be moved to in-scope (requires scope and budget adjustment)?

- Are there any items missing from this list (should be explicitly called out)?

Impact if Unanswered:
Risk of scope disputes mid-project; TMNAS may request "out-of-scope" work and expect it to be included.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: EPAM Delivery Manager + TMNAS Product Owner

### OQ-042: Modernization Project Scope - Foundation for Platform Team

Question: You mentioned "modernization project which allow scalability of SV product releases. It's scope is unclear." Can you clarify what this means?

Context:
This seems to refer to the broader platform modernization initiative that creates the foundation for EPAM's future platform ownership team.

Clarification Needed:

- Is this "modernization project" the same as the current "Project Rambo" (6-month or 9-month option)?

- Or is there a separate "modernization project" with unclear scope that will be defined later?

- What does "allow scalability of SV product releases" mean specifically (technical capabilities, team structure, processes)?

- What is the relationship between this modernization project and the future MSP team?

Impact if Unanswered:
Major scope ambiguity; risk of misaligned expectations about what this project delivers vs. what comes later.

Priority: 🔴 CRITICAL
Workshop: IW1 (Day 1) + CW
Owner: EPAM Delivery Manager + TMNAS CTO

### OQ-043: Phase 2 Scope Ideas (9-Month Option)

Question: If TMNAS chooses the 9-month option ($1.8M), what should be included in Phase 3 (Months 7-9, ~148 SP)?

Possible Phase 3 Scope Ideas:

A) Data Migration:

- Historical data migration from legacy systems to modernized RapidSure

- Data quality assessment and cleanup

- Migration testing and validation

B) Additional UI Modules:

- Modernize additional RapidSure modules not included in Phase 1-2

- Extend UI modernization to admin/back-office screens

- Mobile app development (if applicable)

C) MSP Team Setup:

- Establish L3 Managed Services team structure

- Define operational runbooks and SLAs

- Implement monitoring and alerting

- Conduct knowledge transfer to MSP team

D) Advanced Integrations:

- CCD integration (if CCD is ready)

- Additional external system integrations

- Event-driven architecture (Kafka/Azure Service Bus)

E) More AI Agents:

- Additional CodeMie agents (e.g., Documentation Agent, Deployment Agent)

- AI-powered test data generation

- AI-powered performance optimization

F) Advanced Features:

- Advanced analytics and reporting

- Business intelligence dashboards

- API monetization capabilities

Clarification Needed:

- Which of these ideas are priority for Phase 3?

- Are there other ideas not listed here?

- What is the rough prioritization (must-have vs. nice-to-have for Phase 3)?

Impact if Unanswered:
Cannot finalize 9-month proposal; unclear value proposition for additional $1.2M investment beyond 6-month option.

Priority: 🟠 HIGH (if 9-month option is under consideration)
Workshop: IW2 (Day 2) + CW
Owner: EPAM Delivery Manager + TMNAS Product Owner

## CATEGORY 7: TESTING & QUALITY (6 Questions)

### OQ-044: UAT Test Case Creation - Who Creates, Approves, Maintains?

Question: Who is responsible for creating UAT test cases, who approves them, and who maintains them over time?

Options:

A) TMNAS Business Analysts:

- TMNAS BAs create test cases based on business requirements

- Pros: Business-aligned, TMNAS ownership

- Cons: May not cover technical edge cases

B) 3rd Party UAT Vendor:

- Vendor creates test cases based on requirements

- Pros: Professional test design, independent validation

- Cons: May not understand TMNAS business context deeply

C) EPAM Quality Assurance Team:

- EPAM QA creates test cases during user story development

- Pros: Technical depth, early test planning

- Cons: May not cover all business scenarios

D) Collaborative Approach:

- EPAM QA creates initial test cases, TMNAS BA reviews and adds business scenarios, UAT vendor executes

- Pros: Best of all approaches

- Cons: More coordination overhead

Clarification Needed:

- Which approach is preferred?

- Who has final approval of test cases before UAT?

- How are test cases maintained (versioning, updates for new releases)?

Impact if Unanswered:
Risk of inadequate UAT coverage; disputes over who is responsible for missed test scenarios.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: TMNAS UAT Lead + EPAM QA Lead

### OQ-045: Defect Severity Classification - Who Decides?

Question: Who has authority to classify defect severity (P1/P2/P3/P4), and what is the escalation process for disputes?

Proposed Severity Definitions:

- P1 (Critical): System down, no workaround, blocks all users (e.g., application won't start, database corruption)

- P2 (High): Major functionality broken, workaround exists, blocks many users (e.g., policy creation fails, premium calculation incorrect)

- P3 (Medium): Minor functionality issue, workaround exists, impacts few users (e.g., UI formatting issue, non-critical field validation)

- P4 (Low): Cosmetic issue, no functional impact (e.g., typo, minor UI inconsistency)

Clarification Needed:

- Who classifies defects initially (QA engineer who finds it, UAT tester, product owner)?

- Who has authority to change severity classification (e.g., UAT vendor reports P1, EPAM disputes and says it's P2)?

- What is the escalation process for severity disputes (CR Board? Steering Committee?)?

- What are the SLAs for each severity (e.g., P1: 4-hour response, 24-hour resolution)?

Impact if Unanswered:
Risk of disputes over defect priorities; EPAM may be pressured to treat all defects as P1/P2, impacting velocity and morale.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: TMNAS UAT Lead + EPAM QA Lead

### OQ-046: Test Data - Who Provides, How Much, How Managed?

Question: Who is responsible for test data creation, how much test data is needed, and how is it managed (refresh, privacy, security)?

Clarification Needed:

- Who creates test data? (TMNAS provides production-like data? EPAM generates synthetic data? 3rd party tool?)

- How much test data? (# of policies, customers, transactions needed for realistic testing)

- Data privacy: If using production data, how is PII masked/anonymized?

- Data refresh: How often is test data refreshed (weekly, monthly, on-demand)?

- Data management: Who manages test data (provisioning, cleanup, backup)?

Impact if Unanswered:
Risk of inadequate test coverage due to insufficient or unrealistic test data; risk of PII exposure if production data is used improperly.

Priority: 🟡 MEDIUM
Workshop: CW (Client Workshop)
Owner: TMNAS DBA + EPAM QA Lead

### OQ-047: Regression Testing Strategy

Question: What is the regression testing strategy? Full regression every sprint? Selective regression? Automated regression?

Options:

A) Full Manual Regression Every Sprint:

- Pros: High confidence, catches regressions

- Cons: Time-consuming, expensive, may slow sprint velocity

B) Selective Regression (Risk-Based):

- Only test areas impacted by current sprint changes

- Pros: Faster, more efficient

- Cons: May miss regressions in "untouched" areas

C) Automated Regression:

- Build automated regression test suite, run every sprint (or every commit via CI/CD)

- Pros: Fast, repeatable, scales well

- Cons: Upfront investment in automation

D) Hybrid:

- Automated regression for core workflows, selective manual regression for high-risk areas

- Pros: Balanced approach

- Cons: Requires coordination

Clarification Needed:

- Which approach is preferred?

- If automation, what is the target automation coverage (70%? 80%? 90%)?

- Who maintains automated tests (EPAM QA? TMNAS QA?)?

Impact if Unanswered:
Risk of regressions slipping into production; unclear QA effort and timeline.

Priority: 🟡 MEDIUM
Workshop: CW (Client Workshop)
Owner: EPAM QA Lead + TMNAS UAT Lead

### OQ-048: Production Deployment Process & Rollback Plan

Question: What is the production deployment process, and what is the rollback plan if deployment fails?

Clarification Needed:

- Deployment window: When can production deployments occur (weekends? off-hours? maintenance windows)?

- Deployment process: Who executes deployment (TMNAS Ops? EPAM? Joint?)

- Approval gates: Who approves production deployment (CAB? CTO? CIO?)

- Smoke testing: What smoke tests must pass before declaring deployment successful?

- Rollback plan: If deployment fails, how quickly can system be rolled back? (15 min? 1 hour? 4 hours?)

- Rollback decision: Who decides to rollback (EPAM? TMNAS? Joint?)

Impact if Unanswered:
Risk of failed deployments impacting production; unclear accountability and decision-making during incidents.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: TMNAS Operations Team + EPAM DevOps Lead

### OQ-049: Code Coverage Tool & Reporting

Question: What code coverage tool will be used, and how will coverage be reported and tracked?

Options:

- JaCoCo (Java code coverage, common with Maven/Gradle)

- SonarQube (comprehensive code quality and coverage)

- Cobertura (older Java coverage tool)

- Istanbul/NYC (JavaScript coverage for frontend)

Clarification Needed:

- Which tool is preferred (TMNAS standard, or EPAM recommends)?

- What is the target code coverage (≥85% confirmed in DoD)?

- How is coverage reported (SonarQube dashboard? Jenkins plugin? HTML reports)?

- Is coverage tracked over time (trend analysis, coverage decay alerts)?

- Who reviews coverage reports (tech lead, architect, QA lead)?

Impact if Unanswered:
Inconsistent code coverage measurement; may not catch low-coverage areas.

Priority: 🟡 MEDIUM
Workshop: IW2 (Day 2) - EPAM technical team decides
Owner: EPAM Technical Lead + QA Lead

## CATEGORY 8: DELIVERY FRAMEWORK (6 Questions)

### OQ-050: Sprint Length Confirmation

Question: Confirm 2-week sprint length is acceptable to TMNAS.

Context:
Project Charter assumes 2-week sprints (10 working days). This is industry standard for Agile teams.

Alternative Options:

- 1-week sprints: Faster feedback, more frequent releases, but more ceremony overhead

- 3-week sprints: Less ceremony overhead, but slower feedback and longer time between releases

Clarification Needed:

- Is 2-week sprint length acceptable?

- Are there any TMNAS organizational constraints (e.g., existing teams use 3-week sprints, must align)?

Impact if Unanswered:
Minor, but may require timeline adjustments if sprint length changes.

Priority: 🟡 MEDIUM
Workshop: CW (Client Workshop)
Owner: TMNAS Product Owner + EPAM Delivery Manager

### OQ-051: Sprint Start Day (Monday or Wednesday?)

Question: What day of the week should sprints start?

Options:

- Monday: Traditional start of work week; Sprint Planning on Monday, Sprint Review/Retro on Friday

- Wednesday: Avoids Monday holidays; Sprint Planning on Wednesday, Sprint Review/Retro on Tuesday

Clarification Needed:

- TMNAS preference?

- Any organizational constraints (e.g., TMNAS does all planning meetings on Tuesdays)?

Impact if Unanswered:
Minor, but affects meeting schedules and team coordination.

Priority: 🟡 MEDIUM (Low impact)
Workshop: CW (Client Workshop)
Owner: EPAM Scrum Master + TMNAS Product Owner

### OQ-052: Definition of Ready (DoR) - Client Agreement

Question: Does TMNAS agree with the proposed Definition of Ready (DoR) criteria?

Proposed DoR (from Project Charter):

- User story has clear, testable acceptance criteria (Given-When-Then)

- Dependencies identified and documented

- Story sized and estimated (fits in one sprint)

- Technical design approach agreed

- Test approach defined

- No open questions blocking implementation

- UI/UX mockups available (if applicable)

- API contracts available (if applicable)

Clarification Needed:

- Is this DoR acceptable, or does TMNAS want to add/remove criteria?

- Who enforces DoR (Product Owner, Scrum Master, team vote)?

Impact if Unanswered:
Risk of poorly defined stories entering sprints, leading to rework and delays.

Priority: 🟡 MEDIUM
Workshop: CW (Client Workshop)
Owner: TMNAS Product Owner + EPAM Scrum Master

### OQ-053: Definition of Done (DoD) - Client Agreement

Question: Does TMNAS agree with the proposed Definition of Done (DoD) criteria?

Proposed DoD (from Project Charter):

- Code complete and peer-reviewed

- Unit tests written (≥85% coverage)

- Integration tests passed

- Code merged to main branch

- Static code analysis passed (no critical/high issues)

- Technical documentation updated

- Acceptance criteria validated

- No P1/P2 defects open

- Deployed to QA environment

- Demo-ready

- Product Owner acceptance

Clarification Needed:

- Is this DoD acceptable, or does TMNAS want to add/remove criteria?

- Who signs off on "Done" (Product Owner in Sprint Review)?

Impact if Unanswered:
Risk of incomplete stories being marked "Done," leading to technical debt and quality issues.

Priority: 🟡 MEDIUM
Workshop: CW (Client Workshop)
Owner: TMNAS Product Owner + EPAM Delivery Manager

### OQ-054: Velocity Baseline - Historical Data

Question: What is the historical velocity (story points per sprint) of teams working on RapidSure?

Context:
Proposed backlog assumes velocity of 20-22 SP per sprint for a team of 17 FTE. This is based on industry standards (~1.2-1.3 SP per person per sprint).

Clarification Needed:

- What was the velocity of previous EPAM teams working on RapidSure?

- What was the velocity of TMNAS internal teams or other vendors?

- Are there any known factors that may impact velocity (e.g., platform complexity, frequent production incidents)?

Impact if Unanswered:
Risk of overestimating velocity, leading to missed sprint commitments and timeline delays.

Priority: 🟡 MEDIUM
Workshop: IW1 (Day 1) - EPAM Account Manager provides history
Owner: EPAM Account Manager + Delivery Manager

### OQ-055: Communication Tools - What Does TMNAS Use?

Question: What communication and collaboration tools does TMNAS use, and will EPAM team have access?

Typical Tools:

- Project Management: Jira, Azure DevOps, Monday.com, Asana?

- Communication: Slack, Microsoft Teams, Email?

- Documentation: Confluence, SharePoint, Google Docs?

- Version Control: Git (GitHub, GitLab, Bitbucket, Azure Repos)?

- CI/CD: Jenkins, GitLab CI, Azure Pipelines, CircleCI?

- Video Conferencing: Zoom, Microsoft Teams, Google Meet?

Clarification Needed:

- What tools does TMNAS use (provide list)?

- Will EPAM team have full access to all tools?

- Are there any tool procurement or licensing requirements for EPAM team?

- What is the timeline for tool access provisioning (Sprint 0)?

Impact if Unanswered:
Risk of delays in team onboarding if tool access takes weeks to provision.

Priority: 🟠 HIGH
Workshop: CW (Client Workshop)
Owner: TMNAS IT / Tools Administrator

## CATEGORY 9: PROJECT IDENTIFICATION (7 Questions - All from Q41-Q47)

### OQ-056: Project Name - Official Name

Question: What is the official project name?

Current Working Name: "TMNAS - Project Rambo"

Clarification Needed:

- Is "Project Rambo" the official name, or is it a code name?

- Does TMNAS have a different naming convention (e.g., "TMNAS-2026-Platform-Modernization")?

- Will this name be used in contracts, SOWs, and public communications?

Priority: 🟡 MEDIUM
Workshop: IW1 (Day 1)
Owner: EPAM Delivery Manager + TMNAS Product Owner

### OQ-057: Project Code / ID

Question: Does EPAM or TMNAS have an internal project code or ID for this initiative?

Clarification Needed:

- EPAM project code (for time tracking, billing, resource allocation)

- TMNAS project code (for budget tracking, portfolio management)

Priority: 🟡 MEDIUM
Workshop: IW1 (Day 1)
Owner: EPAM Account Manager + TMNAS Finance

### OQ-058: Contract / SOW Number

Question: Do we have a contract or SOW number yet, or is this pre-contract?

Clarification Needed:

- If pre-contract: When is contract signing expected?

- If contract exists: What is the contract number (for reference in documents)?

Priority: 🟡 MEDIUM
Workshop: IW1 (Day 1)
Owner: EPAM Legal + TMNAS Procurement

### OQ-059: Project Start Date - Confirmed

Question: Confirm project start date is April 1, 2026.

Context:
Project Charter uses April 1, 2026 as assumption, but not confirmed.

Clarification Needed:

- Is April 1, 2026 confirmed, or is it tentative pending contract signing?

- Are there any constraints that may shift start date (budget approval, resource availability)?

Priority: 🔴 CRITICAL
Workshop: IW1 (Day 1) + CW
Owner: EPAM Delivery Manager + TMNAS Product Owner

### OQ-060: EPAM Team Names & Roles

Question: Who are the EPAM team members (names, roles, contact info)?

Roles to Fill:

- Delivery Manager / Program Manager

- Solution Architect

- Technical Lead / Team Lead

- Business Analyst

- QA Lead

- DevOps Lead

- Scrum Master (if separate from DM)

- Account Manager

Clarification Needed:

- Provide names and contact info for all roles

- Confirm availability and start dates

- Identify any roles that are still being recruited

Priority: 🔴 CRITICAL
Workshop: IW1 (Day 1)
Owner: EPAM Resource Manager + Delivery Manager

## END OF OPEN QUESTIONS LIST

### SUMMARY STATISTICS

- Total Questions: 60

- CRITICAL Priority: 21 questions

- HIGH Priority: 24 questions

- MEDIUM Priority: 15 questions

By Workshop:

- Internal Workshop Day 1 (IW1): 12 questions

- Internal Workshop Day 2 (IW2): 8 questions

- Internal Workshop Day 3 (IW3): 0 questions (all questions assigned to IW1/IW2 or CW)

- Client Workshop (CW): 40 questions (many overlap with IW questions for validation)

### NEXT STEPS

- Internal Workshop (3 days):

  - Day 1: Answer IW1 questions (EPAM-internal decisions)

  - Day 2: Answer IW2 questions (EPAM technical decisions, backlog refinement)

  - Day 3: Finalize internal proposal, prep for client workshop

- Client Workshop (2-3 days):

  - Present Project Charter and Open Questions to TMNAS stakeholders

  - Collaborate to answer CW questions

  - Finalize scope, budget, timeline, and success criteria

- Update Documents:

  - Incorporate all answers into Project Charter v3.0

  - Update Product Backlog with refined estimates

  - Create final SOW and contract

- Contract Signing & Kickoff:

  - Sign contract

  - Begin Sprint 0 (April 1, 2026)