## TMNAS - PROJECT RAMBO

## PROJECT BASELINE DOCUMENT

Version: 1.0
Baseline Date: March 20, 2026 (Post-Internal Workshop)
Project Start Date: April 1, 2026
Project End Date: September 30, 2026 (6-month) or December 31, 2026 (9-month)
Status: Draft - Pending Client Workshop Approval

### VERSION CONTROL

| Version | Date | Author | Changes | Approved By |
| --- | --- | --- | --- | --- |
| 1.0 | March 20, 2026 | EPAM Delivery Manager | Initial baseline post-internal workshop | Internal Review |
| 2.0 (Planned) | April 1, 2026 | EPAM Delivery Manager | Final baseline post-client workshop approval | TMNAS CIO/CTO + EPAM Account Manager |

## 1. BASELINE OVERVIEW

### 1.1 Purpose of Baseline

This Project Baseline Document establishes the reference point for measuring project performance throughout the TMNAS Project Rambo engagement. The baseline includes: - Scope Baseline - What will be delivered (16 user stories, 202 story points) - Schedule Baseline - When it will be delivered (timeline, milestones) - Cost Baseline - How much it will cost ($675K or $1.8M)

For a Fixed Fee project, the baseline is CRITICAL to: - Define contractual commitments (deliverables, dates, budget) - Measure project performance (earned value, variance analysis) - Control changes (via Change Request process) - Protect both parties (EPAM and TMNAS) from scope creep and misunderstandings

### 1.2 Baseline Approval

This baseline will be formally approved by: - TMNAS Executive Sponsor (CIO): Lana - Approves business objectives, budget, timeline - TMNAS Project Sponsor (CTO): Prashant - Approves technical approach, scope, architecture - TMNAS Product Owner: TBD - Approves detailed scope (user stories, acceptance criteria) - EPAM Account Manager: TBD - Approves EPAM commercial commitments - EPAM Delivery Manager: TBD - Approves EPAM delivery commitments

Approval Process: 1. March 17-19, 2026: Internal workshop refines baseline (EPAM team) 2. March 20, 2026: Baseline v1.0 finalized (internal approval) 3. Late March/Early April 2026: Client workshop presents baseline to TMNAS 4. April 1, 2026: Baseline v2.0 approved and signed (TMNAS + EPAM executives) 5. April 1, 2026: Baseline becomes contractual commitment (project kickoff)

### 1.3 Baseline Change Control

Once approved, the baseline can only be changed through formal Change Request process: - Type 2 Changes (<5% budget impact): Approved by Change Control Board → Minor baseline version (v2.1, v2.2) - Type 3 Changes (>5% budget impact): Approved by Executive Sponsors + Contract Amendment → Major baseline version (v3.0, v4.0)

All baseline changes are documented, approved, and communicated to all stakeholders.

## 2. SCOPE BASELINE

### 2.1 Project Scope Statement

Project Rambo will modernize the TMNAS RapidSure platform to: - Enable rapid product launches (reduce time-to-market by 40%) - Support business growth through scalable architecture - Improve user experience via UI modernization (JSF/IceFaces → React/Angular) - Increase developer productivity through AI adoption (≥70% team adoption) - Establish mature delivery processes and governance frameworks

Out of Scope (Explicit Exclusions): - SV Product implementation (separate team, separate project) - CCD integration (removed from scope) - Historical data migration (6-month; possible 9-month Phase 3) - End-user training (TMNAS responsibility) - Production L1/L2/L3 support post-warranty (6-month; possible 9-month Phase 3) - Performance/security/UAT test execution (TMNAS responsibility) - Infrastructure provisioning (TMNAS responsibility)

### 2.2 Scope Baseline Summary

Total Scope: 16 User Stories, 202 Story Points

| Epic | User Stories | Story Points | % of Total |
| --- | --- | --- | --- |
| 1. Governance & SDLC | 3 | 34 | 17% |
| 2. Requirements & Solutioning | 2 | 16 | 8% |
| 3. Development & QA | 2 | 21 | 10% |
| 4. Deployment & Infrastructure | 2 | 21 | 10% |
| 5. Platform Modernization | 4 | 76 | 38% |
| 6. AI Adoption | 3 | 34 | 17% |
| TOTAL | 16 | 202 | 100% |

### 2.3 Detailed Scope Baseline

#### Epic 1: Governance & SDLC (34 Story Points)

US-001: Strategic Planning & Roadmap Implementation (13 SP) - Sprint: 1-2 - Deliverable: Strategic planning framework, 12-month product roadmap, OKR tracking system - Acceptance Criteria: Framework documented, roadmap reviewed with stakeholders, OKRs defined for Q2-Q3 2026

US-002: Unified Delivery Framework Rollout (13 SP) - Sprint: 1-2 - Deliverable: Standardized Agile/Scrum delivery framework, process templates, training materials - Acceptance Criteria: Framework documented, templates created (sprint planning, review, retro), TMNAS team trained

US-003: AI-Enhanced Estimation & Change Control (8 SP) - Sprint: 2-3 - Deliverable: Story point estimation guidelines, formal Change Request process (Type 1/2/3), CR tracking log - Acceptance Criteria: Estimation guidelines documented, CR process approved by CR Board, CR log operational

#### Epic 2: Requirements & Solutioning (16 Story Points)

US-004: Requirements Quality Improvement Framework (8 SP) - Sprint: 3-4 - Deliverable: Definition of Ready (DoR) standards, user story templates, requirements quality checklist - Acceptance Criteria: DoR documented and approved, templates created, checklist used in backlog grooming

US-005: Centralized Knowledge Library (8 SP) - Sprint: 4-5 - Deliverable: Centralized knowledge repository (Confluence or similar), migrated documentation, search/tagging system - Acceptance Criteria: Repository operational, ≥80% existing docs migrated, search working

#### Epic 3: Development & QA (21 Story Points)

US-006: QA Shift-Left with AI Test Generation (13 SP) - Sprint: 2-4 - Deliverable: Shift-left testing practices, AI test generation tools, QA automation framework, ≥70% automation coverage - Acceptance Criteria: Automated tests integrated in CI/CD, ≥70% coverage for new code, QA team trained

US-007: Technical Debt Management System (8 SP) - Sprint: 7-8 - Deliverable: Technical debt backlog, prioritization framework, tracking in Jira, reduction roadmap - Acceptance Criteria: Debt backlog created with ≥50 items, prioritization framework documented, tracking system operational

#### Epic 4: Deployment & Infrastructure (21 Story Points)

US-017: Automated CI/CD Pipeline with AI Optimization (13 SP) - CRITICAL - Sprint: 1-3 - Deliverable: Automated CI/CD pipeline (Jenkins/GitLab CI), automated testing, <30 min build-to-deploy, AI-powered failure analysis - Acceptance Criteria: Pipeline operational, <30 min deploy time achieved, automated tests passing, AI optimization deployed

US-018: Environment Automation and Management (8 SP) - Sprint: 3-4 - Deliverable: Automated environment provisioning (DEV, QA), Infrastructure-as-Code (Terraform/Ansible), health monitoring dashboards - Acceptance Criteria: IaC scripts operational, environments provisionable in <1 hour, monitoring dashboards live

#### Epic 5: Platform Modernization (76 Story Points) - CRITICAL PATH

US-008: Business Layer API Implementation (21 SP) - CRITICAL PATH - Sprint: 1-3 - Deliverable: RESTful Business Layer API (Spring Boot), ≥10 endpoints, OAuth2/JWT authentication, API documentation (Swagger) - Acceptance Criteria: API operational with ≥10 endpoints, ≥85% unit test coverage, API docs published, OAuth2 working - Business Capabilities (TBD in client workshop): - Policy Management (create, update, cancel, renew) - Rating (get quote, calculate premium) - Customer Management (create, update, search) - [Additional capabilities TBD]

US-009: Product Configuration API Standardization (13 SP) - Sprint: 4-6 - Deliverable: Standardized Product Configuration API, migrated configuration logic, versioning, backward compatibility - Acceptance Criteria: Product Config API operational, existing config migrated, API versioning implemented

US-010: Database Optimization for High Concurrency (21 SP) - CRITICAL PATH - Sprint: 1-4 (parallel with US-008) - Deliverable: Database performance analysis, schema/indexing optimization, connection pooling, Redis caching optimization, load test results - Acceptance Criteria: Database performance improved to meet targets (TBD in client workshop), load tests passed, caching hit rate >X% (TBD)

US-011: UI Technology Modernization (21 SP) - Sprint: 5-10 - Deliverable: UI migrated from JSF/IceFaces to React/Angular (technology choice TBD), responsive design, component library, Business API integration - Acceptance Criteria: All in-scope modules migrated to React/Angular, responsive design (mobile/tablet/desktop), component library created, integrated with US-008 API

#### Epic 6: AI Adoption (34 Story Points)

US-012: Code Analysis Agent Implementation (13 SP) - Sprint: 5-7 - Deliverable: CodeMie Code Analysis Agent deployed, CI/CD integration, team trained, ≥70% adoption - Acceptance Criteria: Agent operational, integrated with CI/CD, ≥70% team actively using, code quality metrics dashboard

US-013: Knowledge Base Agent for Documentation (13 SP) - Sprint: 7-9 - Deliverable: CodeMie Knowledge Base Agent deployed, documentation indexed, ≥60% query resolution without human intervention - Acceptance Criteria: Agent operational, docs indexed, ≥60% automated query resolution, team trained

US-014: Coverage and Rating Analysis Agent (8 SP) - Sprint: 9-10 - Deliverable: Test Coverage Analysis Agent deployed, automated coverage recommendations, CI/CD integration - Acceptance Criteria: Agent operational, automated coverage reports generated, recommendations actionable

### 2.4 Deliverables Checklist

By Milestone:

M0: Kickoff (Sprint 0, Week 1) - ☐ Project Charter signed - ☐ Team onboarded (17 FTE) - ☐ DEV environment access granted - ☐ VDIs provisioned

M1: Foundation (Sprint 4, Week 8) - ☐ US-008: Business Layer API operational (≥10 endpoints, ≥85% coverage) - ☐ US-010: Database optimized (performance targets met) - ☐ US-017: CI/CD pipeline operational (<30 min deploy) - ☐ US-018: Environment automation operational - ☐ US-001: Strategic planning framework documented - ☐ US-002: Delivery framework documented - ☐ US-003: CR process documented

M2: Core Modernization (Sprint 7, Week 14) - ☐ US-011: UI modernized for ≥2 modules (React/Angular) - ☐ US-009: Product Configuration API operational - ☐ US-012: Code Analysis Agent deployed (≥70% adoption) - ☐ US-004: Requirements quality framework documented - ☐ US-006: QA shift-left implemented (≥70% automation)

M3: Platform Complete (Sprint 10, Week 20) - ☐ US-011: UI modernized for ALL in-scope modules - ☐ US-013: Knowledge Base Agent deployed (≥60% query resolution) - ☐ US-014: Coverage Analysis Agent deployed - ☐ US-005: Knowledge library operational (≥80% docs migrated) - ☐ US-007: Technical debt backlog created (≥50 items)

M4: Warranty Complete (60 days post go-live) - ☐ Zero P1/P2 defects for 30 consecutive days - ☐ Performance SLAs met for 30 consecutive days - ☐ Knowledge transfer complete - ☐ Warranty period closed

## 3. SCHEDULE BASELINE

### 3.1 Project Timeline

6-Month Option: - Start Date: April 1, 2026 - End Date: September 30, 2026 - Duration: 26 weeks (6 months) - Sprints: 10 sprints × 2 weeks = 20 weeks + 2 weeks Sprint 0 + 4 weeks buffer

9-Month Option: - Start Date: April 1, 2026 - End Date: December 31, 2026 - Duration: 39 weeks (9 months) - Sprints: 18 sprints × 2 weeks = 36 weeks + 2 weeks Sprint 0 + 1 week buffer

### 3.2 Milestone Schedule (6-Month Option)

| Milestone | Date | Deliverables | Payment |
| --- | --- | --- | --- |
| M0: Kickoff | April 1-7, 2026 (Week 1) | Project Charter signed, Team onboarded, Environments ready | 10% ($67.5K) |
| M1: Foundation | May 27, 2026 (End Sprint 4, Week 8) | Business API, DB Optimization, CI/CD, Governance | 30% ($202.5K) |
| M2: Core Modernization | July 8, 2026 (End Sprint 7, Week 14) | UI Modernization (2+ modules), Product Config API, Code Analysis Agent | 30% ($202.5K) |
| M3: Platform Complete | August 19, 2026 (End Sprint 10, Week 20) | UI Complete, AI Agents, QA/Tech Debt | 20% ($135K) |
| M4: Warranty Complete | October 18, 2026 (60 days post go-live) | Defect fixes, Performance tuning, KT | 10% ($67.5K) |

### 3.3 Sprint Schedule (6-Month Option)

| Sprint | Start Date | End Date | User Stories | Story Points | Key Deliverables |
| --- | --- | --- | --- | --- | --- |
| Sprint 0 | Apr 1, 2026 | Apr 7, 2026 | Setup | 0 | Team onboarding, environment access, Sprint 1 planning |
| Sprint 1 | Apr 8, 2026 | Apr 21, 2026 | US-001, US-002, US-008 (start), US-010 (start), US-017 (start) | 22 | Strategic planning, delivery framework, API design, DB analysis, CI/CD setup |
| Sprint 2 | Apr 22, 2026 | May 5, 2026 | US-003, US-006 (start), US-008 (cont), US-010 (cont), US-017 (cont) | 20 | CR process, QA shift-left, API endpoints, DB optimization, CI/CD pipeline |
| Sprint 3 | May 6, 2026 | May 19, 2026 | US-004, US-006 (complete), US-008 (complete), US-010 (cont), US-017 (complete), US-018 (start) | 21 | Requirements framework, QA automation, API complete, DB tuning, CI/CD done, env automation |
| Sprint 4 | May 20, 2026 | Jun 2, 2026 | US-005, US-009 (start), US-010 (complete), US-018 (complete) | 20 | M1 Milestone, Knowledge library, Product Config API, DB complete, env automation done |
| Sprint 5 | Jun 3, 2026 | Jun 16, 2026 | US-009 (cont), US-011 (start), US-012 (start) | 22 | Product Config API, UI modernization Module 1, Code Analysis Agent |
| Sprint 6 | Jun 17, 2026 | Jun 30, 2026 | US-009 (complete), US-011 (cont), US-012 (cont) | 21 | Product Config API done, UI Module 2, Code Analysis Agent |
| Sprint 7 | Jul 1, 2026 | Jul 14, 2026 | US-011 (cont), US-012 (complete), US-013 (start) | 20 | M2 Milestone, UI Module 3, Code Analysis Agent done, Knowledge Base Agent |
| Sprint 8 | Jul 15, 2026 | Jul 28, 2026 | US-007, US-011 (cont), US-013 (cont) | 19 | Tech debt backlog, UI Module 4, Knowledge Base Agent |
| Sprint 9 | Jul 29, 2026 | Aug 11, 2026 | US-011 (cont), US-013 (complete), US-014 (start) | 19 | UI Module 5, Knowledge Base Agent done, Coverage Analysis Agent |
| Sprint 10 | Aug 12, 2026 | Aug 25, 2026 | US-011 (complete), US-014 (complete) | 18 | M3 Milestone, UI complete, Coverage Analysis Agent done |
| UAT | Aug 26, 2026 | Sep 8, 2026 | UAT | 0 | UAT execution by TMNAS + 3rd party vendor, defect fixes |
| Go-Live | Sep 9-16, 2026 |  | Deployment | 0 | Production deployment, hypercare |
| Warranty | Sep 17, 2026 | Oct 18, 2026 | Support | 0 | 60-day warranty (P1/P2 defects only) |

Total Story Points Delivered: 202 SP across 10 sprints
Average Velocity: 20.2 SP per sprint (team of 17 FTE)

### 3.4 Critical Path

The critical path determines the minimum project duration. Delays on critical path delay project completion.

Critical Path for 6-Month Option:

- Sprint 0 → Sprint 1 → Sprint 2 → Sprint 3: US-008 (Business Layer API) - 21 SP, 3 sprints

- Sprint 4 → Sprint 5 → Sprint 6 → Sprint 7 → Sprint 8 → Sprint 9 → Sprint 10: US-011 (UI Modernization) - 21 SP, 6 sprints (depends on US-008 API)

- Sprint 10 → UAT → Go-Live: UAT and deployment - 4 weeks

Total Critical Path Duration: Sprint 0-10 (20 weeks) + UAT (2 weeks) + Go-Live (1 week) + Buffer (1 week) = 24 weeks (6 months)

Critical Path Stories: - US-008 (Business Layer API): MUST complete by Sprint 3 to unblock US-011 - US-010 (Database Optimization): MUST complete by Sprint 4 to ensure performance for UAT - US-011 (UI Modernization): Longest story (21 SP, 6 sprints); delays here delay entire project

Risk Mitigation: - Prioritize US-008 and US-010 in early sprints - Run US-010 in parallel with US-008 (both have backend focus) - Assign best developers to critical path stories - Monitor critical path weekly; escalate immediately if at risk

### 3.5 Dependencies & Constraints

External Dependencies (TMNAS): - DEP-001: Environment access (DEV, QA) - DUE: Sprint 0, April 1 - DEP-002: VDI provisioning (17 VDIs) - DUE: Sprint 0, April 1 - DEP-003: Architecture documentation - DUE: Sprint 1, April 15 - DEP-004: API contracts for external systems - DUE: Sprint 2, April 29 - DEP-005: Database access - DUE: Sprint 1, April 15 - DEP-008: UAT coordination and vendor engagement - DUE: Sprint 6, June 17 - DEP-009: Production deployment approvals - DUE: Sprint 10, August 19

Internal Dependencies (EPAM): - DEP-013: Team onboarding - DUE: Sprint 0-1, April 1-15 - DEP-014: Architecture review and approval - DUE: Sprint 1, April 15 - DEP-015: AI agent licensing (CodeMie) - DUE: Sprint 2, April 29

Schedule Constraints: - Must align with SV product release schedule (6-week cadence) - TMNAS stakeholder availability (limited Product Owner time) - Fixed project end date: September 30, 2026 (6-month) or December 31, 2026 (9-month)

## 4. COST BASELINE

### 4.1 Budget Baseline (6-Month Option)

Total Budget: $675,000

| Category | Amount | % of Total | Details |
| --- | --- | --- | --- |
| Development Effort | $540,000 | 80.0% | 202 SP × 10 sprints × 17 FTE × blended rate ~$60/hour |
| Contingency (20%) | $108,000 | 16.0% | High-risk mitigation: requirements uncertainty, legacy complexity, integration challenges |
| Travel & Expenses | $27,000 | 4.0% | 2-3 business trips for key personnel (workshops, go-live support) |
| TOTAL | $675,000 | 100% | Aligned with $450K per 4-month billing structure |

Cost Assumptions: - Blended hourly rate: ~$60/hour (average across roles: Architect $85/hr, Senior Dev $70/hr, Mid Dev $55/hr, Junior Dev $45/hr) - Team locations: CEE2 (Poland+), Ukraine, GUKKA (cost-effective locations) - Focus factor: 65% productive time (35% overhead for meetings, ceremonies, admin) - Attrition buffer: 10% expected attrition (managed through knowledge transfer, backup resources) - No infrastructure costs: TMNAS provides all infrastructure (VDIs, environments, cloud hosting)

### 4.2 Budget Baseline (9-Month Option)

Total Budget: $1,800,000

Structure: 3 phases, quarterly billing (~$600K per phase)

| Phase | Duration | Scope Summary | Budget |
| --- | --- | --- | --- |
| Phase 1: Foundation | Months 1-3 (Sprints 1-6) | Governance, Business API, DB Optimization, CI/CD | $600,000 |
| Phase 2: Modernization | Months 4-6 (Sprints 7-12) | UI Modernization, Product Config API, AI Agents, QA/Requirements | $600,000 |
| Phase 3: Expansion | Months 7-9 (Sprints 13-18) | Additional scope TBD (data migration, MSP setup, additional integrations, more AI agents) | $600,000 |
| TOTAL | 9 months (18 sprints) | ~350 story points (202 SP baseline + ~148 SP Phase 3) | $1,800,000 |

Phase 3 Scope (TBD in Client Workshop): - Possible: Historical data migration, MSP team setup, additional AI agents, advanced integrations, additional UI modules - To be defined during internal workshop (March 17-19) and validated in client workshop

### 4.3 Payment Milestones (6-Month Option)

| Milestone | Timing | Deliverables | Payment | % | Cumulative | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- | --- |
| M0: Kickoff | Sprint 0 (Week 1) | Project Charter signed, Team onboarded, Environments ready | $67,500 | 10% | 10% | Signed Project Charter, Team access granted, Dev environment operational |
| M1: Foundation | Sprint 4 (Week 8) | Business API, DB Optimization, CI/CD, Governance | $202,500 | 30% | 40% | API functional (≥85% coverage), DB performance met, CI/CD operational (<30 min), Governance docs complete |
| M2: Core Modernization | Sprint 7 (Week 14) | UI Modernization (2+ modules), Product Config API, Code Analysis Agent | $202,500 | 30% | 70% | UI migrated for ≥2 modules, Product Config API operational, Code Analysis Agent deployed (≥70% adoption) |
| M3: Platform Complete | Sprint 10 (Week 20) | UI Complete, AI Agents, QA/Tech Debt | $135,000 | 20% | 90% | All UI migrated, All AI agents operational, QA automation ≥70%, Tech debt backlog created |
| M4: Warranty Complete | 60 days post go-live | Defect fixes, Performance tuning, KT | $67,500 | 10% | 100% | Zero P1/P2 defects for 30 days, Performance SLAs met for 30 days, KT complete |
| TOTAL |  |  | $675,000 | 100% |  |  |

Invoice & Payment Terms: - Invoice submission: Within 5 business days of milestone completion - TMNAS review: 10 business days to review deliverables and provide acceptance or feedback - Payment due: 30 days net from acceptance - Disputes: Escalated to Steering Committee within 5 business days

### 4.4 Payment Milestones (9-Month Option)

Structure: Quarterly billing (every 4 months)

| Phase | Payment Timing | Deliverables | Payment | Cumulative | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| Phase 1 | End of Month 4 (Sprints 1-6 complete) | Foundation complete (M1 criteria + progress toward M2) | $600,000 | 33% | Foundation deliverables accepted (Business API, DB Optimization, CI/CD, Governance, early UI work) |
| Phase 2 | End of Month 8 (Sprints 7-12 complete) | Modernization complete (M2 + M3 criteria) | $600,000 | 67% | Modernization deliverables accepted (UI complete, AI agents, Product Config API, QA/Tech Debt) |
| Phase 3 | End of Month 12 (Sprints 13-18 complete + 60-day warranty) | Phase 3 scope complete + warranty | $600,000 | 100% | Phase 3 deliverables accepted (TBD scope) + Warranty criteria met |
| TOTAL |  |  | $1,800,000 |  |  |

### 4.5 Earned Value Management (EVM)

Purpose: Track project performance (cost, schedule) against baseline using Earned Value metrics.

EVM Metrics:

1. Planned Value (PV): - Baseline budget allocated to scheduled work - Example: By Sprint 4 (M1), PV = 40% × $675K = $270K (M0 10% + M1 30%)

2. Earned Value (EV): - Budget allocated to completed work - Example: By Sprint 4, if M1 is 100% complete, EV = $270K

3. Actual Cost (AC): - Actual cost incurred for completed work - Example: By Sprint 4, if we spent $280K, AC = $280K

4. Cost Variance (CV) = EV - AC - Positive = Under budget (good) - Negative = Over budget (risk) - Example: CV = $270K - $280K = -$10K (over budget)

5. Schedule Variance (SV) = EV - PV - Positive = Ahead of schedule (good) - Negative = Behind schedule (risk) - Example: SV = $270K - $270K = $0 (on schedule)

6. Cost Performance Index (CPI) = EV / AC - >1.0 = Under budget - <1.0 = Over budget - Example: CPI = $270K / $280K = 0.96 (slightly over budget)

7. Schedule Performance Index (SPI) = EV / PV - >1.0 = Ahead of schedule - <1.0 = Behind schedule - Example: SPI = $270K / $270K = 1.0 (on schedule)

EVM Reporting: - Weekly: CPI and SPI reported in status report - Monthly: Full EVM analysis in Steering Committee report - Thresholds: - CPI < 0.95: Over budget alert (escalate to Steering Committee) - SPI < 0.95: Behind schedule alert (escalate to Steering Committee)

## 5. PERFORMANCE MEASUREMENT

### 5.1 Key Performance Indicators (KPIs)

Track and report the following KPIs:

Scope Performance: - Story Points Completed: Cumulative SP completed vs. 202 SP baseline - User Stories Completed: # of stories done vs. 16 baseline - Sprint Velocity: Actual SP per sprint vs. planned (20-22 SP) - Scope Variance: SP added via CRs - SP removed = Net scope change (target: 0)

Schedule Performance: - Milestone On-Time Delivery: % of milestones delivered on planned date (target: 100%) - Sprint Commitment Accuracy: % of committed SP completed per sprint (target: ≥90%) - Critical Path Health: Are critical path stories on track? (Yes/No) - Schedule Performance Index (SPI): EV / PV (target: ≥1.0)

Cost Performance: - Budget Utilization: % of budget spent vs. planned (target: ≤100% at project end) - Contingency Usage: % of 20% contingency used (target: ≤100%) - Cost Performance Index (CPI): EV / AC (target: ≥1.0) - Actual Cost vs. Budget: Track monthly (forecast at completion)

Quality Performance: - Code Coverage: % code coverage (target: ≥85%) - Defect Density: Defects per story point (target: <1%) - UAT Pass Rate: % of UAT test cases passed (target: ≥95%) - Production Defects: # of P1/P2 defects in production (target: 0 for 30 days post go-live)

AI Adoption Performance: - Team AI Adoption Rate: % of team actively using AI agents (target: ≥70%) - Code Review Time Reduction: % reduction in code review time (target: ≥30%) - Knowledge Base Query Resolution: % of queries answered without human intervention (target: ≥60%)

Stakeholder Satisfaction: - Client Satisfaction Score: Monthly survey (target: ≥4.5/5.0) - Executive Escalations: # of escalations to CIO/CTO (target: 0) - Sprint Review Attendance: % of Sprint Reviews attended by Product Owner (target: 100%)

### 5.2 Variance Thresholds

Acceptable Variance: - Cost Variance: ±5% ($33.75K for 6-month project) - Schedule Variance: ±1 week per milestone - Scope Variance: ±10 SP (via approved CRs only)

Escalation Thresholds:

| Variance | Action |
| --- | --- |
| Cost Variance >5% | Escalate to Steering Committee; review contingency usage; identify cost reduction opportunities |
| Schedule Variance >1 week | Escalate to Steering Committee; review critical path; consider descoping lower-priority stories or adding resources |
| Scope Variance >10 SP | Review CR log; ensure all CRs are approved; identify unauthorized scope creep |
| CPI < 0.95 or SPI < 0.95 | Trigger corrective action plan; escalate to Executive Sponsors if trend continues for 2 sprints |

## 6. BASELINE MAINTENANCE

### 6.1 Baseline Review Frequency

The baseline is reviewed and updated: - Weekly: Informal review in weekly status report (progress toward baseline) - Bi-Weekly: Sprint Review validates completed work against baseline acceptance criteria - Monthly: Steering Committee reviews baseline performance (EVM, KPIs, variances) - Milestone: Formal baseline performance review at each milestone (M1, M2, M3, M4) - As-Needed: When Type 3 Change Requests are approved (new baseline version)

### 6.2 Baseline Update Process

Minor Updates (Type 2 CRs, <5% impact): 1. CR Board approves Type 2 CR 2. EPAM Delivery Manager updates baseline documents: - Scope Baseline (add/change SP) - Schedule Baseline (adjust sprint allocations if needed) - Cost Baseline (track contingency usage) 3. New baseline version: v2.1, v2.2, etc. 4. Communicate updates to EPAM team and TMNAS stakeholders (weekly status report)

Major Updates (Type 3 CRs, >5% impact): 1. Executive Sponsors approve Type 3 CR 2. Contract amendment executed 3. EPAM Delivery Manager updates baseline documents: - Project Charter (new baseline version) - Scope Baseline (add significant scope) - Schedule Baseline (extend timeline if needed) - Cost Baseline (add budget) 4. New baseline version: v3.0, v4.0, etc. 5. Formal communication to all stakeholders (Steering Committee presentation)

### 6.3 Baseline Documentation

Baseline documents maintained throughout project: - Project Charter - Approved baseline (scope, schedule, budget, assumptions, constraints, risks) - Scope Management Plan - Detailed scope baseline (16 user stories, 202 SP) - Project Schedule - Sprint schedule, milestone dates, Gantt chart - Product Backlog - User story details, acceptance criteria, story points - Budget Breakdown - Cost categories, payment milestones, contingency tracking - Change Request Log - All CRs and their impact on baseline - Earned Value Reports - Monthly EVM analysis

All baseline documents stored in shared repository (Confluence, SharePoint, or shared drive) with version control.

## 7. APPROVAL & SIGN-OFF

### 7.1 Baseline Approval Signatures

This Project Baseline (Version 2.0) is approved by:

| Role | Name | Title | Signature | Date |
| --- | --- | --- | --- | --- |
| TMNAS Executive Sponsor | Lana | Chief Information Officer (CIO) | _________________ | ________ |
| TMNAS Project Sponsor | Prashant | Chief Technology Officer (CTO) | _________________ | ________ |
| TMNAS Product Owner | TBD | Product Owner - RapidSure | _________________ | ________ |
| EPAM Account Manager | TBD | Account Manager - TMNAS | _________________ | ________ |
| EPAM Delivery Manager | TBD | Delivery Manager - Project Rambo | _________________ | ________ |
| EPAM Solution Architect | TBD | Solution Architect - RapidSure Modernization | _________________ | ________ |

Approval Date: April 1, 2026 (Target - Project Kickoff)

This baseline becomes the contractual reference point upon signature and cannot be changed without formal Change Request approval.

## 8. APPENDICES

### Appendix A: Baseline Change Log

| Version | Date | Change Description | CR ID | Approved By | Scope Impact | Schedule Impact | Cost Impact |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.0 | March 20, 2026 | Initial baseline (post-internal workshop) | N/A | EPAM Internal | 202 SP | 10 sprints (6-month) | $675K |
| 2.0 (Planned) | April 1, 2026 | Final baseline (post-client workshop) | N/A | TMNAS + EPAM Executives | TBD adjustments | TBD adjustments | TBD adjustments |
| 2.1 (Example) | TBD | Added Cancel button to policy screen | CR-003 | CR Board | +3 SP | No change | +$10.5K (contingency) |
| 3.0 (Example) | TBD | Added mobile app for agents | CR-025 | Executive Sponsors + Contract Amendment | +34 SP | +4 sprints | +$120K |

### Appendix B: Baseline Metrics Dashboard

Monthly Baseline Performance Report Template:

Project: TMNAS - Project Rambo
Reporting Period: [Month Year]
Report Date: [Date]

1. Scope Performance - Baseline Scope: 202 SP (16 user stories) - Completed to Date: _____ SP (_____ stories) - Remaining: _____ SP (_____ stories) - Scope Added via CRs: _____ SP - Scope Removed via CRs: _____ SP - Net Scope Change: _____ SP - Status: ☐ On Track ☐ At Risk ☐ Behind

2. Schedule Performance - Baseline End Date: September 30, 2026 (6-month) or December 31, 2026 (9-month) - Forecast End Date: ___________ - Schedule Variance: _____ days (ahead/behind) - Milestones On Time: _____% (_____ of _____ milestones) - Sprint Velocity: _____ SP (planned: 20-22 SP) - Status: ☐ On Track ☐ At Risk ☐ Behind

3. Cost Performance - Baseline Budget: $675K (6-month) or $1.8M (9-month) - Actual Cost to Date: $_________ - Earned Value (EV): $_________ - Planned Value (PV): $_________ - Cost Variance (CV): $_________ (EV - AC) - Schedule Variance (SV): $_________ (EV - PV) - Cost Performance Index (CPI): _____ (EV / AC) - Schedule Performance Index (SPI): _____ (EV / PV) - Contingency Used: $_________ (_____% of $108K) - Status: ☐ On Track ☐ At Risk ☐ Over Budget

4. Quality Performance - Code Coverage: _____% (target: ≥85%) - Defect Density: _____ defects per SP (target: <1%) - UAT Pass Rate: _____% (target: ≥95%) - Production Defects (P1/P2): _____ (target: 0) - Status: ☐ On Track ☐ At Risk ☐ Below Standard

5. AI Adoption Performance - Team AI Adoption Rate: _____% (target: ≥70%) - Code Review Time Reduction: _____% (target: ≥30%) - Knowledge Base Query Resolution: _____% (target: ≥60%) - Status: ☐ On Track ☐ At Risk ☐ Below Target

6. Risks & Issues - Open Risks: _____ (High: _____, Medium: _____, Low: _____) - Open Issues: _____ (P1: _____, P2: _____, P3: _____) - Top 3 Risks This Month: [List] - Top 3 Issues This Month: [List]

7. Change Requests - New CRs This Month: _____ (Type 1: _____, Type 2: _____, Type 3: _____) - CRs Approved This Month: _____ - CRs Rejected/Deferred This Month: _____ - Active CRs: _____ (In Review: _____, In Progress: _____, Pending Approval: _____)

8. Forecast at Completion (FAC) - Forecast Total Cost: $_________ (Budget: $675K / $1.8M) - Forecast End Date: ___________ (Baseline: Sep 30 / Dec 31, 2026) - Forecast Total SP: _____ SP (Baseline: 202 SP) - Overall Project Status: ☐ Green ☐ Yellow ☐ Red