## TMNAS - PROJECT RAMBO

## PROJECT CHANGE CONTROL PLAN

Version: 1.0
Date: March 12, 2026
Project Start Date: April 1, 2026
Project End Date: September 30, 2026 (6-month) or December 31, 2026 (9-month)
Status: Draft - For Internal Workshop Review

### VERSION CONTROL

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | March 12, 2026 | EPAM Delivery Manager | Initial Change Control Plan for Fixed Fee project |

## 1. INTRODUCTION

### 1.1 Purpose

This Project Change Control Plan establishes the process for identifying, evaluating, approving, and implementing changes to the TMNAS Project Rambo scope, schedule, budget, quality, resources, or any other project baseline.

For a Fixed Fee engagement, change control is CRITICAL to: - Prevent scope creep that erodes project margin - Maintain schedule and budget commitments - Ensure all changes are visible, assessed, and approved by both parties (EPAM and TMNAS) - Protect EPAM from uncontrolled work expansion - Protect TMNAS from unexpected cost overruns

### 1.2 Scope of Change Control

This Change Control Plan covers changes to: - Project Scope - User stories, deliverables, features, acceptance criteria - Project Schedule - Milestone dates, sprint timelines, delivery dates - Project Budget - Cost estimates, payment milestones, contingency usage - Project Quality - Quality standards, Definition of Done, testing requirements - Project Resources - Team size, team composition, key personnel - Project Assumptions - Foundational assumptions documented in Project Charter - Project Constraints - Budget, timeline, technology, resource constraints - Project Risks - New risks introduced or risk mitigation approaches

This Change Control Plan does NOT cover: - Routine project management decisions - Daily task assignments, sprint planning details (within approved scope) - Defect fixes - Bugs found during development or testing (covered by warranty if post-deployment) - Clarifications within existing scope - Minor clarifications that don’t change scope, schedule, or cost (Type 1 CRs)

## 2. CHANGE CONTROL PRINCIPLES

### 2.1 Guiding Principles

1. Transparency - All changes are visible to all stakeholders (EPAM and TMNAS) - No “informal” or “under the table” changes - Change Request (CR) log is shared and reviewed regularly

2. Proactive Impact Assessment - Every change request receives thorough impact assessment BEFORE approval - Impact includes: scope, schedule, cost, risk, quality - No work begins until impact is understood and approved

3. Mutual Agreement - Both EPAM and TMNAS must agree on changes (via Change Control Board) - Major changes (Type 3) require executive sponsor approval - Unilateral changes are not permitted

4. Baseline Protection - Project baselines (scope, schedule, budget) are formally documented and controlled - Baseline changes require formal approval and versioning - Baseline integrity is maintained throughout project

5. Contingency Management - 20% contingency buffer ($108K for 6-month, $360K for 9-month) is reserved for Type 2 changes (<5% impact) - Contingency is not a “free pool” for new features—it covers unforeseen complexity, requirements clarification, and minor changes - Contingency usage is tracked and reported monthly

6. Client Value Focus - Change requests are evaluated based on business value vs. impact - Changes that deliver high value with low impact are prioritized - Changes that deliver low value with high impact are rejected or deferred

## 3. CHANGE REQUEST CATEGORIES

### 3.1 Change Request Types

All changes are classified into one of three types based on budget impact:

### Type 1: Clarification (No Impact)

Definition:
Clarifications or refinements to existing requirements that do not change scope, schedule, or cost.

Characteristics: - ✅ Clarifies ambiguous acceptance criteria - ✅ Provides additional detail to existing user story - ✅ Corrects typos or documentation errors - ✅ Adjusts implementation approach within existing story points - ❌ Does NOT add new features or capabilities - ❌ Does NOT require additional story points - ❌ Does NOT delay milestones

Examples: - “Can you clarify what ‘policy search’ means in US-008? Does it search by policy number only, or also by customer name?” - “The mockup shows a dropdown for state selection, but the user story doesn’t specify. Can we use a dropdown?” - “Acceptance criterion says ‘fast response time.’ Can we define ‘fast’ as <2 seconds?”

Budget Impact: $0 (absorbed in project, no contingency usage)

Approval Process: - Approver: EPAM Delivery Manager only - Timeline: Immediate (same day or next business day) - Documentation: Noted in user story comments; no formal CR document required

Threshold: As many Type 1 CRs as needed (no limit)

### Type 2: Minor Change (<5% Budget Impact)

Definition:
Small changes to scope, schedule, or resources that have <5% budget impact.

Budget Threshold: - 6-month project ($675K): <$33,750 per CR - 9-month project ($1.8M): <$90,000 per CR

Characteristics: - ✅ Adds minor functionality or changes to existing user story - ✅ Adjusts acceptance criteria in ways that require additional work - ✅ Adds small new user story (typically <8 story points) - ✅ Adjusts timeline by <1 sprint - ✅ Requires modest additional effort (1-2 weeks for team) - ❌ Does NOT require contract amendment - ❌ Does NOT significantly delay major milestones (M1, M2, M3, M4)

Examples: - “Can we add a ‘Cancel’ button to the policy creation screen? It’s not in US-011 but users need it.” (Estimated: 3 SP = ~$10K) - “Can the Business Layer API (US-008) include a ‘Get Policy by Customer Name’ endpoint in addition to ‘Get Policy by Policy Number’?” (Estimated: 2 SP = ~$7K) - “Can we add data validation for ZIP code format in US-011 UI? It’s not specified in acceptance criteria.” (Estimated: 1 SP = ~$3.5K)

Budget Impact: <5% of total budget; absorbed in 20% contingency buffer

Approval Process: - Approver: Change Control Board (EPAM DM + BA + TMNAS PO + CTO/Prashant) - Timeline: Weekly CR Board meeting (decision within 1 week) - Documentation: Formal CR document, impact assessment, CR log entry

Threshold: - Maximum cumulative Type 2 CRs: 20% contingency = $108K (6-month) or $360K (9-month) - Once contingency is exhausted, all further changes are Type 3 (require contract amendment)

Contingency Tracking: - EPAM Delivery Manager tracks contingency usage in weekly status report - When contingency reaches 80% used, escalate to Steering Committee - When contingency reaches 100% used, all further CRs are Type 3

### Type 3: Major Change (>5% Budget Impact)

Definition:
Significant changes to scope, schedule, budget, or resources that have >5% budget impact.

Budget Threshold: - 6-month project ($675K): >$33,750 per CR - 9-month project ($1.8M): >$90,000 per CR

Characteristics: - ✅ Adds significant new functionality (new user story >8 SP, or multiple stories) - ✅ Changes project objectives or success criteria - ✅ Delays major milestones (M1, M2, M3, M4) by >1 sprint - ✅ Requires additional budget beyond contingency - ✅ Requires team size increase or key personnel changes - ✅ Introduces significant new risks or technical complexity

Examples: - “Can we add a mobile app for insurance agents to access RapidSure on the go?” (Estimated: 34 SP = ~$120K, 3-4 sprints) - “Can we migrate all historical policy data from legacy systems as part of this project?” (Estimated: 21 SP = ~$75K, 2-3 sprints, data quality risks) - “Can we integrate with a new third-party fraud detection system not mentioned in original scope?” (Estimated: 13 SP = ~$45K, integration complexity) - “Can we extend the project by 2 months to include additional AI agents not in original 16 stories?” (Estimated: $300K additional budget)

Budget Impact: >5% of total budget; requires contract amendment and additional payment

Approval Process: - Step 1: Change Control Board reviews and recommends to Executive Sponsors - Step 2: Executive Sponsors (TMNAS CIO + CTO + EPAM Account Manager) approve/reject - Step 3: If approved, Legal teams execute contract amendment - Timeline: 2-4 weeks (CR Board → Executive approval → Legal contracting) - Documentation: Formal CR document, detailed impact assessment, contract amendment, updated Project Charter baseline

Threshold: No limit, but each Type 3 CR requires formal contract amendment

## 4. CHANGE CONTROL PROCESS

### 4.1 Change Request Workflow

5-Step Process: Submission → Impact Assessment → CR Board Review → Approval/Rejection → Implementation

### STEP 1: Change Request Submission

Who can submit a CR? - TMNAS stakeholders (Product Owner, CTO, business users, SMEs) - EPAM team members (Delivery Manager, Architect, developers, QA)

How to submit a CR: 1. Fill out Change Request Template (Appendix A) - CR Title and Description - Business Justification (why is change needed?) - Current State (what exists today?) - Proposed Change (what is requested?) - Impact if NOT approved (risks, consequences)

- Submit CR to EPAM Delivery Manager via:

  - Email (with CR template attached)

  - Jira ticket (with CR label)

  - During backlog grooming or Sprint Planning (verbal request → documented by BA)

- CR ID Assigned: EPAM Delivery Manager assigns unique CR ID (e.g., CR-001, CR-002)

Timeline: Submit any time; CR Board reviews weekly

### STEP 2: Impact Assessment (EPAM Delivery Manager)

Timeline: Within 3 business days of CR submission

Impact Assessment Includes:

A. Scope Impact - User Stories Affected: Which existing stories are impacted? (list by US-XXX) - New User Stories Required: Any new stories needed? (describe, estimate SP) - Story Points Added: How many SP added to backlog? (e.g., +5 SP) - Story Points Removed: Any SP removed or descoped? (e.g., -2 SP) - Net Scope Change: Added - Removed = Net (e.g., +3 SP)

B. Schedule Impact - Sprints Affected: Which sprints are impacted? (e.g., Sprint 5-7) - Sprint Delay: Does this delay sprint completion? (e.g., Sprint 6 delayed by 1 week) - Milestone Impact: Does this delay M1, M2, M3, or M4? (Yes/No, by how much?) - Critical Path Impact: Does this affect critical path (US-008, US-010, US-015)? (Yes/No) - Go-Live Impact: Does this delay project completion? (Yes/No, by how much?)

C. Cost Impact - Estimated Cost: Dollar amount or % of budget - Calculation: Story Points × $3,500/SP (assumed blended rate) = Cost - Example: 5 SP × $3,500 = $17,500 - Type Classification: Type 1 / Type 2 / Type 3 based on cost threshold - Contingency Impact: If Type 2, how much contingency is used? (e.g., $17.5K of $108K = 16% of contingency)

D. Risk Impact - New Risks Introduced: List new risks (e.g., integration complexity, third-party dependency, skill gap) - Existing Risks Mitigated: List risks reduced by this change (e.g., reduces technical debt, improves performance) - Net Risk Assessment: Overall risk increase/decrease/neutral

E. Quality Impact - Technical Debt Impact: Does this increase/decrease technical debt? - Code Coverage Impact: Does this affect test coverage (positive/negative/neutral)? - Architecture Impact: Significant architectural change? (Yes/No) - Security/Compliance Impact: Any security or compliance implications? (Yes/No)

F. Resource Impact - Team Capacity Impact: Can current team absorb this work within current sprints? (Yes/No) - Skill Gap: Does team have required skills, or is training/hiring needed? (Yes/No) - Key Personnel Impact: Does this require specific key personnel? (Yes/No)

G. Dependencies - New Dependencies Introduced: Any new dependencies on external systems, TMNAS teams, or third parties? - Existing Dependencies Affected: Does this change existing dependencies?

H. Alternatives Considered - Alternative 1: [Describe lower-cost or lower-risk alternative] - Alternative 2: [Describe another approach] - Do Nothing: What happens if CR is rejected? (consequences, workarounds)

I. EPAM Recommendation - Recommendation: ☐ Approve ☐ Reject ☐ Defer ☐ Approve with Conditions - Rationale: [Explain recommendation based on business value vs. impact]

Deliverable: Completed Change Request Impact Assessment (Appendix A, Part 2)

### STEP 3: Change Control Board Review

Change Control Board (CR Board) Composition:

| Organization | Role | Name (TBD) | Responsibilities |
| --- | --- | --- | --- |
| EPAM | Delivery Manager | TBD | Chair CR Board, present impact assessments, facilitate decisions |
| EPAM | Business Analyst | TBD | Document CRs, update CR log, track scope changes |
| EPAM | Solution Architect | TBD (as needed) | Provide technical input on architecture/risk impact |
| TMNAS | Product Owner | TBD | Represent business stakeholder interests, vote on CRs |
| TMNAS | CTO / Prashant | TBD | Approve technical changes, vote on CRs, escalate Type 3 to CIO |
| TMNAS | Business Analyst | TBD (optional) | Provide business context, clarify requirements |

Meeting Cadence: - Regular Meetings: Weekly, 30 minutes, Wednesdays 10:00 AM (TBD - client workshop) - Ad-Hoc Meetings: Scheduled as needed for urgent CRs (within 2 business days of request)

CR Board Meeting Agenda:

1. Review CR Log Status (5 min) - CRs submitted since last meeting - CRs pending decision - CRs approved and in implementation - CRs completed

2. Review New CRs (15 min, ~3 CRs per meeting) - EPAM DM presents each new CR: - CR Title, Submitter, Business Justification - Impact Assessment Summary (scope, schedule, cost, risk) - EPAM Recommendation - Discussion: Questions, clarifications, concerns - Vote: Approve / Reject / Defer

3. Review Type 3 CRs (5 min) - CRs requiring Executive Sponsor approval - CR Board recommendation to Executives - Next steps (schedule Executive Sponsor meeting)

4. Contingency Status (3 min) - Current contingency usage (% of 20% buffer used) - Forecast: Will contingency be exhausted? - Action: If >80% used, escalate to Steering Committee

5. Action Items & Next Meeting (2 min) - Action items assigned - Next meeting date confirmed

Decision-Making Process:

Voting: - Each CR Board member has one vote (EPAM DM, EPAM BA, TMNAS PO, TMNAS CTO = 4 votes total) - Type 1 CRs: No CR Board vote needed (EPAM DM approves) - Type 2 CRs: Majority vote required (3 of 4 votes to approve) - Type 3 CRs: CR Board makes recommendation; Executives have final approval

Tie-Breaker: - If CR Board is deadlocked (2-2 vote), escalate to Steering Committee for decision

Decision Options: - Approve: CR is approved; move to implementation (Step 5) - Approve with Conditions: CR is approved if specific conditions are met (e.g., “Approve if TMNAS can provide API contract by Sprint 5”) - Reject: CR is rejected; EPAM DM communicates decision and rationale to submitter - Defer: CR is deferred to future phase (e.g., Phase 2, post-project); added to “parking lot”

Documentation: - CR Board meeting minutes (attendees, CRs discussed, decisions, votes) - CR log updated with decisions - CR submitter notified of decision (within 1 business day of meeting)

### STEP 4: Executive Sponsor Approval (Type 3 CRs Only)

Executive Sponsor Composition:

| Organization | Role | Name (TBD) | Approval Authority |
| --- | --- | --- | --- |
| TMNAS | Chief Information Officer (CIO) | Lana | Final approval for Type 3 CRs (budget, strategic direction) |
| TMNAS | Chief Technology Officer (CTO) | Prashant | Technical approval for Type 3 CRs (architecture, feasibility) |
| EPAM | Account Manager | TBD | EPAM commercial interests, contract amendment negotiation |
| EPAM | Delivery Manager | TBD (presents) | Present CR and impact assessment |

Process for Type 3 CRs:

1. CR Board Recommendation (from Step 3) - CR Board reviews Type 3 CR and makes recommendation to Executives - Recommendation: Approve / Reject / Defer (with detailed rationale)

2. Executive Sponsor Meeting - Timeline: Within 2 weeks of CR Board recommendation - Format: In-person or video conference, 30-60 minutes - Agenda: 1. EPAM Delivery Manager presents CR and impact assessment (15 min) 2. CR Board recommendation and rationale (5 min) 3. Executive discussion and Q&A (20 min) 4. Executive decision (10 min)

3. Executive Decision - Approve: Proceed to contract amendment (Step 4a) - Reject: Communicate decision to CR submitter; no further action - Defer: Add to parking lot for future consideration (Phase 2, post-project)

4. Executive Approval Documentation - Approval Document: Signed by TMNAS CIO + CTO + EPAM Account Manager - Approval Conditions: Any conditions that must be met (e.g., “Approve pending budget allocation in Q3”)

STEP 4a: Contract Amendment (Type 3 CRs Only)

If Type 3 CR is approved by Executives, a contract amendment is required.

Contract Amendment Process:

1. Draft Contract Amendment (EPAM Legal + TMNAS Procurement) - Timeline: Within 2 weeks of Executive approval - Content: - CR Description and Scope Change - Budget Increase ($ amount) - Timeline Extension (if applicable, # of sprints or weeks) - Updated Payment Milestones (if applicable) - Updated Deliverables List - Any other contractual changes (warranties, SLAs, etc.)

2. Legal Review and Negotiation - Timeline: 1-2 weeks for review and negotiation - Participants: EPAM Legal, TMNAS Legal/Procurement, EPAM Account Manager

3. Contract Amendment Execution - Signatories: TMNAS authorized signatory (CIO, Procurement Director) + EPAM authorized signatory - Effective Date: Date of last signature

4. Project Baseline Update - EPAM Delivery Manager updates: - Project Charter (new baseline version) - Scope Management Plan (new scope baseline) - Product Backlog (add/change user stories) - Project Schedule (update milestones if timeline extended) - Budget (update budget breakdown with additional funds)

5. Communicate to Teams - EPAM Delivery Manager communicates contract amendment to EPAM team and TMNAS stakeholders - Updated documents shared (Project Charter, backlog, schedule)

Timeline Summary for Type 3 CRs: - CR Submission → Impact Assessment: 3 days - Impact Assessment → CR Board Review: 1 week - CR Board Review → Executive Sponsor Meeting: 2 weeks - Executive Approval → Contract Amendment Execution: 3-4 weeks - Total: 6-7 weeks from CR submission to implementation start

### STEP 5: Implementation

For Approved CRs (Type 2 and Type 3):

1. Backlog Update (EPAM Business Analyst) - Add new user stories to product backlog (if CR creates new stories) - Update existing user stories (if CR modifies existing stories) - Assign story points based on impact assessment - Prioritize CR-related stories in backlog (based on business value and CR Board priority)

2. Sprint Planning - CR-related stories included in upcoming sprint planning - Team commits to CR work alongside baseline scope work - EPAM Delivery Manager ensures CR work doesn’t displace baseline scope (unless CR Board approves descoping)

3. Implementation - Team implements CR-related work according to Definition of Done - Code, tests, documentation completed - Sprint Review demonstrates CR deliverables to Product Owner

4. Acceptance - Product Owner accepts CR deliverables in Sprint Review (same process as baseline stories) - For Type 3 CRs with contract amendments: Milestone acceptance may be required for payment

5. CR Closure - EPAM Business Analyst updates CR log: Status = “Implemented” - CR submitter notified of completion - Lessons learned captured (did implementation match estimate? any surprises?)

For Rejected CRs:

1. Communication (EPAM Delivery Manager) - Notify CR submitter of rejection within 1 business day of CR Board decision - Provide clear rationale for rejection (based on impact assessment and CR Board discussion) - Suggest alternatives or workarounds (if applicable)

2. CR Log Update - EPAM Business Analyst updates CR log: Status = “Rejected” - Rejection rationale documented

3. Escalation Option - If CR submitter disagrees with rejection, they can escalate to Steering Committee - Steering Committee reviews CR at next monthly meeting and makes final decision

For Deferred CRs:

1. Parking Lot (EPAM Business Analyst) - CR added to “Parking Lot” (list of deferred CRs for future consideration) - Parking Lot reviewed during: - Phase 2 planning (for 9-month project) - Post-project planning (for follow-on work) - Annual strategic planning

2. CR Log Update - EPAM Business Analyst updates CR log: Status = “Deferred” - Future consideration date noted (e.g., “Review in Phase 2 planning”)

## 5. CHANGE CONTROL ROLES & RESPONSIBILITIES

| Role | Change Control Responsibilities |
| --- | --- |
| EPAM Delivery Manager | - Receive and log all Change Requests- Conduct impact assessments (within 3 business days)- Chair Change Control Board meetings (weekly)- Present CRs to CR Board and Executive Sponsors- Communicate CR decisions to submitters and teams- Track contingency usage and escalate when >80% used- Update Project Charter and baselines for approved CRs- Report CR metrics in weekly status report and monthly Steering Committee |
| EPAM Business Analyst | - Maintain Change Request Log (shared with TMNAS)- Document CR Board meeting minutes- Update product backlog with approved CR changes- Support impact assessment (requirements analysis)- Track CR implementation progress (Status: Approved → In Progress → Implemented) |
| EPAM Solution Architect | - Provide technical input on CR impact assessments (architecture, risk, complexity)- Attend CR Board meetings as needed for technical CRs- Validate technical feasibility of proposed changes- Identify architectural risks introduced by CRs |
| TMNAS Product Owner | - Submit Change Requests on behalf of business stakeholders- Participate in CR Board meetings (vote on CRs)- Provide business justification and priority for CRs- Accept or reject CR deliverables in Sprint Review- Communicate CR decisions to TMNAS stakeholders |
| TMNAS CTO / Prashant | - Participate in CR Board meetings (vote on CRs, especially technical CRs)- Approve Type 2 CRs (minor changes)- Recommend Type 3 CRs to Executive Sponsors- Provide technical guidance on architectural changes |
| TMNAS CIO / Lana | - Approve Type 3 CRs (major changes requiring budget increase)- Review CR trends in monthly Steering Committee- Escalation point for CR disputes- Ensure CRs align with TMNAS strategic objectives |
| EPAM Account Manager | - Represent EPAM commercial interests in Type 3 CR approvals- Negotiate contract amendments with TMNAS Procurement- Escalate commercial risks to EPAM leadership- Ensure CR process protects EPAM margin and Fixed Fee integrity |
| Change Control Board | - Review and approve/reject Type 2 CRs (weekly meetings)- Recommend Type 3 CRs to Executive Sponsors- Ensure CRs are evaluated fairly (business value vs. impact)- Monitor contingency usage and escalate when needed |
| Steering Committee | - Review CR trends and cumulative impact (monthly)- Resolve CR disputes escalated from CR Board- Approve strategic scope changes (Type 3 CRs)- Ensure project remains aligned with business objectives despite changes |

## 6. CHANGE CONTROL TOOLS & TEMPLATES

### 6.1 Change Request Log

Purpose: Track all Change Requests from submission to closure

Tool: Excel, Jira, or shared project management tool (TBD - client workshop)

Change Request Log Fields:

| Field | Description |
| --- | --- |
| CR ID | Unique identifier (e.g., CR-001, CR-002) |
| Submission Date | Date CR was submitted |
| Submitter | Name and role (e.g., “Jane Smith, TMNAS Product Owner”) |
| CR Title | Short descriptive title (max 100 characters) |
| CR Type | Type 1 / Type 2 / Type 3 |
| Business Justification | Why is this change needed? (1-2 sentences) |
| Impact Assessment | Summary of scope, schedule, cost, risk impact |
| Estimated Cost | Dollar amount (e.g., $17,500) or % of budget (e.g., 2.6%) |
| Story Points Added | # of SP added (e.g., +5 SP) |
| Status | Submitted / Under Review / Approved / Rejected / Deferred / Implemented / Closed |
| CR Board Decision Date | Date CR Board reviewed and decided |
| CR Board Decision | Approved / Rejected / Deferred |
| Executive Approval Date | (Type 3 only) Date Executives approved |
| Implementation Sprint | Sprint # where CR is implemented (e.g., Sprint 6) |
| Closure Date | Date CR implementation is complete and accepted |
| Contingency Used | (Type 2 only) $ amount of contingency used |
| Contract Amendment | (Type 3 only) Contract amendment reference # |

CR Log Access: - EPAM Team: Full read/write access (EPAM DM, BA) - TMNAS Stakeholders: Read access (PO, CTO, CIO) - Updated: Real-time as CRs are submitted, reviewed, approved, implemented

CR Log Review: - Weekly: CR Board reviews CR log status (Step 1 of meeting agenda) - Monthly: Steering Committee reviews CR log trends and cumulative impact

### 6.2 Change Request Template

See Appendix A: Change Request Template for complete template with all fields.

### 6.3 Impact Assessment Template

See Appendix B: Impact Assessment Template for detailed impact assessment format.

### 6.4 CR Board Meeting Minutes Template

Meeting Details: - Date: [Meeting date] - Time: [Start time - End time] - Location: [In-person / Video conference] - Attendees: [List names and roles] - Absent: [List names and roles]

CRs Reviewed:

CR-XXX: [CR Title] - Submitter: [Name] - Type: [Type 1/2/3] - Impact Summary: [Scope, schedule, cost] - EPAM Recommendation: [Approve/Reject/Defer] - Discussion Summary: [Key points discussed] - Decision: ☐ Approved ☐ Rejected ☐ Deferred - Vote: [X for, Y against, Z abstain] (if applicable) - Conditions: [Any conditions for approval] - Action Items: [Who does what by when]

Contingency Status: - Total Contingency: $108K (6-month) or $360K (9-month) - Contingency Used to Date: $[amount] ([%]%) - Contingency Remaining: $[amount] ([%]%)

Action Items: - [Action item 1] - Owner: [Name] - Due: [Date] - [Action item 2] - Owner: [Name] - Due: [Date]

Next Meeting: [Date, Time]

## 7. CHANGE CONTROL METRICS & REPORTING

### 7.1 Change Control Metrics

Track and report the following metrics:

1. CR Volume Metrics: - Total CRs Submitted: # of CRs submitted (cumulative and per month) - CRs by Type: # of Type 1, Type 2, Type 3 CRs - CR Approval Rate: % of CRs approved vs. rejected - CR Deferral Rate: % of CRs deferred to future phases

2. CR Impact Metrics: - Scope Impact: Total SP added via CRs (cumulative) - Cost Impact: Total cost of approved CRs (cumulative) - Contingency Usage: % of contingency used (track toward 100%) - Schedule Impact: # of milestones delayed due to CRs

3. CR Cycle Time Metrics: - CR Submission to Decision: Average days from submission to CR Board decision - CR Approval to Implementation: Average days from approval to implementation complete - Type 3 CR Cycle Time: Average days from submission to Executive approval

4. CR Quality Metrics: - CR Rework Rate: % of CRs requiring re-assessment or revision - CR Implementation Variance: Actual cost/effort vs. estimated in impact assessment

### 7.2 Change Control Reporting

Weekly Status Report (EPAM DM → TMNAS Sponsors):

Change Request Summary: - New CRs This Week: [X CRs submitted] - Type 1: [#], Type 2: [#], Type 3: [#] - CRs Approved This Week: [Y CRs approved] - CRs Rejected/Deferred This Week: [Z CRs] - CRs In Implementation: [List CR IDs and target completion sprint]

Contingency Status: - Contingency Used: $[amount] / $108K ([%]% used) - Contingency Remaining: $[amount] ([%]% remaining) - Forecast: Based on current CR rate, contingency will be exhausted by [date/sprint] (if trending toward 100%)

CR Risks: - [Risk: e.g., “High volume of Type 2 CRs may exhaust contingency by Sprint 7. Recommend stricter CR approval criteria.”]

Monthly Steering Committee Report:

Change Request Trends: - CR Volume Trend: Chart showing # of CRs submitted per month (Type 1, 2, 3) - Contingency Usage Trend: Chart showing cumulative contingency usage over time - CR Approval Rate: % of CRs approved vs. rejected (is it trending up/down?)

Top CRs This Month: - CR-XXX: [Title] - [Type 2/3] - [Status: Approved/In Progress] - [Impact: $X, Y SP] - CR-YYY: [Title] - [Type 3] - [Status: Pending Executive Approval] - [Impact: $X, Y weeks delay]

Contingency Forecast: - Current Usage: [%]% used - Forecast: Based on current trend, contingency will be [exhausted / sufficient] - Recommendation: [If >80% used: “Recommend tightening CR approval criteria or requesting additional contingency from client”]

CR Process Health: - Average CR Cycle Time: [X days from submission to decision] - CR Board Effectiveness: [Are decisions timely? Any bottlenecks?] - CR Quality: [Are impact assessments accurate? Any surprises during implementation?]

## 8. CONTINGENCY MANAGEMENT

### 8.1 Contingency Buffer

Purpose:
20% contingency buffer is allocated to absorb Type 2 Changes (minor changes <5% budget impact) and unforeseen complexity in delivering baseline scope.

Contingency Amount: - 6-month project ($675K): $108,000 (16% of $675K = ~$108K, rounded for 20% of base effort $540K) - 9-month project ($1.8M): $360,000 (20% of base effort $1.44M)

What Contingency Covers: - ✅ Type 2 Change Requests: Minor scope additions approved by CR Board - ✅ Requirements Clarifications: Additional work needed to clarify ambiguous requirements (beyond Type 1 clarifications) - ✅ Unforeseen Technical Complexity: Unexpected challenges in legacy platform, integration issues, performance bottlenecks - ✅ Extended UAT Cycles: Additional defect fix cycles if UAT finds more defects than expected - ✅ Minor Rework: Rework due to requirements misunderstandings or design changes - ✅ Team Ramp-Up Delays: Slower-than-expected team velocity in first 2-3 sprints

What Contingency Does NOT Cover: - ❌ New Features: Entirely new functionality not related to baseline scope (requires Type 3 CR) - ❌ Major Scope Expansions: Large additions like mobile apps, data migration, new integrations (requires Type 3 CR) - ❌ TMNAS-Caused Delays: Delays due to TMNAS stakeholder unavailability, UAT vendor delays, environment issues - ❌ Third-Party Issues: Delays due to external systems being unavailable or API contracts delayed - ❌ Gold-Plating: Unnecessary enhancements or “nice-to-have” features beyond acceptance criteria

### 8.2 Contingency Tracking

Tracked By: EPAM Delivery Manager

Tracking Frequency: Updated weekly (after CR Board meeting)

Tracking Method:

Contingency Usage Table:

| Date | CR ID | CR Title | CR Type | Cost Impact | Cumulative Used | Remaining | % Used |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Week 1 | - | Initial | - | $0 | $0 | $108,000 | 0% |
| Week 4 | CR-003 | Add Cancel button to policy screen | Type 2 | $10,500 | $10,500 | $97,500 | 9.7% |
| Week 7 | CR-008 | Additional API endpoint for customer search | Type 2 | $7,000 | $17,500 | $90,500 | 16.2% |
| Week 10 | CR-015 | Extended UAT cycle (2 extra weeks) | Type 2 | $28,000 | $45,500 | $62,500 | 42.1% |
| … | … | … | … | … | … | … | … |

Contingency Thresholds & Actions:

| Threshold | Action |
| --- | --- |
| 50% used | Alert: EPAM DM notifies TMNAS PO and CTO in weekly status reportAction: Review CR approval criteria; consider rejecting lower-value Type 2 CRs |
| 75% used | Warning: EPAM DM escalates to Steering CommitteeAction: Tighten CR approval criteria; only approve high-value CRs; consider descoping lower-priority baseline stories |
| 90% used | Critical: EPAM DM escalates to Executive Sponsors (CIO/CTO)Action: Inform client that contingency is nearly exhausted; all further changes will be Type 3 (require contract amendment) |
| 100% used | Exhausted: All further changes are Type 3 (require contract amendment and additional budget)Action: Client must decide: Accept remaining baseline scope as-is, or pay for additional changes |

### 8.3 Contingency Replenishment (Not Recommended)

Question: Can contingency be replenished if exhausted?

Answer: Generally NO for Fixed Fee projects.

Rationale: - Contingency is a risk buffer, not a “feature pool” - If contingency is exhausted, it indicates higher-than-expected change volume or requirements uncertainty - Replenishing contingency essentially converts Fixed Fee to Time & Materials (defeats the purpose of Fixed Fee)

Exception: - If TMNAS requests contingency replenishment, it requires: - Executive Sponsor approval (CIO/CTO) - Contract amendment (additional budget) - Treated as Type 3 Change Request

Alternative to Replenishment: - Descope baseline scope to create capacity for additional changes - Example: Defer lower-priority user stories (e.g., US-007 Technical Debt Management, US-014 Coverage Analysis Agent) to create “headroom” for approved Type 2 CRs

## 9. BASELINE MANAGEMENT

### 9.1 Project Baselines

Definition: A baseline is an approved version of a project artifact (scope, schedule, budget) that serves as a reference point for measuring project performance and managing changes.

Project Rambo Baselines:

1. Scope Baseline - Version 1.0: 16 user stories, 202 story points (defined in Scope Management Plan) - Approved: Client workshop (TBD - Late March/Early April 2026) - Change Process: Type 2 CRs adjust scope within contingency; Type 3 CRs require contract amendment and new baseline version

2. Schedule Baseline - Version 1.0: April 1 - September 30, 2026 (6-month) or April 1 - December 31, 2026 (9-month) - Milestones: M0 (Kickoff), M1 (Sprint 4), M2 (Sprint 7), M3 (Sprint 10), M4 (60 days post go-live) - Approved: Client workshop - Change Process: Type 2 CRs may cause minor milestone delays (<1 sprint); Type 3 CRs may extend project timeline (requires contract amendment)

3. Budget Baseline - Version 1.0: $675,000 (6-month) or $1,800,000 (9-month) - Breakdown: Base effort + 20% contingency + travel - Approved: Contract signing - Change Process: Type 2 CRs absorbed in contingency; Type 3 CRs require additional budget (contract amendment)

4. Quality Baseline - Version 1.0: Definition of Done, Definition of Ready, Quality Gates (defined in Project Charter) - Approved: Client workshop - Change Process: Changes to quality standards (e.g., reduce code coverage from 85% to 70%) require CR Board approval; significant changes require Executive approval

### 9.2 Baseline Versioning

Baseline Version Numbering:

Minor Changes (Type 2 CRs): - Version 1.1, 1.2, 1.3, etc. - Example: CR-008 adds 3 SP to scope → Scope Baseline v1.1 (202 → 205 SP)

Major Changes (Type 3 CRs with contract amendments): - Version 2.0, 3.0, 4.0, etc. - Example: CR-025 adds mobile app (34 SP, $120K) → Scope Baseline v2.0 (202 → 236 SP), Budget Baseline v2.0 ($675K → $795K)

Baseline Change Documentation:

Each baseline change includes: - Change Description: What changed and why (reference CR ID) - Impact Summary: Scope, schedule, budget changes (quantified) - Approval: CR Board approval (Type 2) or Executive approval + contract amendment (Type 3) - Effective Date: Date new baseline takes effect - Previous Version: Reference to superseded baseline version

### 9.3 Baseline Communication

All baseline changes are communicated to: - EPAM Team: Via team meeting, email, updated documents in shared repository - TMNAS Stakeholders: Via weekly status report, Steering Committee presentation, updated Project Charter

Communication Timeline: - Type 2 Baseline Changes: Communicated within 1 week of CR Board approval - Type 3 Baseline Changes: Communicated immediately upon Executive approval and contract amendment execution

## 10. CHANGE CONTROL GOVERNANCE

### 10.1 Governance Structure

Three-Tier Governance:

Tier 1: Operational Level (Weekly) - Change Control Board - Reviews and approves Type 2 CRs - Participants: EPAM DM + BA + TMNAS PO + CTO - Authority: Approve/reject Type 2 CRs; recommend Type 3 CRs to Tier 2

Tier 2: Executive Level (As Needed) - Executive Sponsors - Approve Type 3 CRs requiring contract amendments - Participants: TMNAS CIO + CTO + EPAM Account Manager - Authority: Approve/reject Type 3 CRs; authorize contract amendments

Tier 3: Strategic Level (Monthly) - Steering Committee - Reviews CR trends, contingency usage, escalations - Participants: TMNAS CIO + CTO + EPAM Program Manager + Account Manager + Delivery Manager - Authority: Resolve CR disputes; adjust CR approval criteria if needed; strategic direction on scope trade-offs

### 10.2 Escalation Path for Change Control

Level 1: CR Board (Weekly) - Decision Timeframe: 1 week from CR submission - Escalate If: CR Board is deadlocked (2-2 vote), or CR is Type 3 (requires Executive approval)

Level 2: Executive Sponsors (Type 3 CRs, As Needed) - Decision Timeframe: 2 weeks from CR Board recommendation - Escalate If: Executives cannot reach consensus, or CR has strategic implications

Level 3: Steering Committee (Monthly) - Decision Timeframe: Next monthly meeting (up to 4 weeks) - Final Authority: Steering Committee has final say on CR disputes

## 11. CHANGE CONTROL TRAINING & ONBOARDING

### 11.1 Change Control Training

Who Needs Training: - EPAM Team (all members) - Sprint 0 - TMNAS Stakeholders (PO, CTO, BA) - Client workshop

Training Content: - Change Request types (Type 1, 2, 3) and thresholds - How to submit a Change Request (template, process) - Change Control Board process and decision-making - Contingency management and tracking - Impact assessment methodology - CR log and how to track CR status

Training Delivery: - EPAM Team: 1-hour training session during Sprint 0 (April 1-2, 2026) - TMNAS Stakeholders: Presented during client workshop (Late March/Early April 2026)

### 11.2 Change Control Onboarding Checklist

For EPAM Team: - ☐ Read Change Control Plan document - ☐ Attend Change Control training session - ☐ Access CR log (Jira or Excel) - ☐ Understand how to submit a CR (if they have a concern or suggestion) - ☐ Understand impact of changes on Fixed Fee project (margin, timeline)

For TMNAS Stakeholders: - ☐ Understand difference between Type 1, 2, 3 CRs - ☐ Know how to submit a CR (via TMNAS Product Owner or directly to EPAM DM) - ☐ Understand CR approval process and timelines - ☐ Understand contingency limitations (20% buffer, not unlimited) - ☐ Commit to weekly CR Board attendance (Product Owner, CTO)

## 12. APPENDICES

### Appendix A: Change Request Template

═══════════════════════════════════════════════════════════════
                    CHANGE REQUEST FORM
                    TMNAS - PROJECT RAMBO
═══════════════════════════════════════════════════════════════

CHANGE REQUEST ID: CR-_____ (Assigned by EPAM DM)
SUBMISSION DATE: _______________
SUBMITTER NAME: _______________________
SUBMITTER ROLE: _______________________
SUBMITTER ORGANIZATION: ☐ TMNAS ☐ EPAM

───────────────────────────────────────────────────────────────
SECTION 1: CHANGE REQUEST DESCRIPTION
───────────────────────────────────────────────────────────────

CR TITLE (Short, descriptive):
________________________________________________________________

BUSINESS JUSTIFICATION (Why is this change needed?):
________________________________________________________________
________________________________________________________________
________________________________________________________________

CURRENT STATE (What exists today?):
________________________________________________________________
________________________________________________________________

PROPOSED CHANGE (What is requested? Be specific.):
________________________________________________________________
________________________________________________________________
________________________________________________________________

IMPACT IF CR IS NOT APPROVED (Risks, business consequences):
________________________________________________________________
________________________________________________________________

───────────────────────────────────────────────────────────────
SECTION 2: IMPACT ASSESSMENT (Completed by EPAM Delivery Manager)
───────────────────────────────────────────────────────────────

ASSESSMENT DATE: _______________
ASSESSED BY: _______________________ (EPAM Delivery Manager)

A. SCOPE IMPACT
   User Stories Affected: _______________________________________
   New User Stories Required: ___________________________________
   Story Points Added: _____ SP
   Story Points Removed: _____ SP
   Net Scope Change: _____ SP (Added - Removed)

B. SCHEDULE IMPACT
   Sprints Affected: Sprint(s) _____
   Sprint Delay: ☐ No delay ☐ Delay by _____ week(s)
   Milestone Impact: ☐ M1 ☐ M2 ☐ M3 ☐ M4 - Delay by _____ weeks
   Critical Path Impact: ☐ Yes ☐ No
   Go-Live Impact: ☐ No delay ☐ Delay by _____ weeks

C. COST IMPACT
   Estimated Cost: $_____________ OR _____% of budget
   Calculation: _____ SP × $3,500/SP = $__________
   
   CR TYPE CLASSIFICATION:
   ☐ Type 1 (Clarification) - No impact
   ☐ Type 2 (Minor) - <5% budget (<$33.75K for 6-month, <$90K for 9-month)
   ☐ Type 3 (Major) - >5% budget (>$33.75K for 6-month, >$90K for 9-month)

   Contingency Impact (Type 2 only): $_________ of $108K (____%)

D. RISK IMPACT
   New Risks Introduced:
   ________________________________________________________________
   
   Existing Risks Mitigated:
   ________________________________________________________________
   
   Net Risk Assessment: ☐ Increase ☐ Decrease ☐ Neutral

E. QUALITY IMPACT
   Technical Debt: ☐ Increase ☐ Decrease ☐ No change
   Code Coverage: ☐ Positive ☐ Negative ☐ Neutral
   Architecture Impact: ☐ Significant ☐ Minor ☐ None
   Security/Compliance: ☐ Impact ☐ No impact

F. RESOURCE IMPACT
   Team Capacity: ☐ Can absorb ☐ Requires additional capacity
   Skill Gap: ☐ Yes (training/hiring needed) ☐ No
   Key Personnel Required: ☐ Yes (specify: _______) ☐ No

G. DEPENDENCIES
   New Dependencies Introduced: ___________________________________
   Existing Dependencies Affected: ________________________________

H. ALTERNATIVES CONSIDERED
   Alternative 1: ________________________________________________
   Alternative 2: ________________________________________________
   Do Nothing (Consequences): ____________________________________

I. EPAM RECOMMENDATION
   ☐ APPROVE - Rationale: _______________________________________
   ☐ REJECT - Rationale: ________________________________________
   ☐ DEFER - Rationale: _________________________________________
   ☐ APPROVE WITH CONDITIONS - Conditions: ______________________

───────────────────────────────────────────────────────────────
SECTION 3: CR BOARD DECISION (Completed by CR Board)
───────────────────────────────────────────────────────────────

CR BOARD MEETING DATE: _______________
CR BOARD MEMBERS PRESENT: __________________________________________

DISCUSSION SUMMARY:
________________________________________________________________
________________________________________________________________

CR BOARD DECISION:
☐ APPROVED
☐ APPROVED WITH CONDITIONS: ____________________________________
☐ REJECTED - Rationale: ________________________________________
☐ DEFERRED - Future Consideration Date: ________________________

VOTE (Type 2 CRs): _____ FOR, _____ AGAINST, _____ ABSTAIN

IMPLEMENTATION SPRINT (if approved): Sprint _____

───────────────────────────────────────────────────────────────
SECTION 4: EXECUTIVE SPONSOR APPROVAL (Type 3 CRs ONLY)
───────────────────────────────────────────────────────────────

EXECUTIVE SPONSOR MEETING DATE: _______________

EXECUTIVE DECISION:
☐ APPROVED - Contract Amendment Required: ☐ Yes ☐ No
☐ REJECTED - Rationale: ________________________________________
☐ DEFERRED - Future Consideration: _____________________________

APPROVALS:

TMNAS CIO (Lana):       _____________________  Date: __________
TMNAS CTO (Prashant):   _____________________  Date: __________
EPAM Account Manager:   _____________________  Date: __________

CONTRACT AMENDMENT ID (if applicable): _________________________

───────────────────────────────────────────────────────────────
SECTION 5: IMPLEMENTATION & CLOSURE (Completed by EPAM BA)
───────────────────────────────────────────────────────────────

IMPLEMENTATION START DATE: _______________
IMPLEMENTATION COMPLETE DATE: _______________
ACCEPTANCE DATE (Product Owner): _______________

CR STATUS:
☐ Submitted
☐ Under Review
☐ Approved
☐ In Progress
☐ Implemented
☐ Accepted by Product Owner
☐ CLOSED

LESSONS LEARNED (Did implementation match estimate? Any surprises?):
________________________________________________________________
________________________________________________________________

═══════════════════════════════════════════════════════════════
                    END OF CHANGE REQUEST
═══════════════════════════════════════════════════════════════