## TMNAS - PROJECT RAMBO

## PROJECT CHARTER

Version: 2.0
Date: January 2025
Status: Draft - For Internal Workshop Review

### VERSION CONTROL

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | Jan 2025 | EPAM Team | Initial draft |
| 2.0 | Jan 2025 | EPAM Team | Updated scope (removed SV implementation), team structure (4 pods, 17 people), budget alignment |

### EXECUTIVE SUMMARY

Project Name: TMNAS - Project Rambo
Project Type: Fixed Fee Platform Modernization
Client: TMNAS (Insurance - Personal Lines)
Duration: 6 months (Apr-Sep 2026) OR 9 months (Apr-Dec 2026)
Budget: $675K (6-month) OR $1.8M (9-month)
Team Size: 17 FTE across 4 specialized pods
Scope: 16 user stories, 202 story points

Purpose:
Transform TMNAS RapidSure platform from legacy monolithic architecture to a modern, scalable, API-driven platform that enables rapid product launches, reduces technical debt, and establishes EPAM as a trusted platform ownership partner.

Key Deliverables:

- Business Layer API implementation

- UI modernization (JSF/IceFaces → React/Angular)

- Database optimization for high concurrency

- CI/CD pipeline automation

- AI-powered development agents deployment

- Modern governance and delivery frameworks

Success Criteria:

- Platform ready to support SV product migration

- Delivery velocity increased by ≥25%

- ≥70% AI adoption across development team

- Zero critical escalations; client satisfaction ≥4.5/5.0

## 1. PROJECT IDENTIFICATION

### 1.1 Basic Information

| Field | Value |
| --- | --- |
| Project Name | TMNAS - Project Rambo |
| Project Code | TBD (Open Question - Internal Workshop) |
| Contract/SOW Number | TBD (Open Question - Internal Workshop) |
| Customer | TMNAS |
| Industry | Insurance - Personal Lines |
| Project Type | Fixed Fee - Platform Modernization |
| Start Date | April 1, 2026 (TBD - Internal Workshop) |
| End Date - 6 month | September 30, 2026 |
| End Date - 9 month | December 31, 2026 |
| Budget - 6 month | $675,000 |
| Budget - 9 month | $1,800,000 |
| Delivery Model | Hybrid (Agile execution + Waterfall governance) |

### 1.2 Stakeholders

TMNAS Stakeholders:

| Role | Name | Responsibility |
| --- | --- | --- |
| Executive Sponsor (CIO) | Lana | Overall project sponsorship, strategic alignment, executive escalations |
| Project Sponsor (CTO) | Prashant | Technical direction, architecture approvals, Change Control Board member |
| Product Owner | TBD (Open Question - Internal Workshop) | Requirements prioritization, sprint approvals, acceptance sign-off |
| Business Analyst | TBD (Open Question - Internal Workshop) | Requirements clarification, user story validation |
| Technical Lead | TBD (Open Question - Internal Workshop) | Technical coordination, integration support |
| UAT Lead | TBD (Open Question - Internal Workshop) | UAT coordination with 3rd party vendor |

EPAM Stakeholders:

| Role | Name | Responsibility |
| --- | --- | --- |
| Delivery Manager / Program Manager | TBD (Open Question - Internal Workshop) | Overall delivery accountability, stakeholder management, escalations |
| Solution Architect | TBD (Open Question - Internal Workshop) | Technical architecture, design decisions, technology choices |
| Technical Lead / Team Lead | TBD (Open Question - Internal Workshop) | Development leadership, code quality, technical guidance |
| Business Analyst | TBD (Open Question - Internal Workshop) | Requirements analysis, backlog management, Change Control Board member |
| QA Lead | TBD (Open Question - Internal Workshop) | Test strategy, quality assurance, defect management |
| DevOps Lead | TBD (Open Question - Internal Workshop) | CI/CD pipeline, infrastructure automation, environments |
| Account Manager | TBD (Open Question - Internal Workshop) | Client relationship, commercial management, contract oversight |

## 2. BUSINESS CASE

### 2.1 Business Problem Statement

TMNAS RapidSure platform faces critical challenges that impede business growth and market competitiveness:

Technical Challenges:

- Legacy monolithic architecture limits scalability and increases maintenance costs

- Outdated UI technology (JSF/IceFaces from 2010s) degrades user experience and makes it difficult to attract modern development talent

- Lack of modern API layer prevents seamless integration with new systems and partners

- Database performance bottlenecks under high concurrency during peak renewal seasons

- High cost of change due to tightly coupled architecture—even small changes require extensive testing and lengthy deployment cycles

- Load and performance risks during peak periods threaten business continuity and customer satisfaction

Business Impact:

- Inability to rapidly launch new insurance products—SV product line delayed multiple times due to platform limitations

- Extended time-to-market for features (current baseline TBD - workshop question)

- Revenue loss from delayed product launches and competitive disadvantage

- High operational costs due to technical debt and manual processes

- Customer satisfaction risks from slow, outdated user interfaces

- Competitive disadvantage in rapidly evolving digital insurance market where competitors launch products in weeks, not months

Process Maturity Challenges:

- Immature SDLC processes lead to unpredictable delivery timelines and frequent project delays

- Lack of standardized governance causes scope creep, budget overruns, and misaligned expectations

- Insufficient quality controls result in production defects and emergency hotfixes

- Chaotic change management—changes go directly to backlog without impact assessment

- Trust deficit between TMNAS and delivery partners due to history of missed deadlines and quality issues

Strategic Need:
TMNAS requires a modern, scalable platform foundation that enables business agility, reduces time-to-market, and establishes a trusted technology partnership for long-term platform ownership and evolution.

### 2.2 Business Objectives

1. Support SV Product Launch

- Goal: Modernize platform foundation to enable future SV product releases

- Approach: Ensure architecture can handle SV product migration from legacy implementation to modernized platform

- Target: Platform ready for SV migration by project end; enable faster product line expansions (reduce launch time by 40%)

2. Improve Time-to-Market

- Goal: Accelerate product and feature delivery cycles

- Approach:

  - Reduce product launch cycle from current baseline to target (TBD - workshop question)

  - Enable parallel development through modular, API-driven architecture

  - Implement CI/CD for automated testing and faster, safer deployments

- Target: Reduce feature delivery time by 30-40%

3. Establish Trusted Partnership

- Goal: Transform EPAM relationship from staff augmentation vendor to trusted platform ownership partner

- Approach:

  - Demonstrate delivery excellence through predictable, high-quality outcomes

  - Implement transparent governance and communication

  - Deliver quick wins early to build credibility

- Target: Build foundation for long-term Managed Services relationship; achieve client satisfaction ≥4.5/5.0

4. Reduce Technical Debt

- Goal: Modernize legacy components to reduce maintenance costs and improve developer productivity

- Approach:

  - Modernize UI from JSF/IceFaces to React/Angular for better UX and developer experience

  - Implement Business Layer API for integration flexibility and future microservices evolution

  - Optimize database for high concurrency, improved performance, and scalability

  - Establish technical debt management process and prioritized backlog

- Target: Reduce cost of change by 25%; improve system performance metrics (TBD - workshop)

5. Improve Delivery Maturity

- Goal: Elevate TMNAS delivery processes from immature/chaotic to predictable and professional

- Approach:

  - Implement modern Agile/Scrum SDLC with hybrid governance for Fixed Fee control

  - Establish formal change control process with impact assessment

  - Create quality gates and Definition of Done/Ready standards

  - Build reusable governance frameworks and process templates

- Target: Achieve predictable sprint velocity; reduce scope creep incidents by 80%

6. Accelerate AI Adoption

- Goal: Leverage AI to boost developer productivity and code quality

- Approach:

  - Deploy AI-powered development agents (CodeMie: Code Analysis, Knowledge Base, Test Coverage)

  - Train team on AI-assisted development practices

  - Establish AI-driven knowledge management and automated code analysis

- Target: ≥70% of development team actively using AI agents; 30% reduction in code review time

### 2.3 Success Criteria

Technical Success Metrics:

- ✅ Business Layer API operational with ≥85% unit test coverage and comprehensive integration tests

- ✅ UI modernization complete for all in-scope modules (migration from JSF/IceFaces to React/Angular)

- ✅ Database performance improved to meet or exceed targets (baseline and targets TBD - workshop)

- ✅ CI/CD pipeline operational achieving <30 minutes build-to-deploy time with automated testing

- ✅ Zero P1/P2 defects in production for 30 consecutive days post go-live

- ✅ Code coverage ≥85% across all new and refactored modules

- ✅ Technical documentation complete including architecture diagrams, API contracts, deployment runbooks

Business Success Metrics:

- ✅ Platform ready to support SV product migration from old to new architecture

- ✅ Delivery velocity increased by ≥25% (measured in story points per sprint, baseline vs. project average)

- ✅ Time-to-market reduced from baseline to target (specific metrics TBD - workshop)

- ✅ Cost of change reduced through modular architecture and automated pipelines

- ✅ Quick wins delivered in first 2-3 sprints to build client confidence

AI Adoption Success Metrics:

- ✅ ≥70% of development team actively using AI agents (CodeMie) in daily work

- ✅ Code review time reduced by ≥30% through AI-assisted reviews

- ✅ Knowledge base agent answering ≥60% of common technical queries without human intervention

- ✅ Test coverage analysis automated with recommendations for improvement areas

Partnership Success Metrics:

- ✅ Client satisfaction score ≥4.5/5.0 across dimensions (delivery, communication, quality, responsiveness)

- ✅ Zero critical escalations to executive level (Lana/Prashant) during project

- ✅ On-time, on-budget delivery for all major milestones

- ✅ Approval to proceed with Phase 2 / MSP engagement as strategic partner

Quality Success Metrics:

- ✅ All quality gates passed before UAT handoff

- ✅ UAT pass rate ≥95% (minimal defects found in UAT)

- ✅ Production defect rate <1% of delivered story points

- ✅ Performance SLAs met for 30 consecutive days in production

## 3. PROJECT SCOPE

### 3.1 In-Scope

Total Scope: 16 User Stories, 202 Story Points

Organized by Epic:

#### Epic 1: Governance & SDLC (34 Story Points)

US-001: Strategic Planning & Roadmap Implementation (13 SP)

- Implement strategic planning framework aligned with TMNAS business goals

- Create product roadmap with quarterly objectives

- Establish OKR (Objectives & Key Results) tracking system

- Deliverable: Strategic planning framework, product roadmap (12-month view)

US-002: Unified Delivery Framework Rollout (13 SP)

- Design and implement standardized Agile/Scrum delivery framework

- Create process templates (sprint planning, review, retrospective)

- Train TMNAS team on new delivery processes

- Deliverable: Unified delivery framework documentation, process templates

US-003: AI-Enhanced Estimation & Change Control (8 SP)

- Implement story point estimation guidelines with AI assistance

- Create formal Change Request (CR) process with Type 1/2/3 categorization

- Establish Change Control Board with weekly cadence

- Deliverable: Estimation guidelines, CR process document, CR tracking log template

#### Epic 2: Requirements & Solutioning (16 Story Points)

US-004: Requirements Quality Improvement Framework (8 SP)

- Implement Definition of Ready (DoR) standards

- Create user story templates with acceptance criteria guidelines

- Establish requirements review process with quality checklist

- Deliverable: DoR documentation, user story templates, requirements quality checklist

US-005: Centralized Knowledge Library (8 SP)

- Build centralized knowledge repository (Confluence or similar)

- Migrate existing documentation to centralized location

- Implement search and tagging system for easy discovery

- Deliverable: Centralized knowledge library with ≥80% existing docs migrated

#### Epic 3: Development & QA (21 Story Points)

US-006: QA Shift-Left with AI Test Generation (13 SP)

- Implement shift-left testing practices (unit tests, integration tests in CI/CD)

- Deploy AI-powered test case generation tools

- Train QA team on automation frameworks (Selenium, JUnit, etc.)

- Achieve ≥70% test automation coverage for new code

- Deliverable: Test automation framework, ≥70% automation coverage, QA training materials

US-007: Technical Debt Management System (8 SP)

- Create technical debt backlog with prioritization framework

- Implement technical debt tracking in Jira with custom fields

- Establish technical debt reduction goals (e.g., 20% of sprint capacity)

- Deliverable: Technical debt backlog, tracking system, reduction roadmap

#### Epic 4: Deployment & Infrastructure (21 Story Points)

US-017: Automated CI/CD Pipeline with AI Optimization (13 SP)

- Implement automated CI/CD pipeline (Jenkins/GitLab CI)

- Integrate automated testing (unit, integration, code quality scans)

- Achieve <30 min build-to-deploy time

- Implement AI-powered build optimization and failure analysis

- Deliverable: Operational CI/CD pipeline with <30 min deployment time

US-018: Environment Automation and Management (8 SP)

- Automate environment provisioning (DEV, QA environments)

- Implement Infrastructure-as-Code (Terraform/Ansible)

- Create environment health monitoring dashboards

- Deliverable: Automated environment provisioning, IaC scripts, monitoring dashboards

#### Epic 5: Platform Modernization (76 Story Points) - CRITICAL

US-008: Business Layer API Implementation (21 SP) - CRITICAL PATH

- Design and implement RESTful Business Layer API using Spring Boot/Spring MVC

- Expose core business capabilities (Policy Management, Rating, Underwriting - scope TBD workshop)

- Implement API Gateway pattern with Azure API Management

- Implement OAuth2/JWT authentication and authorization

- Achieve ≥85% unit test coverage

- Create API documentation (Swagger/OpenAPI)

- Deliverable: Operational Business Layer API with ≥10 endpoints, API documentation, ≥85% test coverage

US-009: Product Configuration API Standardization (13 SP)

- Standardize Product Configuration API for consistent product setup

- Migrate existing configuration logic to new API

- Implement versioning and backward compatibility

- Deliverable: Product Configuration API operational, migration complete

US-010: Database Optimization for High Concurrency (21 SP) - CRITICAL PATH

- Analyze database performance bottlenecks (slow queries, locking issues)

- Optimize database schema and indexing strategy

- Implement connection pooling and query optimization

- Enhance Redis caching strategy (Redisson configuration)

- Conduct load testing to validate performance improvements

- Deliverable: Database performance improved to meet targets (TBD workshop), load test results

US-011: UI Technology Modernization (21 SP)

- Migrate UI from JSF/IceFaces to React/Angular (technology choice TBD - workshop)

- Modernize user experience with responsive design (mobile, tablet, desktop)

- Implement component library for reusable UI components

- Integrate with Business Layer API (US-008 dependency)

- Deliverable: UI modernized for all in-scope modules, responsive design implemented

#### Epic 6: AI Adoption (34 Story Points)

US-012: Code Analysis Agent Implementation (13 SP)

- Deploy CodeMie Code Analysis Agent

- Integrate with CI/CD pipeline for automated code review

- Train development team on AI-assisted code reviews

- Achieve ≥70% team adoption

- Deliverable: Code Analysis Agent operational, ≥70% team adoption, code quality metrics dashboard

US-013: Knowledge Base Agent for Documentation (13 SP)

- Deploy CodeMie Knowledge Base Agent

- Index existing documentation and codebase

- Train team on using agent for technical queries

- Achieve ≥60% query resolution without human intervention

- Deliverable: Knowledge Base Agent operational, ≥60% automated query resolution

US-014: Coverage and Rating Analysis Agent (8 SP)

- Deploy Test Coverage Analysis Agent

- Implement automated test coverage recommendations

- Integrate with CI/CD for coverage tracking

- Deliverable: Coverage Analysis Agent operational, automated coverage reports

#### Additional In-Scope Items:

Platform Upgrade for SV Product Support:

- Upgrade platform architecture to support future SV product migration

- Ensure Business Layer API can accommodate SV product business logic

- Note: SV product implementation itself is OUT OF SCOPE (separate team, separate project)

### 3.2 Out-of-Scope

The following items are explicitly excluded from this project scope. Any work on these items will require a formal Change Request with budget and timeline impact assessment.

Product Implementation:

- ❌ SV Product implementation - The actual development of SV product line features, business logic, and workflows is handled by a separate TMNAS team on the existing architecture. This project provides the modernized platform foundation for future SV migration only.

- ❌ CCD Integration - Integration with CCD system has been removed from project scope.

Data Migration:

- ❌ Historical data migration - Migration of historical policy, claims, and customer data from legacy systems. This may be included in Phase 2 (9-month option) pending workshop discussions.

Training & Support:

- ❌ End-user training programs - Training for insurance agents, underwriters, and business users on application functionality. TMNAS is responsible for end-user training.

- ❌ Production L1/L2/L3 support post-warranty - Ongoing production support after 60-day warranty period. Building an MSP support team may be included in Phase 2 (9-month option).

Testing Execution:

- ❌ Performance test execution - TMNAS is responsible for executing performance and load testing, likely with external vendor support. EPAM provides ad-hoc support as needed.

- ❌ Security testing execution and penetration testing - TMNAS is responsible for security assessments and penetration testing. EPAM ensures code follows secure coding practices (OWASP guidelines).

- ❌ UAT test execution - TMNAS coordinates UAT activities with their designated 3rd party testing vendor. EPAM provides defect triage support and prioritization guidance during UAT.

Infrastructure & Operations:

- ❌ Infrastructure provisioning and management - TMNAS is responsible for all production and UAT infrastructure, including servers, databases, networks, and cloud resources.

- ❌ License procurement - All development tools, testing tools, and software licenses are provided by TMNAS via VDI environments. No additional license procurement by EPAM.

- ❌ Production deployment execution - TMNAS operations team executes production deployments. EPAM provides deployment runbooks, support during deployment windows, and post-deployment validation.

External Integrations:

- ❌ Integration with systems beyond those specified in backlog - Only integrations explicitly called out in the 16 user stories are in scope (e.g., Azure API Management, Salesforce RS Sync via existing interfaces). New integration requests require Change Requests.

- ❌ Salesforce customization - Integration with Salesforce is via existing RS Sync interface only; no Salesforce platform customizations or enhancements.

- ❌ Third-party vendor system modifications - EPAM does not modify systems owned by third-party vendors (e.g., Common Services, Image Right, Path). Integration is via published APIs and contracts only.

## 4. BUDGET & COST

### 4.1 Budget Options

Option 1: 6-Month Engagement - $675,000

| Category | Amount | % of Total | Details |
| --- | --- | --- | --- |
| Development Effort | $540,000 | 80% | 202 story points across 10 sprints, 17 FTE blended team |
| Contingency Buffer (20%) | $108,000 | 16% | High-risk mitigation for requirements uncertainty, legacy complexity, integration dependencies |
| Travel & Expenses | $27,000 | 4% | Business trips for workshops, go-live support (quantity TBD - workshop) |
| TOTAL | $675,000 | 100% | Aligned with $450K per 4-month billing structure |

Scope: 16 user stories, 202 story points
Timeline: April 1 - September 30, 2026 (6 months, 10 two-week sprints)
Team: 17 FTE across 4 specialized pods

Option 2: 9-Month Engagement - $1,800,000

Structure: 3 phases, quarterly billing

| Phase | Duration | Scope Summary | Budget |
| --- | --- | --- | --- |
| Phase 1: Foundation | Months 1-3 (Sprints 1-6) | Governance frameworks (US-001-003), Business Layer API (US-008), Database Optimization (US-010), CI/CD (US-017, US-018) | $600,000 |
| Phase 2: Modernization | Months 4-6 (Sprints 7-12) | UI Modernization (US-011), Product Config API (US-009), AI Agents (US-012-014), QA & Requirements (US-004-007) | $600,000 |
| Phase 3: Expansion | Months 7-9 (Sprints 13-18) | Additional scope TBD (workshop discussion): Possible items include historical data migration, additional UI modules, MSP team setup, advanced integrations, additional AI agents | $600,000 |
| TOTAL | 9 months | ~350 story points (202 SP + ~148 SP Phase 3 TBD) | $1,800,000 |

Timeline: April 1 - December 31, 2026 (9 months, 18 two-week sprints)
Team: 17-20 FTE (may scale up slightly in Phase 3 depending on scope)

### 4.2 Cost Assumptions

Rate Structure:

- Blended hourly rate: ~$60/hour (average across roles and locations)

- Locations: CEE2 (Poland+), Ukraine, GUKKA

- No onshore presence (cost savings vs. onshore-heavy teams)

Effort Assumptions:

- Story point velocity: 20-22 story points per sprint (team of 17 FTE)

- Focus factor: 65% productive time (35% overhead for meetings, ceremonies, admin, knowledge sharing)

- Sprint length: 2 weeks (10 working days)

- Working hours per sprint per FTE: 80 hours × 65% = 52 productive hours

Contingency Rationale (20%):

- High-risk project factors:

  - Immature client processes and governance

  - Legacy platform complexity with limited documentation

  - Requirements expected to evolve during execution

  - Multiple 3rd party dependencies (UAT vendor, external systems)

  - Trust deficit requiring extra communication and transparency efforts

- Industry standard: 15-20% contingency for high-risk Fixed Fee projects

- Usage: Contingency covers Type 2 Change Requests (<5% budget impact), unforeseen technical challenges, and extended UAT/defect resolution cycles

Excluded Costs (TMNAS Responsibility):

- Infrastructure costs (cloud hosting, servers, databases)

- Software licenses (development tools provided via TMNAS VDIs)

- UAT and performance testing execution (3rd party vendor)

- Production support post-warranty period

Travel & Expenses:

- Assumed: 2-3 business trips for key personnel (workshops, go-live support)

- Cost per trip: ~$3,000-$5,000 per person (flights, hotel, meals for 3-5 days)

- Total travel budget: $27K (6-month), adjustable based on actual need

- Note: Travel quantity and necessity TBD during workshop discussions

### 4.3 Payment Terms

6-Month Option - Milestone-Based Payments:

| Milestone | Timing | Deliverables | Payment | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| M0: Kickoff | Sprint 0 (Weeks 0-1) | Project Charter signed, Team onboarded, Dev environment operational | 10% ($67.5K) | Signed Project Charter, Team access granted, Dev environment validated |
| M1: Foundation | End Sprint 4 (Week 8) | US-008 Business API, US-010 DB Optimization, US-017/018 CI/CD & Environments, US-001-003 Governance | 30% ($202.5K) | API functional with ≥85% test coverage, DB performance baseline met, CI/CD operational (<30 min deploy), Governance frameworks documented |
| M2: Core Modernization | End Sprint 7 (Week 14) | US-011 UI Modernization (Phase 1 - 2+ modules), US-009 Product Config API, US-012 Code Analysis Agent | 30% ($202.5K) | UI migrated for ≥2 modules, Product Config API operational, Code Analysis Agent deployed with ≥70% team adoption |
| M3: Platform Complete | End Sprint 10 (Week 20) | US-011 UI Complete (all modules), US-013/014 AI Agents, US-004-007 Requirements/QA/TechDebt | 20% ($135K) | All UI migrated, All AI agents operational, QA automation ≥70%, Tech debt backlog created |
| M4: Warranty Complete | 60 days post go-live | Defect fixes (P1/P2 only), Performance tuning, Knowledge transfer complete | 10% ($67.5K) | Zero P1/P2 defects for 30 consecutive days, Performance SLAs met, KT documentation delivered |

9-Month Option - Quarterly Billing:

| Phase | Payment | Due Date | Acceptance Criteria |
| --- | --- | --- | --- |
| Phase 1 | $600K | End of Month 3 | Foundation deliverables (M1 criteria above) |
| Phase 2 | $600K | End of Month 6 | Modernization deliverables (M2 + M3 criteria above) |
| Phase 3 | $600K | End of Month 9 + 60 days warranty | Phase 3 scope deliverables (TBD workshop) + warranty criteria |

Invoice Process:

- Invoices submitted within 5 business days of milestone completion

- TMNAS has 10 business days to review deliverables and provide acceptance or feedback

- Payment due within 30 days of acceptance

- Disputes escalated to Steering Committee within 5 business days

## 5. TEAM STRUCTURE

### 5.1 Team Organization

Total Team Size: 17 FTE across 4 specialized pods

Note: Pod 2 (SV Product Launch) has been removed from scope as SV product implementation is out of scope for this project.

#### Pod 1: Platform Modernization (6 people)

Focus: Business Layer API, Product Configuration API, Database Optimization, Technical Debt Management

Team Composition:

- 1 × Solution Architect (50% allocation, shared with other pods for architectural guidance)

- 3 × Senior Backend Developers (Java, Spring Boot, Hibernate, SQL)

- 1 × Database Administrator / Performance Engineer (MS SQL Server optimization)

- 1 × QA Engineer (Backend testing, API testing)

Assigned User Stories:

- US-008: Business Layer API Implementation (21 SP) - Sprints 1-3

- US-009: Product Configuration API Standardization (13 SP) - Sprints 4-6

- US-010: Database Optimization for High Concurrency (21 SP) - Sprints 1-4 (parallel with US-008)

- US-007: Technical Debt Management System (8 SP) - Sprints 7-8

Total Story Points: 63 SP
Sprint Allocation: Sprints 1-8

#### Pod 3: UI & Frontend (4 people)

Focus: UI Technology Modernization (JSF/IceFaces → React/Angular)

Team Composition:

- 1 × Frontend Architect / Senior Frontend Developer (React/Angular expert)

- 2 × Frontend Developers (JavaScript, React/Angular, CSS/SCSS)

- 1 × QA Engineer (UI/UX testing, cross-browser testing, accessibility testing)

Assigned User Stories:

- US-011: UI Technology Modernization (21 SP) - Sprints 5-10

Total Story Points: 21 SP
Sprint Allocation: Sprints 5-10

Dependencies:

- Depends on US-008 (Business Layer API) being operational by Sprint 4-5 for API integration

#### Pod 4: Process & AI (4 people)

Focus: Governance Frameworks, Requirements Quality, AI Agent Deployment

Team Composition:

- 1 × Project Manager / Scrum Master (Process frameworks, ceremonies, governance)

- 1 × Senior Business Analyst (Requirements, user stories, DoR/DoD, knowledge management)

- 2 × AI/ML Engineers (CodeMie agent deployment, AI tool integration, training)

Assigned User Stories:

- US-001: Strategic Planning & Roadmap Implementation (13 SP) - Sprints 1-2

- US-002: Unified Delivery Framework Rollout (13 SP) - Sprints 1-2

- US-003: AI-Enhanced Estimation & Change Control (8 SP) - Sprints 2-3

- US-004: Requirements Quality Improvement Framework (8 SP) - Sprints 3-4

- US-005: Centralized Knowledge Library (8 SP) - Sprints 4-5

- US-012: Code Analysis Agent Implementation (13 SP) - Sprints 5-7

- US-013: Knowledge Base Agent for Documentation (13 SP) - Sprints 7-9

- US-014: Coverage and Rating Analysis Agent (8 SP) - Sprints 9-10

Total Story Points: 84 SP
Sprint Allocation: Sprints 1-10 (continuous throughout project)

#### Pod 5: Infrastructure & DevOps (3 people)

Focus: CI/CD Pipeline, Environment Automation, QA Shift-Left

Team Composition:

- 1 × DevOps Lead / Senior DevOps Engineer (Jenkins/GitLab CI, Infrastructure-as-Code)

- 2 × DevOps Engineers (Automation, scripting, monitoring, environment management)

Assigned User Stories:

- US-006: QA Shift-Left with AI Test Generation (13 SP) - Sprints 2-4

- US-017: Automated CI/CD Pipeline with AI Optimization (13 SP) - Sprints 1-3

- US-018: Environment Automation and Management (8 SP) - Sprints 3-4

Total Story Points: 34 SP
Sprint Allocation: Sprints 1-4 (early focus to establish foundation)

### 5.2 Key Personnel (Retention Required)

The following roles are critical to project success and must be retained for the project duration (6 or 9 months). Replacement of key personnel requires:

- 30-day advance notice

- Overlap period for knowledge transfer (minimum 2 weeks)

- Approval from TMNAS Project Sponsor

Key Personnel:

- Delivery Manager / Program Manager - Overall accountability, stakeholder management, escalation point

- Solution Architect - Technical vision, architecture decisions, ensures consistency across pods

- Technical Lead - Development leadership, code quality standards, technical mentorship

Attrition Management:

- Expected attrition: 10% (industry standard)

- Mitigation: Continuous knowledge sharing, pair programming, comprehensive documentation, backup resources identified

- Knowledge Transfer Protocol: 30-day KT process for any departing team member (existing KT plan to be updated)

### 5.3 Ramp-Up / Ramp-Down Plan

Ramp-Up (Sprint 0-1, Weeks 0-2):

| Week | Activity | Team Size |
| --- | --- | --- |
| Week 0 | Onboarding prep: VDI setup, access provisioning, tool installation | 3 people (DM, Architect, Lead) |
| Week 1 | Sprint 0: Environment validation, architecture review, backlog refinement | 12 people (50% team) |
| Week 2 | Sprint 1: Full team onboarded, first development sprint begins | 17 people (100% team) |

Full Capacity (Sprints 2-9, Weeks 3-18):

- Team Size: 17 FTE

- All pods operating at full capacity

Ramp-Down (Sprint 10+, Weeks 19-20+):

| Phase | Activity | Team Size |
| --- | --- | --- |
| Sprint 10 | Final development, UAT support, defect fixes | 17 people (100%) |
| Weeks 21-22 (Post-Sprint 10) | UAT support, production deployment prep | 12 people (70%) |
| Weeks 23-24 | Go-live support, hypercare, initial knowledge transfer | 8 people (47%) |
| Warranty Period (60 days) | Defect fixes (P1/P2 only), final knowledge transfer | 3-5 people (on-demand) |

## 6. ASSUMPTIONS

### 6.1 Client Responsibilities & Support

Access & Environment:

- TMNAS will provide access to all required environments (DEV, QA) by project kickoff (Sprint 0, Week 0). Delays in environment access will impact project timeline and may require schedule adjustments.

- TMNAS will provision Virtual Desktop Infrastructure (VDI) with pre-installed development tools, testing tools, and software licenses for all EPAM team members (17 VDIs) by Sprint 0. EPAM is not responsible for procuring additional licenses.

- TMNAS will grant database access and credentials to development and QA environments by Sprint 1, Week 2, enabling EPAM team to perform database optimization and testing activities.

Stakeholder Engagement:
4. TMNAS stakeholders will maintain availability for weekly planning sessions, sprint reviews, backlog grooming, and decision-making forums. Unavailability of key stakeholders (Product Owner, CTO, SMEs) may delay critical decisions and impact project velocity.

- TMNAS will provide timely responses to clarification requests, questions, and decisions within 2 business days to maintain project velocity. Delays beyond 2 business days may result in blocked work and schedule impacts.

- TMNAS will assign a dedicated Product Owner with authority to make prioritization decisions, approve sprint backlogs, and sign off on deliverables. Product Owner should have minimum 50% allocation to this project.

Subject Matter Experts (SMEs):
7. TMNAS will grant access to subject matter experts (SMEs) as needed for requirements validation, technical consultation, and business logic clarification. SME availability is assumed at 10-20 hours per month per domain (e.g., Underwriting, Rating, Policy Management).

### 6.2 Requirements & Scope Management

Requirements Evolution:
8. Requirements are expected to evolve during project execution as business needs are clarified and technical discoveries are made. Scope will be managed through the formal Change Request (CR) process with impact assessment for schedule and budget.

- User stories in the backlog (16 stories, 202 SP) represent the baseline scope. Any additions, modifications, or expansions beyond this baseline require a formal Change Request approved by the Change Control Board.

Out-of-Scope Boundary:
10. Out-of-scope items explicitly documented (Section 3.2) will not be included in project deliverables without a formal Change Request and budget approval. This includes SV product implementation, CCD integration, historical data migration, end-user training, and production support post-warranty.

### 6.3 Integration & Testing

Integration Approach:
11. Third-party system integration will be conducted using API contracts and mock services. EPAM is not responsible for direct integration with external systems (e.g., Salesforce, Common Services, Image Right) beyond published API specifications. Integration testing will use mocks; end-to-end testing with live external systems is TMNAS responsibility during UAT.

- API contracts and interface specifications for external systems (Salesforce RS Sync, Azure API Management, CCD if applicable) will be provided by TMNAS by Sprint 2, Week 4. Delays in receiving API contracts will delay integration development.

UAT & Testing Responsibilities:
13. TMNAS will coordinate UAT activities with their designated 3rd party testing vendor. EPAM will provide defect triage support, prioritization guidance, and fixes for confirmed defects, but is not responsible for UAT test case creation, execution, or vendor management.

- Performance and security testing execution is TMNAS responsibility, likely with external vendor support. EPAM will provide ad-hoc resources for troubleshooting and performance tuning as needed, but does not own performance test execution or infrastructure for load testing.

- UAT environment availability and 3rd party vendor engagement by Sprint 6, Week 12 is assumed. Delays in UAT environment setup or vendor availability will delay UAT start and potentially impact go-live timeline.

### 6.4 Organizational Stability

TMNAS Organization:
16. No major organizational restructuring or leadership changes at TMNAS are anticipated during project execution. Significant changes (e.g., CIO/CTO departure, business unit reorganization) may require project re-baseline and stakeholder realignment.

- TMNAS processes and governance are immature and expected to improve throughout the project. EPAM will proactively drive process maturation (governance frameworks, change control, quality gates) as project deliverables.

EPAM Team:
18. EPAM team composition will remain stable with allowance for 10% attrition (industry standard), managed through knowledge transfer protocols and backup resources. Key personnel (DM, Architect, Tech Lead) require 30-day notice and overlap for replacement.

### 6.5 Technical & Infrastructure

Technology Constraints:
19. TMNAS technology stack constraints (JBoss/WildFly, MS SQL Server, Azure API Management, existing integrations) are assumed as fixed unless architectural changes are explicitly approved through the governance process.

- No infrastructure procurement or setup by EPAM. All infrastructure (servers, databases, cloud resources, networks) is TMNAS responsibility. EPAM works within provided environments.

- Production deployment execution is TMNAS operations team responsibility. EPAM provides deployment runbooks, support during deployment windows, and post-deployment validation, but does not execute production deployments.

### 6.6 Project Management

Communication & Reporting:
22. Weekly status reports, sprint reviews, and steering committee meetings will be attended by designated TMNAS stakeholders. Consistent attendance ensures transparency and alignment.

- Change Control Board meetings will occur weekly (as needed) with representatives from both EPAM (DM, BA) and TMNAS (PO, Prashant/CTO, BA). CR decisions will be documented and tracked in shared CR log.

Business Continuity:
24. Project will not disrupt current production operations. All development and testing activities occur in isolated DEV/QA environments. Production deployment follows TMNAS change management procedures with rollback plans.

## 7. CONSTRAINTS

### 7.1 Budgetary & Timeline Constraints

Budget:

- Fixed budget allocation: $675,000 (6-month option) or $1,800,000 (9-month option) with scope, schedule, and deliverables adjusted to fit within budget. Any scope expansions require formal Change Request with budget amendment.

- 20% contingency buffer ($108K for 6-month, $360K for 9-month) is allocated for high-risk mitigation (requirements uncertainty, legacy complexity, integration challenges). Contingency is not available for new features—it covers Type 2 CRs (<5% impact) and unforeseen technical challenges.

Timeline:
3. Fixed timeline:

- 6-month option: April 1 - September 30, 2026 (10 two-week sprints)

- 9-month option: April 1 - December 31, 2026 (18 two-week sprints)

Hard deadline cannot be extended without formal contract amendment. If scope increases, lower-priority stories will be deferred to maintain timeline.

Payment:
4. Payment milestones:

- 6-month: Milestone-based (M0-M4) tied to deliverable acceptance

- 9-month: Quarterly billing aligned with phase completion

Payment terms are contractual obligations; delays in milestone acceptance may delay subsequent payments.

### 7.2 Resource & Staffing Constraints

Team Location:
5. EPAM team sourced exclusively from CEE2 (Poland+), Ukraine, and GUKKA locations. No onshore presence expansion planned. This provides cost efficiency but requires effective remote collaboration tools and practices.

- No planned onshore presence expansion; business travel on as-needed basis only (2-3 trips budgeted). Onshore travel requires advance approval and justification (e.g., critical workshops, go-live support).

Team Size:
7. Team size capped at 17 FTE across 4 specialized pods for 6-month option. Scaling beyond 17 FTE requires budget adjustment and may not be feasible mid-project due to onboarding time and productivity ramp.

- Key personnel (DM, Architect, Tech Lead) must be retained for project duration. Replacement requires 30-day notice and knowledge transfer overlap, which may impact project continuity.

### 7.3 Technical & Architectural Constraints

Technology Stack:
9. Must operate within existing TMNAS technology stack constraints unless architectural changes are explicitly approved:

- App Server: JBoss/WildFly (legacy)

- Database: MS SQL Server (cannot switch to PostgreSQL, Azure SQL, etc. without approval)

- API Gateway: Azure API Management (existing investment, must leverage)

- Caching: Redis with Redisson (existing setup)

- Messaging: Azure Service Bus, JMS

Modernization proposals (e.g., Spring Boot standalone vs. JBoss) subject to architectural review and approval.

Release Alignment:
10. Must align delivery milestones with TMNAS SV product release schedule (6-week release cadence). This constraint requires coordination with SV team and may impact sprint planning flexibility. Platform changes must be deployed in sync with SV releases to avoid integration issues.

Production Impact:
11. Must maintain zero-impact to current production operations during modernization activities. All development and testing in isolated environments (DEV, QA). Production deployments follow strict change management with rollback plans. No "big bang" cutover—phased migration approach required.

### 7.4 Infrastructure & Tooling Constraints

Infrastructure:
12. Must utilize TMNAS-provided infrastructure and development environments exclusively. EPAM cannot provision cloud resources, servers, or databases independently. All environment requests go through TMNAS infrastructure team with associated lead times.

Tools & Licenses:
13. No procurement of additional tools or licenses; must work within existing TMNAS-approved toolset provided via VDIs. If new tools are required (e.g., specialized testing tools, monitoring platforms), TMNAS must procure and provision them, which may introduce delays.

### 7.5 Stakeholder & Process Constraints

Stakeholder Availability:
14. Limited TMNAS stakeholder availability due to immature organizational processes and competing priorities. This constraint requires:

- Structured communication and meeting cadence (weekly, not ad-hoc)

- Escalation protocols for blocked decisions (escalate to CTO/CIO within 2 days)

- Asynchronous decision-making mechanisms (email approvals, shared decision logs)

Process Maturity:
15. TMNAS delivery processes are immature and evolving. EPAM must invest extra effort in:

- Process definition and documentation (governance frameworks)

- Training and change management (adopting new processes)

- Patient, consultative approach to process improvement

This constraint may slow initial sprints as processes are established.

Vendor Dependencies:
16. Dependency on 3rd party vendors for UAT and performance testing introduces schedule risk:

- EPAM has no direct control over vendor availability, quality, or timelines

- UAT delays by vendor may compress defect fix cycles and delay go-live

- Requires proactive coordination, early engagement, and buffer time in schedule

## 8. RISKS & MITIGATION

### Top 10 Project Risks

R-001: Unclear / Evolving Requirements

| Risk Description | Requirements are not fully defined upfront and will evolve as TMNAS stakeholders gain clarity on business needs and technical implementation. Immature requirements processes increase risk of misalignment and rework. |
| --- | --- |
| Impact | HIGH - Rework, scope creep, delays, budget overruns |
| Probability | HIGH - TMNAS has immature requirements processes; expect significant evolution |
| Mitigation Strategy | • Rolling wave planning: Plan 3 sprints ahead in detail; avoid over-committing far in advance • Formal CR process: All scope changes require impact assessment and approval • 20% contingency buffer: Absorbs minor changes (Type 2 CRs <5% impact) • Weekly backlog grooming: Continuous requirements clarification with TMNAS PO • Definition of Ready (DoR): No user story enters sprint without meeting DoR criteria • Frequent demos: Sprint reviews every 2 weeks to validate understanding and course-correct early |
| Owner | EPAM Delivery Manager + TMNAS Product Owner |
| Monitoring | Track: # of CRs submitted, % of stories requiring significant clarification, rework % |

R-002: TMNAS Stakeholder Availability

| Risk Description | TMNAS stakeholders (Product Owner, CTO, SMEs) have limited availability due to competing priorities and immature organizational processes. Delayed decisions block development and slow project velocity. |
| --- | --- |
| Impact | HIGH - Blocked stories, delayed sprints, team idle time, missed milestones |
| Probability | MEDIUM - Historical pattern of limited stakeholder engagement |
| Mitigation Strategy | • Dedicated TMNAS Product Owner assignment: Minimum 50% allocation to project • Escalation protocol: Decisions not made within 2 business days escalated to CTO/CIO • Asynchronous decision-making: Use email approvals, shared decision logs, Confluence for decisions that don't require meetings • Weekly steering committee: Monthly executive-level review ensures high-level alignment and unblocks escalations • Buffer stories: Maintain backlog of "ready" stories that don't require immediate stakeholder input (e.g., technical debt, refactoring) • Proactive communication: Send decision requests with clear options, deadlines, and escalation paths |
| Owner | EPAM Delivery Manager |
| Monitoring | Track: # of blocked stories, decision turnaround time, escalations to CTO/CIO |

R-003: 3rd Party UAT Delays

| Risk Description | UAT is coordinated by TMNAS with a 3rd party testing vendor. EPAM has no control over vendor availability, test quality, or timelines. UAT delays compress defect fix cycles and may delay go-live. |
| --- | --- |
| Impact | HIGH - Compressed defect fix time, delayed go-live, potential milestone payment delays |
| Probability | MEDIUM - Common issue in projects with external UAT vendors |
| Mitigation Strategy | • Early UAT planning: Engage UAT vendor in Sprint 3-4 to plan test cases, environments, schedule • EPAM drives defect triage: EPAM leads daily triage meetings during UAT to prioritize and resolve defects quickly • 2-week buffer in schedule: Plan for UAT start in Sprint 8 (Week 16) for 6-month project, allowing 2-week buffer before go-live • Parallel UAT streams: Where possible, conduct UAT in phases (e.g., API testing in Sprint 6, UI testing in Sprint 9) to spread risk • Quality gates before UAT: Ensure ≥85% code coverage, zero P1/P2 defects before UAT handoff to minimize defects found • Escalation to TMNAS CTO: If UAT delays threaten go-live, escalate to CTO/CIO for vendor management |
| Owner | EPAM Delivery Manager + TMNAS UAT Lead |
| Monitoring | Track: UAT start date (planned vs. actual), # of UAT defects found, defect resolution time, UAT completion date |

R-004: Legacy Platform Complexity

| Risk Description | RapidSure is a legacy monolithic platform with 10+ years of technical debt, tightly coupled architecture, and limited documentation. Unexpected technical challenges may emerge during modernization (e.g., hidden dependencies, undocumented business logic). |
| --- | --- |
| Impact | MEDIUM - Delays in development, increased debugging time, potential rework |
| Probability | HIGH - Legacy platforms always have surprises; expect 10-20% of stories to hit unexpected complexity |
| Mitigation Strategy | • Experienced architects: Assign senior architects with insurance domain knowledge and legacy modernization experience • Technical spikes for high-risk areas: Allocate 1-2 sprints for POCs and technical spikes (e.g., database optimization, JSF-to-React migration pattern) before committing to full implementation • POCs for critical integrations: Validate integration approaches (e.g., Azure API Management, Salesforce RS Sync) early in project (Sprint 2-3) • Architecture review checkpoints: Bi-weekly architecture reviews with TMNAS CTO to validate technical decisions and uncover hidden constraints • Incremental refactoring: Use Strangler Pattern for UI modernization—migrate one module at a time, validate, then proceed • 20% contingency buffer: Covers unexpected complexity and extended troubleshooting time |
| Owner | EPAM Solution Architect |
| Monitoring | Track: # of stories blocked by technical complexity, spike story % of total, architecture review action items |

R-005: Integration Dependencies (External Systems)

| Risk Description | RapidSure integrates with multiple external systems (Salesforce RS Sync, Azure API Management, CCD, Common Services, Image Right, etc.). Delayed API contracts, system unavailability, or integration failures may block development and testing. |
| --- | --- |
| Impact | MEDIUM - Blocked integration stories, delayed testing, potential rework if contracts change |
| Probability | MEDIUM - External systems often have availability issues or delayed documentation |
| Mitigation Strategy | • Mock-based testing strategy: Develop and test integrations using mock services based on API contracts; don't wait for live system availability • API contract-first development: Obtain API contracts (Swagger/OpenAPI specs) by Sprint 2, Week 4; develop against contracts, not live systems • Early integration testing: Conduct integration smoke tests with live external systems in Sprint 3-4 to validate contracts and uncover issues early • Dependency tracking in RAID log: Track all external system dependencies with owners, due dates, and status; escalate delays immediately • Fallback plans: For non-critical integrations, implement feature flags to deploy without integration if system is unavailable • TMNAS liaison for external teams: Request TMNAS assign a liaison to coordinate with external system teams and expedite contract delivery |
| Owner | EPAM Technical Lead + TMNAS Integration Team |
| Monitoring | Track: API contract delivery dates (planned vs. actual), integration test pass rate, external system availability % |

R-006: Team Attrition

| Risk Description | 10% annual attrition is industry standard. Team member departures during project (especially key personnel) can disrupt continuity, require knowledge transfer, and temporarily reduce team velocity. |
| --- | --- |
| Impact | MEDIUM - Temporary velocity reduction, knowledge loss, onboarding time for replacement |
| Probability | MEDIUM - Expect 1-2 team member departures over 6-9 months |
| Mitigation Strategy | • Continuous knowledge sharing: Pair programming, code reviews, documentation-as-you-go minimize knowledge silos • Comprehensive documentation: Architecture diagrams, API documentation, deployment runbooks ensure knowledge is captured • Backup resources identified: For each key role, identify backup resources who can step in with 2-week notice • 30-day knowledge transfer protocol: When team member departs, implement structured KT: documentation handoff, shadowing, Q&A sessions • Key personnel retention: Require 30-day notice and overlap for DM, Architect, Tech Lead; TMNAS approval required for replacement • Cross-training: Rotate team members across stories to build shared knowledge (e.g., backend dev works on UI story occasionally) |
| Owner | EPAM Resource Manager + Delivery Manager |
| Monitoring | Track: attrition rate, time to replace departed team members, velocity impact (sprint before/after departure) |

R-007: Performance Bottlenecks (Database, Caching)

| Risk Description | Database and caching layer are identified risk areas in current RapidSure architecture. Database optimization (US-010) may uncover deep-rooted performance issues requiring more extensive refactoring than anticipated. Performance targets may not be achieved in initial attempts. |
| --- | --- |
| Impact | MEDIUM - Extended optimization cycles, potential rework, delayed go-live if performance SLAs not met |
| Probability | MEDIUM - Performance optimization is iterative; first attempt rarely achieves all targets |
| Mitigation Strategy | • Database optimization as early priority (US-010): Start in Sprint 1-2 to identify issues early and allow time for iterative tuning • Performance testing every sprint: Conduct load tests in QA environment every 2-3 sprints to catch regressions early • Redis caching strategy optimization: Review Redisson configuration, cache hit rates, and eviction policies; tune based on profiling data • Load testing before major releases: Conduct full load tests before UAT and before production go-live to validate performance under realistic load • DBA involvement throughout project: Dedicated DBA (Pod 1) continuously monitors query performance, indexing, and database health • Escalation to TMNAS for infrastructure: If performance issues stem from infrastructure limitations (undersized DB server, network latency), escalate to TMNAS infrastructure team for resolution |
| Owner | EPAM DBA + TMNAS Infrastructure Team |
| Monitoring | Track: Database query response times, cache hit rates, load test results (TPS, response time), P95/P99 latency |

R-008: Scope Creep

| Risk Description | Immature requirements processes and evolving business needs increase risk of uncontrolled scope expansion. Without formal change control, project may exceed budget and timeline. |
| --- | --- |
| Impact | HIGH - Budget overruns, missed deadlines, team burnout, client dissatisfaction |
| Probability | HIGH - Common in Fixed Fee projects with unclear requirements |
| Mitigation Strategy | • Formal CR process: Implement Type 1/2/3 CR categorization with impact assessment (US-003 deliverable) - Type 1 (Clarification): No impact, approved by EPAM DM - Type 2 (Minor, <5%): Absorbed in contingency, requires CR Board approval - Type 3 (Major, >5%): Requires contract amendment and additional budget • Baseline scope documented and signed: Project Charter (this document) serves as scope baseline; any additions require CR • Weekly Change Control Board meetings: EPAM DM/BA + TMNAS PO/Prashant review all CRs, assess impact, approve/reject • Executive sponsor approval for Type 3 CRs: CTO/CIO must approve major changes to ensure budget and timeline understanding • Transparent impact communication: Every CR includes impact assessment (scope, schedule, cost) before approval • Defer lower-priority stories: If scope grows, move lower-priority stories out of current phase to maintain timeline |
| Owner | EPAM Delivery Manager + Change Control Board |
| Monitoring | Track: # of CRs by type, % of CRs approved vs. rejected, cumulative CR impact on budget/schedule |

R-009: Trust Deficit with TMNAS

| Risk Description | TMNAS has a 7-year relationship with EPAM but has not yet achieved "trusted partnership" status. Client constantly challenges delivery, and there is skepticism about EPAM's ability to deliver on time and budget. Trust must be earned through demonstrated delivery excellence. |
| --- | --- |
| Impact | MEDIUM - Increased scrutiny, slower approvals, escalations, client dissatisfaction even if delivery is objectively successful |
| Probability | MEDIUM - Historical pattern; trust takes time to build |
| Mitigation Strategy | • Transparent communication and reporting: Weekly status reports with traffic light dashboard (red/yellow/green), risks, issues, blockers; no surprises • Deliver quick wins early: Prioritize high-visibility, low-risk deliverables in Sprint 2-3 (e.g., CI/CD pipeline operational, governance framework documented) to build confidence • Proactive risk escalation: Don't hide problems—escalate risks early with mitigation plans; demonstrate EPAM is managing risks professionally • Demonstrate delivery excellence through quality: Exceed quality standards (≥85% code coverage, zero P1/P2 defects before UAT) to show EPAM commitment • Frequent touchpoints: Sprint reviews every 2 weeks, steering committee monthly, informal check-ins with PO/CTO as needed • Under-promise, over-deliver: Set realistic expectations, then exceed them (e.g., deliver 22 SP in sprint when committed to 20 SP) • Client education: Help TMNAS understand modern delivery practices (Agile, Fixed Fee with CR process) to align expectations |
| Owner | EPAM Delivery Manager + Account Manager |
| Monitoring | Track: Client satisfaction surveys (monthly), # of escalations to executive level, sentiment in meetings (qualitative) |

R-010: SV Product Release Schedule Alignment

| Risk Description | Platform modernization must align with TMNAS SV product release schedule (6-week release cadence). Misalignment may cause integration issues, deployment conflicts, or delays in SV product migration. |
| --- | --- |
| Impact | MEDIUM - Deployment delays, integration issues, additional coordination overhead |
| Probability | LOW - Risk is manageable with proactive coordination |
| Mitigation Strategy | • Continuous coordination with SV team: Bi-weekly sync meetings between EPAM platform team and TMNAS SV team to share roadmaps and identify conflicts • Platform readiness milestones aligned with SV releases: Ensure US-008 (Business Layer API) is operational before SV team begins API integration work • Flexible deployment windows: Plan platform deployments in sync with SV releases; avoid deploying breaking changes mid-SV release cycle • Rollback plan for failed integrations: If SV integration fails post-platform deployment, have rollback plan to revert platform changes without impacting SV production • API versioning strategy: Implement API versioning (v1, v2) to allow SV team to migrate gradually without breaking existing functionality • Early integration testing: Conduct integration smoke tests with SV team in Sprint 5-6 to validate API contracts and uncover issues before production |
| Owner | EPAM Solution Architect + TMNAS SV Product Manager |
| Monitoring | Track: SV release schedule (planned vs. actual), integration test results, deployment conflicts |

## 9. DEPENDENCIES

### Critical Path Dependencies

### 9.1 TMNAS-Provided (CRITICAL - Project Blockers)

| ID | Dependency | Description | Due Date | Owner | Impact if Delayed |
| --- | --- | --- | --- | --- | --- |
| DEP-001 | Environment Access (DEV, QA) | EPAM team requires access to TMNAS DEV and QA environments with appropriate permissions (deploy, test, troubleshoot) | Sprint 0, Week 0(April 1, 2026) | TMNAS Infrastructure Team | CRITICAL: Blocks Sprint 1 start; delays entire project timeline |
| DEP-002 | VDI Provisioning (17 Team Members) | TMNAS must provision 17 VDIs with pre-installed development tools (IntelliJ, Visual Studio, Eclipse, SQL clients), testing tools, and all necessary software licenses | Sprint 0, Week 0(April 1, 2026) | TMNAS IT Support | CRITICAL: Team cannot start work; delays Sprint 1 |
| DEP-003 | Current Architecture Documentation | Comprehensive architecture documentation including system diagrams, integration flows, API contracts, database schema, deployment architecture | Sprint 1, Week 2(April 15, 2026) | TMNAS Architecture Team | HIGH: Slows architecture review and technical spike activities; increases risk of rework |
| DEP-004 | API Contracts for External Systems | API specifications (Swagger/OpenAPI) for Salesforce RS Sync, Azure API Management, CCD, Common Services, Image Right, and other external systems | Sprint 2, Week 4(April 29, 2026) | TMNAS Integration Team | HIGH: Blocks integration development (US-008, US-009); forces development against assumptions |
| DEP-005 | Database Access and Credentials | Connection strings, credentials, and permissions for RapidSureDB (main), RapidSureDB Config, Reference DB, Static Codes DB in DEV and QA environments | Sprint 1, Week 2(April 15, 2026) | TMNAS DBA Team | HIGH: Blocks US-010 (Database Optimization) and backend development |

### 9.2 TMNAS SME Availability (HIGH PRIORITY)

| ID | Dependency | Description | Frequency | Owner | Impact if Delayed |
| --- | --- | --- | --- | --- | --- |
| DEP-006 | Business Requirements Clarification | Access to business SMEs (Underwriting, Rating, Policy Management, Claims) for user story clarification, acceptance criteria validation, business logic questions | ONGOING(10-20 hours per month per SME) | TMNAS Product Owner | HIGH: Blocked stories, delayed sprints, rework due to misunderstood requirements |
| DEP-007 | Technical Architecture Decisions | Access to TMNAS CTO / Prashant and technical architects for architecture approvals, technology choices, integration approaches | ONGOING(Bi-weekly architecture reviews) | TMNAS CTO / Prashant | HIGH: Delayed architecture decisions block development; risk of unapproved technical approaches |
| DEP-008 | UAT Coordination and Vendor Management | TMNAS UAT Lead coordinates with 3rd party testing vendor for test planning, environment setup, test execution, defect reporting | Sprint 6, Week 12(June 10, 2026) | TMNAS QA Manager | HIGH: UAT delays compress defect fix cycles; may delay go-live |
| DEP-009 | Production Deployment Approvals | TMNAS Change Advisory Board (CAB) or equivalent approves production deployment plans, deployment windows, rollback plans | Sprint 10, Week 20(August 5, 2026) | TMNAS CIO / Lana | CRITICAL: Blocks production go-live; delays project completion |

### 9.3 Third-Party System Dependencies

| ID | Dependency | Description | Due Date | Owner | Impact if Delayed |
| --- | --- | --- | --- | --- | --- |
| DEP-010 | Salesforce RS Sync API Availability | Salesforce RS Sync system available for integration testing; API endpoints operational in QA environment | Sprint 3, Week 6(May 13, 2026) | Salesforce Admin Team (TMNAS or vendor) | MEDIUM: Delays integration testing; forces mock-based testing only |
| DEP-011 | Azure API Management Configuration | Azure API Management gateway configured in QA environment with policies, authentication, rate limiting for RapidSure APIs | Sprint 4, Week 8(May 27, 2026) | TMNAS Cloud Team | MEDIUM: Delays API testing; may require rework if configuration differs from assumptions |
| DEP-012 | UAT Vendor Availability and Test Environment | 3rd party UAT vendor engaged, test plan created, UAT environment provisioned and ready for testing | Sprint 6, Week 12(June 10, 2026) | TMNAS QA Vendor (3rd party) | HIGH: Delays UAT start; compresses UAT cycle; may delay go-live |

### 9.4 Internal EPAM Dependencies

| ID | Dependency | Description | Due Date | Owner | Impact if Delayed |
| --- | --- | --- | --- | --- | --- |
| DEP-013 | Team Onboarding and Ramp-Up | EPAM Resource Manager recruits and onboards 17 team members; completes background checks, contracts, tool access (VPN, Jira, Git, etc.) | Sprint 0-1, Weeks 0-2(April 1-15, 2026) | EPAM Resource Manager | CRITICAL: Delays project start; reduces Sprint 1-2 velocity |
| DEP-014 | Solution Architecture Review and Approval | EPAM Chief Architect reviews proposed solution architecture, validates technical approach, approves technology choices | Sprint 1, Week 2(April 15, 2026) | EPAM Chief Architect | HIGH: Risk of unapproved architecture; may require rework if architecture is rejected |
| DEP-015 | AI Agent Licensing and Setup (CodeMie) | EPAM AI/Run team provisions CodeMie licenses (Code Analysis, Knowledge Base, Coverage Analysis agents) and provides onboarding support | Sprint 2, Week 4(April 29, 2026) | EPAM AI/Run Team | MEDIUM: Delays US-012, US-013, US-014 (AI agent deployment); reduces AI adoption benefits |

## 10. QUALITY MANAGEMENT

### 10.1 Definition of Ready (DoR)

A user story is "Ready" to be pulled into a sprint when it meets the following criteria:

✅ User story has clear, testable acceptance criteria written in Given-When-Then format
✅ Dependencies identified and documented (external systems, other user stories, infrastructure)
✅ Story sized and estimated (story points assigned, fits within one 2-week sprint)
✅ Technical design approach agreed upon by development team and architect
✅ Test approach defined (unit tests, integration tests, manual tests, test data requirements)
✅ No open questions blocking implementation (all clarifications obtained from Product Owner / SMEs)
✅ UI/UX mockups available (if applicable for frontend stories)
✅ API contracts available (if applicable for integration stories)

Enforcement: Product Owner and Scrum Master review DoR during Sprint Planning. Stories not meeting DoR are not pulled into sprint; team works on refining them during backlog grooming.

### 10.2 Definition of Done (DoD)

A user story is "Done" when it meets the following criteria:

✅ Code complete and committed to version control (Git)
✅ Peer code review completed and approved (minimum 1 reviewer, preferably 2 for critical code)
✅ Unit tests written with ≥85% code coverage for new/modified code
✅ Integration tests passed (API tests, database tests, end-to-end tests as applicable)
✅ Code merged to main branch (or release branch) with no merge conflicts
✅ Static code analysis passed (SonarQube or equivalent: no critical/high issues)
✅ Technical documentation updated (README, API docs, architecture diagrams, deployment notes)
✅ Acceptance criteria validated by QA team (manual testing if needed)
✅ No P1/P2 defects open related to this story
✅ Deployed to QA environment and validated in integrated environment
✅ Demo-ready (can be demonstrated in Sprint Review to Product Owner)
✅ Product Owner acceptance obtained (formal sign-off or approval in Sprint Review)

Enforcement: Definition of Done is reviewed in Sprint Review. Stories not meeting DoD are not accepted and carried over to next sprint for completion.

### 10.3 Quality Gates (Before UAT Handoff)

Before handing off deliverables to TMNAS for UAT, the following quality gates must be passed:

✅ All acceptance criteria met for stories included in UAT scope
✅ Code coverage ≥85% across all new and refactored modules
✅ No P1/P2 defects open (Critical and High severity defects resolved and verified)
✅ Technical documentation complete:

- Architecture diagrams updated

- API documentation (Swagger/OpenAPI)

- Deployment runbooks (step-by-step deployment instructions)

- Database migration scripts documented and tested

✅ Deployment runbook validated (dry-run deployment to QA environment successful)
✅ Client sign-off on sprint deliverables (Product Owner has accepted all stories in Sprint Review)
✅ Integration smoke tests passed with external systems (Salesforce, Azure API Management, etc.)
✅ Non-functional requirements validated (performance benchmarks met, security scan passed - TBD workshop)

Note: Performance baseline and security scan gates have been removed from this list as performance testing and security testing are TMNAS responsibilities.

Approval: Quality gates are reviewed by EPAM Delivery Manager, QA Lead, and Solution Architect. Gate completion is documented in quality gate checklist and shared with TMNAS before UAT handoff.

## 11. COMMUNICATION PLAN

### 11.1 Meeting Cadence

| Meeting | Frequency | Duration | Attendees | Purpose | Owner |
| --- | --- | --- | --- | --- | --- |
| Daily Standup | Daily (Mon-Fri) | 15 min | EPAM Development Team (all pods) | Sync on progress, blockers, plan for the day | Scrum Master |
| Sprint Planning | Every 2 weeks (start of sprint) | 2 hours | EPAM Team + TMNAS Product Owner | Review sprint goal, select user stories, commit to sprint backlog | EPAM DM + TMNAS PO |
| Sprint Review / Demo | Every 2 weeks (end of sprint) | 1 hour | EPAM Team + TMNAS Stakeholders (PO, CTO, SMEs) | Demo completed stories, gather feedback, obtain acceptance | EPAM DM |
| Sprint Retrospective | Every 2 weeks (end of sprint) | 1 hour | EPAM Team only | Reflect on sprint, identify improvements, action items | Scrum Master |
| Backlog Grooming | Weekly | 1 hour | EPAM BA/DM + TMNAS Product Owner | Refine upcoming user stories, clarify requirements, estimate, prioritize | EPAM BA |
| Status Report | Weekly (Fridays) | Email | EPAM DM → TMNAS Sponsors (Lana, Prashant) | Traffic light dashboard (RAG status), progress, risks, issues, next week plan | EPAM DM |
| Steering Committee | Monthly | 1 hour | EPAM Leadership (DM, Architect, Account Mgr) + TMNAS Executives (CIO, CTO) | Strategic alignment, executive-level decisions, escalations, budget/schedule review | EPAM Program Manager |
| Change Control Board | Weekly (as needed) | 30 min | EPAM (DM, BA) + TMNAS (PO, Prashant, BA) | Review Change Requests, assess impact, approve/reject, update CR log | EPAM DM + TMNAS PO |
| Risk Review | Bi-weekly | 30 min | EPAM DM + TMNAS Sponsors (Prashant) | Review RAID log, assess risk mitigation effectiveness, escalate high risks | EPAM DM |
| Architecture Review | Bi-weekly | 1 hour | EPAM (Solution Architect, Tech Lead) + TMNAS (CTO, Technical Architect) | Technical architecture decisions, design reviews, technology approvals | EPAM Solution Architect |

### 11.2 Reporting Artifacts

Weekly Status Report (Sent Fridays):

- RAG Status Dashboard: Red/Amber/Green status for scope, schedule, budget, quality, risks

- Sprint Progress: Story points completed vs. planned, velocity trend

- Milestones: Progress toward next milestone, on-track / at-risk / delayed status

- Risks & Issues: Top 3-5 risks/issues with status and mitigation actions

- Blockers: Current blockers requiring TMNAS action or escalation

- Next Week Plan: Key activities and deliverables for upcoming week

Sprint Burndown Chart:

- Updated daily during sprint

- Shows remaining story points vs. ideal burndown

- Shared in Sprint Review

Release Burnup Chart:

- Updated every sprint

- Shows cumulative story points completed vs. total scope

- Tracks progress toward milestone completion

RAID Log (Risks, Assumptions, Issues, Dependencies):

- Updated weekly by EPAM DM

- Shared in Steering Committee and Risk Review meetings

- Tracks status, owner, mitigation actions, closure dates

Change Request Log:

- Updated weekly by EPAM BA

- Tracks all CRs: submission date, type (1/2/3), impact assessment, approval status, implementation status

- Reviewed in Change Control Board meetings

Quality Metrics Dashboard:

- Updated every sprint

- Metrics: Code coverage %, defect density (defects per story point), velocity (SP per sprint), UAT pass rate, production defect rate

- Shared in Sprint Review and Steering Committee

### 11.3 Escalation Path

Level 1: Team-Level Issues (Response Time: Same Day)

- Issue: Technical blockers, requirements clarifications, minor scope questions

- Escalation: EPAM Tech Lead → TMNAS SME or PO

- Resolution: Via daily standup, Slack/email, or ad-hoc call

Level 2: Delivery Manager / Product Owner (Response Time: 2 Business Days)

- Issue: Blocked stories, delayed decisions, resource issues, minor scope changes (Type 1-2 CRs)

- Escalation: EPAM DM → TMNAS Product Owner

- Resolution: Via backlog grooming, sprint planning, or dedicated call

Level 3: Change Control Board (Response Time: 1 Week)

- Issue: Major scope changes (Type 3 CRs), architectural decisions, quality gate failures

- Escalation: EPAM DM + BA → Change Control Board (TMNAS PO + Prashant)

- Resolution: Via weekly Change Control Board meeting

Level 4: Steering Committee / Executive Sponsors (Response Time: 2 Weeks)

- Issue: Budget overruns, timeline delays, critical risks, contract amendments, trust/relationship issues

- Escalation: EPAM Program Manager + Account Manager → TMNAS CIO (Lana) + CTO (Prashant)

- Resolution: Via monthly Steering Committee or emergency escalation meeting

Escalation Trigger: If issue is not resolved within response time at current level, automatically escalate to next level.

## 12. APPROVAL & SIGN-OFF

### 12.1 Document Approval

This Project Charter serves as the foundational agreement between EPAM and TMNAS for the execution of Project Rambo (TMNAS RapidSure Platform Modernization). Approval of this document signifies:

- Agreement on project scope, objectives, budget, timeline, and deliverables

- Commitment to the roles, responsibilities, and governance structure outlined

- Acceptance of assumptions, constraints, risks, and dependencies

- Authorization to proceed with project execution

### 12.2 Approval Signatures

| Role | Name | Title | Signature | Date |
| --- | --- | --- | --- | --- |
| TMNAS Executive Sponsor | Lana | Chief Information Officer (CIO) | _________________ | ________ |
| TMNAS Project Sponsor | Prashant | Chief Technology Officer (CTO) | _________________ | ________ |
| TMNAS Product Owner | TBD (Open Question - Workshop) | Product Owner - RapidSure | _________________ | ________ |
| EPAM Delivery Manager | TBD (Open Question - Workshop) | Delivery Manager / Program Manager | _________________ | ________ |
| EPAM Solution Architect | TBD (Open Question - Workshop) | Solution Architect - RapidSure Modernization | _________________ | ________ |
| EPAM Account Manager | TBD (Open Question - Workshop) | Account Manager - TMNAS | _________________ | ________ |

### 12.3 Change Control

Any changes to this Project Charter (scope, budget, timeline, team structure, assumptions, risks) require formal approval via the Change Request process outlined in Section 10 (Quality Management) and detailed in the Change Control Plan (separate document).

Minor changes (typos, clarifications, non-material updates) can be approved by EPAM Delivery Manager and TMNAS Product Owner.

Major changes (scope expansion, budget increase, timeline extension, team size changes) require Change Control Board approval and executive sponsor sign-off (Lana, Prashant).

### 12.4 Document Revision History

| Version | Date | Author | Description of Changes | Approvers |
| --- | --- | --- | --- | --- |
| 1.0 | Jan 2025 | EPAM Team | Initial draft for internal workshop review | Internal Review |
| 2.0 | Jan 2025 | EPAM Team | Updated after internal workshop: Removed SV implementation scope, adjusted team structure (4 pods, 17 people), aligned budget to quarterly billing, incorporated Q&A feedback | Internal Review |
| 3.0 (Planned) | TBD | EPAM Team | Final version after client workshop: Incorporated TMNAS feedback, finalized scope, confirmed stakeholders, approved budget | TMNAS + EPAM Executives |