## TMNAS - PROJECT RAMBO

## PROJECT MANAGEMENT PLAN (PMP)

Version: 1.0
Date: March 12, 2026
Project Start Date: April 1, 2026
Project End Date: September 30, 2026 (6-month) or December 31, 2026 (9-month)
Project Manager: TBD (EPAM Delivery Manager)
Status: Draft - For Internal Workshop Review

### VERSION CONTROL

| Version | Date | Author | Changes | Approved By |
| --- | --- | --- | --- | --- |
| 1.0 | March 12, 2026 | EPAM Delivery Manager | Initial PMP based on EPAM FF framework | Internal Review |
| 2.0 (Planned) | March 20, 2026 | EPAM Delivery Manager | Updated after internal workshop (March 17-19) | EPAM Leadership |
| 3.0 (Planned) | April 1, 2026 | EPAM Delivery Manager | Final PMP after client workshop approval | TMNAS + EPAM Executives |

## TABLE OF CONTENTS

- Executive Summary

- Project Overview

- Project Organization & Governance

- Scope Management Approach

- Schedule Management Approach

- Cost Management Approach

- Quality Management Approach

- Resource Management Approach

- Communications Management Approach

- Risk Management Approach

- Procurement Management Approach

- Stakeholder Management Approach

- Integration Management Approach

- Project Control & Monitoring

- Project Closure

- Appendices

## 1. EXECUTIVE SUMMARY

### 1.1 Project Purpose

TMNAS - Project Rambo is a Fixed Fee platform modernization engagement to transform the TMNAS RapidSure insurance platform from a legacy monolithic architecture to a modern, scalable, API-driven platform. This project enables TMNAS to accelerate product launches, improve developer productivity through AI adoption, and establish EPAM as a trusted long-term platform ownership partner.

### 1.2 Project Objectives

- Support SV Product Launch - Modernize platform to enable future SV product releases

- Improve Time-to-Market - Reduce product launch cycle by 40% through modern architecture

- Establish Trusted Partnership - Transition from staff augmentation to full platform ownership

- Reduce Technical Debt - Modernize UI, APIs, and database for lower maintenance costs

- Improve Delivery Maturity - Implement Agile/Scrum with governance frameworks

- Accelerate AI Adoption - Deploy AI agents to boost developer productivity (≥70% adoption)

### 1.3 Project Scope Summary

Deliverables: 16 User Stories, 202 Story Points covering: - Business Layer API (RESTful, Spring Boot, OAuth2/JWT) - Database Optimization (performance, concurrency, caching) - UI Modernization (JSF/IceFaces → React/Angular) - CI/CD Pipeline Automation (build-to-deploy <30 min) - Governance Frameworks (strategic planning, delivery framework, change control) - AI Agent Deployment (Code Analysis, Knowledge Base, Coverage Analysis) - Technical Debt Management System

Out of Scope: SV product implementation, CCD integration, historical data migration, end-user training, production support post-warranty

### 1.4 Project Timeline & Budget

6-Month Option: - Timeline: April 1 - September 30, 2026 (10 sprints + warranty) - Budget: $675,000 (Base: $540K, Contingency: $108K, Travel: $27K) - Team: 17 FTE across 4 specialized pods

9-Month Option: - Timeline: April 1 - December 31, 2026 (18 sprints + warranty) - Budget: $1,800,000 ($600K per 4-month phase × 3 phases) - Team: 17-20 FTE (scales up in Phase 3 based on scope)

### 1.5 Critical Success Factors

- ✅ TMNAS stakeholder availability (Product Owner 50% allocation, CTO/CIO engagement)

- ✅ Timely environment access (DEV, QA by Sprint 0)

- ✅ Clear requirements and acceptance criteria (DoR enforced)

- ✅ Formal change control (prevent scope creep, protect Fixed Fee margin)

- ✅ Early delivery of critical path stories (US-008 Business API, US-010 DB Optimization)

- ✅ Effective UAT coordination (3rd party vendor managed, defect triage support)

- ✅ Proactive risk management (20% contingency, weekly risk reviews)

## 2. PROJECT OVERVIEW

### 2.1 Project Background

TMNAS (Insurance Carrier) has a 7-year relationship with EPAM but has not yet achieved “trusted partnership” status. TMNAS challenges EPAM delivery and seeks a partner who can take full platform ownership. The RapidSure platform (Personal Lines insurance policy administration) is a legacy monolithic system built on JBoss, JSF/IceFaces, and MS SQL Server, with significant technical debt that limits business agility.

Business Challenge: - SV product launch delayed multiple times due to platform limitations - High cost of change (even small changes require extensive testing and long deployment cycles) - Load and performance risks during peak renewal seasons - Immature SDLC processes lead to unpredictable delivery and trust deficit

Strategic Goal: Modernize RapidSure platform to enable rapid product launches, establish EPAM as trusted platform owner, and build foundation for long-term Managed Services relationship.

### 2.2 Project Approach

Delivery Model: Hybrid (Agile Execution + Waterfall Governance)

Agile Elements: - 2-week sprints with continuous delivery - Daily standups, sprint planning, review, retrospective - Rolling wave planning (3 sprints ahead) - Iterative development and feedback

Waterfall Elements: - Fixed payment milestones (M0, M1, M2, M3, M4) - Formal change control process (Type 1/2/3 CRs) - Quality gates at milestones - Baseline scope documentation - Formal acceptance sign-offs

Rationale for Hybrid: - Balances flexibility (Agile) with predictability (Waterfall) required for Fixed Fee - Allows TMNAS to adapt requirements while maintaining budget/schedule control - Helps mature TMNAS processes gradually (from immature/chaotic to structured/predictable)

### 2.3 Project Assumptions

Key Assumptions (from Project Charter): 1. TMNAS provides environment access (DEV, QA) and VDIs by Sprint 0 2. TMNAS Product Owner allocated 50% to project (20 hours/week) 3. Requirements are 70-80% defined; remaining 20-30% refined during sprints 4. Third-party system integration via API contracts and mocks (not direct integration) 5. TMNAS coordinates UAT with 3rd party vendor; EPAM provides defect triage support 6. No major TMNAS organizational changes during project execution 7. EPAM team has stable staffing (10% attrition buffer included)

See Project Charter Section 6 for complete list of 24 assumptions.

### 2.4 Project Constraints

Key Constraints (from Project Charter): 1. Fixed Budget: $675K (6-month) or $1.8M (9-month) 2. Fixed Timeline: April-September 2026 (6-month) or April-December 2026 (9-month) 3. Fixed Team Size: 17 FTE across 4 pods 4. Technology Stack: Must work within TMNAS constraints (JBoss, MS SQL, Azure API Mgmt) unless approved 5. SV Product Release Alignment: Must align with 6-week release cadence 6. TMNAS Stakeholder Availability: Limited Product Owner time (50% allocation)

See Project Charter Section 7 for complete list of 16 constraints.

### 2.5 Project Risks

Top 5 Risks: 1. Unclear/Evolving Requirements (HIGH/HIGH) - Mitigate: Rolling wave planning, formal CR process, 20% contingency 2. TMNAS Stakeholder Availability (HIGH/MEDIUM) - Mitigate: Dedicated PO, escalation protocol, asynchronous decisions 3. 3rd Party UAT Delays (HIGH/MEDIUM) - Mitigate: Early UAT planning, EPAM drives triage, 2-week buffer 4. Legacy Platform Complexity (MEDIUM/HIGH) - Mitigate: Experienced architects, POCs, technical spikes 5. Scope Creep (HIGH/HIGH) - Mitigate: Formal CR process, baseline protection, weekly CR Board

See Project Charter Section 8 for complete Top 10 risks with mitigation strategies.

## 3. PROJECT ORGANIZATION & GOVERNANCE

### 3.1 Project Organization Structure

Three-Tier Governance:

Tier 1: Operational (Weekly) - Team: EPAM Development Team (17 FTE across 4 pods) - Leadership: EPAM Delivery Manager, Technical Lead, Scrum Master - Meetings: Daily standups, sprint planning, sprint review, retrospective, backlog grooming - Authority: Execute approved sprint backlog, technical decisions within approved architecture

Tier 2: Tactical (Weekly/Monthly) - Forum: Change Control Board (CR Board) - Members: EPAM DM + BA + TMNAS PO + CTO/Prashant - Meetings: Weekly CR Board (30 min), Monthly Milestone Reviews - Authority: Approve/reject Type 2 CRs (<5% impact), recommend Type 3 CRs to Tier 3

Tier 3: Strategic (Monthly) - Forum: Steering Committee - Members: TMNAS CIO/CTO + EPAM Account Manager + Program Manager + Delivery Manager - Meetings: Monthly Steering Committee (1 hour) - Authority: Approve Type 3 CRs (>5% impact), resolve escalations, strategic direction

### 3.2 Roles & Responsibilities

#### TMNAS Stakeholders

| Role | Name | Responsibilities |
| --- | --- | --- |
| Executive Sponsor (CIO) | Lana | - Overall project sponsorship and strategic alignment- Approve Type 3 Change Requests (major budget/scope changes)- Executive escalation point- Review project progress in monthly Steering Committee |
| Project Sponsor (CTO) | Prashant | - Technical direction and architecture approvals- Participate in Change Control Board (vote on CRs)- Recommend Type 3 CRs to CIO- Review technical risks and mitigation strategies |
| Product Owner | TBD | - Define and prioritize product backlog- Accept or reject user stories in Sprint Review- Participate in Change Control Board (vote on CRs)- Clarify requirements during backlog grooming (50% time allocation)- Represent business stakeholders |
| Business Analyst | TBD | - Provide business context and requirements clarification- Review user stories and acceptance criteria- Participate in Change Control Board (optional) |
| Technical Lead | TBD | - Provide TMNAS architecture context and standards- Review technical designs and code (as needed)- Coordinate with TMNAS technical teams |
| UAT Lead | TBD | - Coordinate UAT with 3rd party testing vendor- Define UAT entry/exit criteria- Manage UAT defect triage with EPAM |

#### EPAM Team

| Role | Name | Team | Responsibilities |
| --- | --- | --- | --- |
| Delivery Manager / Program Manager | TBD | Leadership | - Overall project accountability (scope, schedule, budget, quality)- Stakeholder management (TMNAS + EPAM)- Change control (conduct impact assessments, chair CR Board)- Risk management (RAID log owner)- Weekly status reporting to TMNAS Sponsors- Escalation point for EPAM team |
| Solution Architect | TBD | Leadership | - Technical architecture design and decisions- Ensure consistency across pods- Architecture review and approval (with EPAM Chief Architect)- Assess technical impact of Change Requests- Identify and mitigate technical risks |
| Technical Lead / Team Lead | TBD | Leadership | - Development leadership and code quality standards- Technical mentorship for developers- Code review and technical guidance- Sprint planning and estimation facilitation |
| Business Analyst | TBD | Pod 4 | - Maintain product backlog (user stories, acceptance criteria)- Facilitate backlog grooming with TMNAS PO- Document Change Requests and track CR log- Ensure user stories meet Definition of Ready- Requirements analysis and validation |
| QA Lead | TBD | Pod 5 | - Define and implement test strategy- QA automation framework and shift-left practices- Quality gate validation before UAT- Defect management and severity classification- Support UAT defect triage |
| DevOps Lead | TBD | Pod 5 | - CI/CD pipeline design and implementation- Infrastructure-as-Code (environment automation)- Build and deployment automation- Monitoring and logging setup (recommendations) |
| Scrum Master | TBD (or DM) | Leadership | - Facilitate Agile ceremonies (standups, planning, review, retro)- Remove impediments for development team- Enforce DoR and DoD- Track sprint velocity and burndown |
| Backend Developers | TBD (6 people) | Pod 1 | - Develop Business Layer API (US-008), Product Config API (US-009)- Database optimization (US-010)- Technical debt fixes (US-007) |
| Database Administrator | TBD (1 person) | Pod 1 | - Database performance analysis and optimization- Schema design and indexing- Redis caching optimization |
| Frontend Developers | TBD (3 people) | Pod 3 | - UI modernization (JSF → React/Angular) (US-011)- Responsive design and component library |
| AI/ML Engineers | TBD (2 people) | Pod 4 | - Deploy AI agents (CodeMie: US-012, US-013, US-014)- Train team on AI tools- Measure AI adoption and productivity gains |
| DevOps Engineers | TBD (2 people) | Pod 5 | - CI/CD pipeline implementation (US-017)- Environment automation (US-018)- QA shift-left support (US-006) |

#### Support Roles (Part-Time / As-Needed)

| Role | Organization | Involvement |
| --- | --- | --- |
| EPAM Chief Architect | EPAM | Architecture review and approval (Sprint 1, Day 2 PM of internal workshop) |
| EPAM Account Manager | EPAM | Client relationship, commercial management, contract oversight, Type 3 CR approvals |
| EPAM Commercial Team | EPAM | Rate card, budget, contract amendments |
| EPAM Legal | EPAM | Contract review, amendments, warranty terms |
| AI/Run SME | EPAM | AI agent licensing, deployment support, training |
| TMNAS Finance / Procurement | TMNAS | Budget approval, payment processing, contract execution |
| TMNAS Infrastructure Team | TMNAS | Environment provisioning, VDI setup, network access |
| TMNAS UAT Vendor | 3rd Party | UAT test execution, defect reporting |

### 3.3 Decision-Making Authority Matrix (RACI)

| Decision / Activity | TMNAS CIO | TMNAS CTO | TMNAS PO | EPAM DM | EPAM Architect | EPAM Account Mgr |
| --- | --- | --- | --- | --- | --- | --- |
| Approve Project Charter | A | C | C | R | C | A |
| Approve Budget | A | C | I | I | I | R |
| Define Product Backlog | I | C | A/R | C | I | I |
| Prioritize User Stories | I | C | A | C | I | I |
| Accept Sprint Deliverables | I | I | A | R | I | I |
| Approve Type 1 CRs (Clarification) | I | I | I | A | I | I |
| Approve Type 2 CRs (<5% impact) | I | R | R | A/R | C | I |
| Approve Type 3 CRs (>5% impact) | A | A | I | R | C | R |
| Approve Architecture | I | A | I | C | R | I |
| Approve Technical Design | I | C | I | C | A/R | I |
| Approve Go-Live | A | A | C | R | C | I |
| Resolve Escalations | A | A | I | R | C | R |

Legend: - R = Responsible (does the work) - A = Accountable (final authority, single point) - C = Consulted (provides input) - I = Informed (kept in the loop)

### 3.4 Communication & Escalation Path

Escalation Levels:

Level 1: Team-Level (Same Day Response) - Issue: Technical blockers, requirements clarifications, minor scope questions - Escalation: EPAM Tech Lead → TMNAS SME or PO - Resolution: Daily standup, Slack/Teams, ad-hoc call

Level 2: Delivery Manager / Product Owner (2 Business Days) - Issue: Blocked stories, delayed decisions, resource issues, Type 1-2 CRs - Escalation: EPAM DM → TMNAS PO - Resolution: Backlog grooming, sprint planning, dedicated meeting

Level 3: Change Control Board (1 Week) - Issue: Type 2-3 CRs, architectural decisions, quality gate failures - Escalation: EPAM DM + BA → CR Board (TMNAS PO + Prashant) - Resolution: Weekly CR Board meeting

Level 4: Steering Committee / Executive Sponsors (2 Weeks) - Issue: Budget overruns, timeline delays, critical risks, contract amendments, trust/relationship issues - Escalation: EPAM Program Manager + Account Manager → TMNAS CIO + CTO - Resolution: Monthly Steering Committee or emergency escalation meeting

Escalation Trigger: If issue is not resolved within response time at current level, automatically escalate to next level.

## 4. SCOPE MANAGEMENT APPROACH

### 4.1 Scope Definition

Scope is defined through: 1. Project Charter - High-level scope statement, objectives, deliverables 2. Product Backlog - Detailed user stories (16 stories, 202 SP) with acceptance criteria 3. Scope Management Plan - In-scope vs. out-of-scope boundaries, deliverables checklist 4. Work Breakdown Structure (WBS) - Hierarchical decomposition (Project → Epics → User Stories → Tasks)

Scope Baseline: 16 user stories, 202 story points (see Section 2.3 of Project Baseline Document)

### 4.2 Scope Validation

Validation Checkpoints: - Sprint Review (Bi-Weekly): Product Owner accepts/rejects completed user stories based on Definition of Done - Milestone Review (M1, M2, M3, M4): Executive Sponsors accept milestone deliverables based on acceptance criteria - Quality Gate Review (Before UAT): QA Lead + Delivery Manager validate quality gates passed - UAT Exit Review: TMNAS UAT Lead + CTO approve go-live based on UAT exit criteria

### 4.3 Scope Control

All scope changes managed through formal Change Request (CR) process: - Type 1 (Clarification, No Impact): EPAM DM approval only - Type 2 (Minor, <5% Impact): CR Board approval, absorbed in 20% contingency - Type 3 (Major, >5% Impact): Executive Sponsor approval + contract amendment

See Project Change Control Plan for detailed CR process.

## 5. SCHEDULE MANAGEMENT APPROACH

### 5.1 Schedule Development

Schedule Development Process: 1. Decompose Scope: Break 16 user stories into tasks during sprint planning 2. Estimate Effort: Story points (already estimated: 202 SP total), hours per task 3. Sequence Activities: Identify dependencies (US-008 → US-011, US-010 parallel with US-008) 4. Assign Resources: Allocate 4 pods (17 FTE) to stories based on skills 5. Develop Schedule: Create sprint schedule, Gantt chart, milestone dates 6. Validate Schedule: Ensure critical path fits within 6 or 9 months

Schedule Baseline: 10 sprints for 6-month (April 1 - August 25, 2026), 18 sprints for 9-month (April 1 - December 31, 2026)

### 5.2 Schedule Control

Schedule is monitored and controlled through: - Sprint Burndown Chart: Daily tracking of remaining story points in sprint - Release Burnup Chart: Cumulative tracking of story points completed vs. 202 SP total - Velocity Tracking: Actual SP per sprint vs. planned (20-22 SP) - Critical Path Monitoring: Weekly review of US-008, US-010, US-011 progress - Milestone Variance Analysis: Actual milestone dates vs. baseline (acceptable: ±1 week)

Schedule Change Control: - Minor delays (<1 week): Addressed within sprint (adjust sprint backlog, team capacity) - Milestone delays (>1 week): Escalate to CR Board, may require Type 2 or Type 3 CR depending on impact

### 5.3 Schedule Assumptions

- 2-week sprint length (10 working days)

- 65% focus factor (35% overhead for meetings, ceremonies, admin)

- 17 FTE team capacity (may ramp up/down per plan)

- No major holidays or blackout periods during project (validate in client workshop)

- TMNAS provides timely decisions (2 business day response time)

## 6. COST MANAGEMENT APPROACH

### 6.1 Budget Development

Budget Baseline: - 6-Month: $675,000 (Development: $540K, Contingency: $108K, Travel: $27K) - 9-Month: $1,800,000 ($600K per 4-month phase × 3 phases)

Cost Assumptions: - Blended rate: ~$60/hour (CEE2, Ukraine, GUKKA locations) - No infrastructure costs (TMNAS-provided) - No license costs (TMNAS-provided VDIs) - 20% contingency for high-risk factors (requirements uncertainty, legacy complexity, integration challenges)

### 6.2 Cost Control

Cost is monitored and controlled through: - Earned Value Management (EVM): Monthly tracking of PV, EV, AC, CPI, SPI - Contingency Tracking: Weekly tracking of 20% contingency usage ($108K for 6-month) - Budget Variance Analysis: Actual cost vs. baseline (acceptable: ±5% or $33.75K for 6-month) - Forecast at Completion (FAC): Projected total cost based on CPI (if CPI < 0.95, forecast cost overrun)

Cost Change Control: - Type 2 CRs (<5% impact): Absorbed in 20% contingency - Type 3 CRs (>5% impact): Require additional budget (contract amendment) - Contingency Exhaustion: When 100% used, all further changes are Type 3

Escalation Thresholds: - Contingency >80% used: Escalate to Steering Committee - CPI < 0.95 for 2 sprints: Trigger corrective action plan, escalate to Executive Sponsors

## 7. QUALITY MANAGEMENT APPROACH

### 7.1 Quality Standards

Quality is defined by: 1. Definition of Ready (DoR): User story readiness criteria before entering sprint (see DoD/DoR slides) 2. Definition of Done (DoD): User story completion criteria before marking “Done” (see DoD/DoR slides) 3. Code Coverage: ≥85% unit test coverage for new/modified code 4. Code Quality: SonarQube scan passes (no critical/high issues) 5. Defect Density: <1% defects per story point 6. UAT Pass Rate: ≥95% UAT test cases passed 7. Performance Targets: TBD in client workshop (response time, throughput, concurrency)

### 7.2 Quality Assurance Activities

Quality is assured through: - Unit Testing: Developers write unit tests (≥85% coverage), run in CI/CD pipeline - Integration Testing: QA team conducts API tests, database tests, end-to-end tests - Code Review: Peer code review (minimum 1 reviewer, preferably 2 for critical code) - Static Code Analysis: SonarQube scans on every commit, fail build if critical/high issues - QA Shift-Left (US-006): Automated tests integrated in CI/CD, run on every build - UAT (TMNAS + 3rd Party Vendor): Formal acceptance testing with UAT entry/exit criteria - Performance Testing (TMNAS): Load/stress testing before go-live - Security Testing (TMNAS): Security scans, penetration testing (EPAM follows secure coding practices)

### 7.3 Quality Control

Quality Gates (Before UAT Handoff): - ✅ All acceptance criteria met for stories in UAT scope - ✅ Code coverage ≥85% - ✅ No P1/P2 defects open - ✅ Technical documentation complete (API docs, architecture diagrams, deployment runbooks) - ✅ Deployment runbook validated (dry-run in QA successful) - ✅ Client sign-off on sprint deliverables (Product Owner acceptance in Sprint Review)

Quality Metrics Tracked: - Code coverage % (target: ≥85%) - Defect density (defects per SP, target: <1%) - UAT pass rate (target: ≥95%) - Production defects (P1/P2, target: 0 for 30 days post go-live)

## 8. RESOURCE MANAGEMENT APPROACH

### 8.1 Resource Planning

Team Structure: 4 Pods, 17 FTE

| Pod | Focus | Team Size | Roles |
| --- | --- | --- | --- |
| Pod 1: Platform Modernization | Business API, DB, Tech Debt | 6 people | 1 Architect, 3 Backend Devs, 1 DBA, 1 QA |
| Pod 3: UI & Frontend | UI Modernization | 4 people | 1 Frontend Architect, 2 Frontend Devs, 1 QA |
| Pod 4: Process & AI | Governance, Requirements, AI | 4 people | 1 PM, 1 BA, 2 AI/ML Engineers |
| Pod 5: Infrastructure | CI/CD, QA, Environments | 3 people | 1 DevOps Lead, 2 DevOps Engineers |

Team Ramp-Up/Ramp-Down Plan: - Sprint 0 (Week 1): 12 people (ramp-up, onboarding) - Sprints 1-9: 17 people (full capacity) - Sprint 10+: 15 people (ramp-down, warranty support)

Key Personnel (Retention Required): - Delivery Manager / Program Manager - Solution Architect - Technical Lead

Attrition Management: - Expected attrition: 10% (industry standard) - Mitigation: Knowledge sharing, pair programming, documentation, backup resources, 30-day KT protocol

### 8.2 Resource Acquisition

Resource Acquisition Process: 1. EPAM Resource Manager identifies candidates from CEE2, Ukraine, GUKKA 2. Interviews & Selection: Delivery Manager + Solution Architect interview candidates 3. Onboarding: Sprint 0 (April 1-7, 2026) - VDI setup, tool access, project training 4. Ramp-Up: Sprint 1 (April 8-21) - Team productivity ramps to full capacity

Resource Requirements: - All team members must have VDI access (TMNAS-provided) by Sprint 0 - All team members must pass TMNAS background checks (if required) - Key skills: Java, Spring Boot, React/Angular, MS SQL Server, Azure, CI/CD, Agile/Scrum

### 8.3 Team Development

Team development activities: - Sprint 0 Training: Change Control Plan, DoR/DoD, Agile ceremonies, tools (Jira, Git, CI/CD) - Technical Training: Architecture deep dive (RapidSure platform), technology stack, coding standards - AI Adoption Training (US-012-014): CodeMie agent workshops, hands-on labs - Continuous Learning: Lunch-and-learn sessions, knowledge sharing, retrospectives

Team Building: - Sprint retrospectives (team reflection, continuous improvement) - Virtual team events (for distributed team across CEE2, Ukraine, GUKKA) - Recognition and rewards (sprint awards, kudos)

## 9. COMMUNICATIONS MANAGEMENT APPROACH

### 9.1 Communication Requirements

Stakeholder Communication Needs:

| Stakeholder | Information Needs | Frequency | Method |
| --- | --- | --- | --- |
| TMNAS Executive Sponsors (CIO/CTO) | High-level progress, risks, budget, strategic decisions | Monthly | Steering Committee meeting, executive summary |
| TMNAS Product Owner | Sprint progress, backlog, acceptance, CRs | Bi-weekly + weekly | Sprint review, backlog grooming, CR Board |
| TMNAS Technical Team | Technical design, integration, architecture | As needed | Architecture reviews, technical discussions |
| EPAM Team | Sprint tasks, blockers, technical guidance | Daily | Daily standup, Slack/Teams, code reviews |
| EPAM Leadership | Project health, commercial risks, escalations | Weekly | Status report, escalations as needed |

### 9.2 Communication Plan

Meetings:

| Meeting | Frequency | Duration | Attendees | Purpose | Owner |
| --- | --- | --- | --- | --- | --- |
| Daily Standup | Daily (Mon-Fri) | 15 min | EPAM Dev Team | Sync on progress, blockers, plan | Scrum Master |
| Sprint Planning | Bi-weekly (start of sprint) | 2 hours | EPAM Team + TMNAS PO | Review sprint goal, select stories, commit | EPAM DM + TMNAS PO |
| Sprint Review / Demo | Bi-weekly (end of sprint) | 1 hour | EPAM Team + TMNAS Stakeholders | Demo completed stories, gather feedback | EPAM DM |
| Sprint Retrospective | Bi-weekly (end of sprint) | 1 hour | EPAM Team only | Reflect on sprint, identify improvements | Scrum Master |
| Backlog Grooming | Weekly | 1 hour | EPAM BA/DM + TMNAS PO | Refine upcoming stories, clarify requirements | EPAM BA |
| Status Report | Weekly (Fridays) | Email | EPAM DM → TMNAS Sponsors | Progress, risks, issues, next week plan | EPAM DM |
| Steering Committee | Monthly | 1 hour | EPAM Leadership + TMNAS Executives | Strategic alignment, escalations, budget/schedule | EPAM Program Manager |
| Change Control Board | Weekly (as needed) | 30 min | EPAM (DM, BA) + TMNAS (PO, CTO) | Review CRs, approve/reject | EPAM DM |
| Risk Review | Bi-weekly | 30 min | EPAM DM + TMNAS Prashant | Review RAID log, assess mitigation | EPAM DM |
| Architecture Review | Bi-weekly | 1 hour | EPAM (Architect, Tech Lead) + TMNAS CTO | Technical decisions, design reviews | EPAM Architect |

Reporting:

| Report | Frequency | Audience | Content | Owner |
| --- | --- | --- | --- | --- |
| Weekly Status Report | Weekly (Friday) | TMNAS Sponsors + EPAM Leadership | RAG status, progress, risks, issues, blockers, CRs | EPAM DM |
| Sprint Burndown Chart | Daily | EPAM Team + TMNAS PO | Remaining SP in sprint vs. ideal | Scrum Master |
| Release Burnup Chart | Bi-weekly | TMNAS PO + EPAM DM | Cumulative SP completed vs. 202 SP | EPAM BA |
| RAID Log | Bi-weekly | TMNAS CTO + EPAM DM | Risks, Assumptions, Issues, Dependencies | EPAM DM |
| Change Request Log | Weekly | CR Board | All CRs: status, impact, approval | EPAM BA |
| Quality Metrics Dashboard | Bi-weekly | EPAM Team + TMNAS PO | Code coverage, defects, velocity, UAT pass rate | EPAM QA Lead |
| Monthly Steering Committee Report | Monthly | TMNAS Executives + EPAM Leadership | EVM, milestones, CR trends, risks, forecast | EPAM Program Manager |

### 9.3 Communication Tools

Tools (TBD - Client Workshop): - Project Management: Jira, Azure DevOps, or similar (TMNAS standard) - Communication: Slack, Microsoft Teams, or similar - Documentation: Confluence, SharePoint, or similar - Version Control: Git (GitHub, GitLab, Bitbucket, Azure Repos) - CI/CD: Jenkins, GitLab CI, Azure Pipelines - Video Conferencing: Zoom, Microsoft Teams, Google Meet

All communication tools and access provisioned by Sprint 0.

## 10. RISK MANAGEMENT APPROACH

### 10.1 Risk Management Process

5-Step Risk Management Process:

1. Risk Identification - When: Project kickoff, sprint planning, retrospectives, monthly steering committee - How: Brainstorming, lessons learned from past projects, risk checklists (EPAM FF framework) - Output: RAID log with identified risks

2. Risk Assessment - Impact: HIGH (project failure), MEDIUM (milestone delay), LOW (minor disruption) - Probability: HIGH (>50% chance), MEDIUM (25-50%), LOW (<25%) - Priority: Risk Score = Impact × Probability (High/High = Top Priority) - Output: Prioritized risk list

3. Risk Mitigation Planning - For each HIGH/HIGH or HIGH/MEDIUM risk: - Mitigation Strategy: Actions to reduce probability or impact - Owner: Who is responsible for executing mitigation - Timeline: When mitigation actions will be completed - Contingency Plan: What to do if risk occurs despite mitigation - Output: Risk mitigation plan

4. Risk Monitoring - Frequency: Bi-weekly risk review meetings, monthly steering committee - Metrics: Risk score trends, # of new risks, # of mitigated risks, # of realized risks - Output: Updated RAID log

5. Risk Response - If risk occurs: Execute contingency plan, escalate if needed, update RAID log - If risk is mitigated: Close risk, document lessons learned

### 10.2 Top Project Risks

See Project Charter Section 8 for Top 10 risks with detailed mitigation strategies.

Risk Escalation Thresholds: - Any HIGH/HIGH risk: Escalate to Steering Committee immediately - Risk score increases: Escalate to Steering Committee if mitigation is insufficient - Risk realized: Escalate to appropriate level (Level 2, 3, or 4 based on impact)

### 10.3 Risk Register (RAID Log)

RAID Log Structure:

| Risk ID | Risk Description | Category | Impact | Probability | Score | Owner | Mitigation Strategy | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-001 | Unclear/evolving requirements | Requirements | HIGH | HIGH | H/H | EPAM DM + TMNAS PO | Rolling wave planning, formal CR process, 20% contingency | Open |
| R-002 | TMNAS stakeholder availability | Organizational | HIGH | MEDIUM | H/M | EPAM DM | Dedicated PO, escalation protocol, asynchronous decisions | Open |
| … | … | … | … | … | … | … | … | … |

RAID Log maintained in shared tool (Jira, Excel, or similar), reviewed bi-weekly.

## 11. PROCUREMENT MANAGEMENT APPROACH

### 11.1 Procurement Overview

For this project, procurement is MINIMAL: - No infrastructure procurement: TMNAS provides all infrastructure (VDIs, environments, cloud hosting) - No license procurement: TMNAS provides all licenses (development tools via VDIs) - No third-party services procurement by EPAM: TMNAS manages UAT vendor, performance testing vendor

EPAM Procurements (if any): - AI Agent Licensing (CodeMie): EPAM AI/Run team provides (internal EPAM service, no external procurement) - Travel & Expenses: Business trips for key personnel (booked by EPAM, reimbursed by TMNAS per contract)

### 11.2 Vendor Management (TMNAS Responsibility)

TMNAS manages relationships with: - UAT Testing Vendor - Executes UAT, reports defects - Performance Testing Vendor - Executes load/stress testing - Security Testing Vendor - Executes security scans, penetration testing

EPAM Role: - UAT: Provide defect triage support, fix confirmed defects, attend UAT status meetings - Performance Testing: Provide ad-hoc support for troubleshooting, performance tuning - Security Testing: Follow secure coding practices (OWASP), fix security vulnerabilities found

Vendor Coordination: TMNAS UAT Lead coordinates vendors; EPAM DM escalates if vendor delays impact project.

## 12. STAKEHOLDER MANAGEMENT APPROACH

### 12.1 Stakeholder Identification

Key Stakeholders:

| Stakeholder | Organization | Role | Interest/Influence | Engagement Strategy |
| --- | --- | --- | --- | --- |
| Lana (CIO) | TMNAS | Executive Sponsor | HIGH Interest, HIGH Influence | Monthly Steering Committee, executive summaries, early escalation of critical issues |
| Prashant (CTO) | TMNAS | Project Sponsor | HIGH Interest, HIGH Influence | Weekly CR Board, monthly Steering Committee, bi-weekly risk review, architecture reviews |
| Product Owner | TMNAS | Product Owner | HIGH Interest, MEDIUM Influence | Sprint planning, backlog grooming, sprint review, CR Board (50% time allocation) |
| TMNAS Dev Team | TMNAS | Technical Stakeholders | MEDIUM Interest, LOW Influence | Architecture reviews, technical discussions, knowledge transfer |
| EPAM Team | EPAM | Delivery Team | HIGH Interest, LOW Influence | Daily standups, sprint ceremonies, clear communication of expectations |
| EPAM Account Manager | EPAM | Commercial Owner | MEDIUM Interest, HIGH Influence | Monthly Steering Committee, Type 3 CR approvals, contract amendments |
| EPAM Leadership | EPAM | Executive Sponsors | MEDIUM Interest, HIGH Influence | Escalations, critical decisions, resource allocation |

### 12.2 Stakeholder Engagement

Engagement Strategies:

For High Interest / High Influence (Lana, Prashant): - Strategy: Manage Closely - Actions: Regular communication, early involvement in decisions, proactive escalation of issues

For High Interest / Medium Influence (Product Owner): - Strategy: Keep Informed - Actions: Frequent touchpoints, involve in sprint ceremonies, ensure 50% time allocation

For Medium Interest / Low Influence (TMNAS Dev Team): - Strategy: Monitor - Actions: Periodic updates, involve when needed (architecture reviews, knowledge transfer)

For High Interest / Low Influence (EPAM Team): - Strategy: Keep Informed - Actions: Transparent communication, clear expectations, regular feedback

### 12.3 Stakeholder Communication Matrix

See Section 9.1 for detailed stakeholder communication requirements and plan.

## 13. INTEGRATION MANAGEMENT APPROACH

### 13.1 Integration Management

Integration Management ensures all project management processes work together harmoniously.

Key Integration Points:

1. Scope-Schedule-Cost Integration: - Changes to scope (via CRs) impact schedule and cost - Integrated Change Control: All CRs assessed for scope, schedule, and cost impact before approval

2. Quality-Schedule Integration: - Quality gates must pass before milestone acceptance (may delay schedule if not met) - Sprint Review: Product Owner acceptance required before moving to next sprint

3. Risk-All Knowledge Areas Integration: - Risks can impact scope, schedule, cost, quality, resources - Bi-weekly risk review considers impact on all knowledge areas

4. Communication-Stakeholder Integration: - Communication plan tailored to stakeholder needs (Section 9) - Stakeholder engagement ensures communication is effective

5. Resource-Schedule Integration: - Resource availability impacts sprint velocity and schedule - Team ramp-up/ramp-down plan synchronized with sprint schedule

### 13.2 Integrated Change Control

All changes (scope, schedule, cost, quality, resources) managed through: - Change Request Process: Type 1/2/3 CRs with integrated impact assessment (See Change Control Plan) - Change Control Board: Reviews CRs holistically (scope + schedule + cost + risk) - Baseline Management: All approved changes update baselines (scope, schedule, cost)

## 14. PROJECT CONTROL & MONITORING

### 14.1 Performance Measurement

Project performance measured using:

1. Earned Value Management (EVM): - Planned Value (PV): Baseline budget for scheduled work - Earned Value (EV): Budget for completed work - Actual Cost (AC): Actual cost incurred - Cost Performance Index (CPI): EV / AC (target: ≥1.0) - Schedule Performance Index (SPI): EV / PV (target: ≥1.0)

2. Key Performance Indicators (KPIs): - Scope: SP completed vs. 202 SP baseline, velocity (target: 20-22 SP/sprint) - Schedule: Milestone on-time delivery (target: 100%), SPI (target: ≥1.0) - Cost: Budget utilization (target: ≤100%), CPI (target: ≥1.0), contingency usage (target: ≤100%) - Quality: Code coverage (target: ≥85%), defect density (target: <1%), UAT pass rate (target: ≥95%) - AI Adoption: Team adoption rate (target: ≥70%), code review time reduction (target: ≥30%) - Stakeholder Satisfaction: Client satisfaction score (target: ≥4.5/5.0), escalations (target: 0)

See Project Baseline Document Section 5 for complete KPI list and thresholds.

### 14.2 Monitoring & Control Processes

Weekly Monitoring: - Sprint Progress: Daily standup, sprint burndown chart - Blockers & Issues: RAID log updated, escalations as needed - Change Requests: CR log reviewed, CR Board meetings - Status Report: Weekly status report to TMNAS Sponsors

Bi-Weekly Monitoring: - Sprint Review: Product Owner acceptance, demo to stakeholders - Sprint Retrospective: Team reflection, continuous improvement - Risk Review: RAID log review, mitigation progress - Quality Metrics: Code coverage, defects, velocity trends

Monthly Monitoring: - Steering Committee: Executive-level review (EVM, milestones, CR trends, risks, forecast) - Milestone Review: Formal acceptance of M1, M2, M3, M4 deliverables

Corrective Actions: - If CPI < 0.95 or SPI < 0.95: Trigger corrective action plan (adjust team capacity, descope lower-priority stories, escalate) - If milestone at risk: Escalate to Steering Committee, consider schedule recovery plan - If scope creep detected: Enforce CR process, educate stakeholders on baseline protection

## 15. PROJECT CLOSURE

### 15.1 Project Closure Activities

Project closure includes:

1. Deliverable Acceptance: - M4 (Warranty Complete): Final acceptance by TMNAS CIO/CTO - All user stories accepted by Product Owner in Sprint Reviews - All quality gates passed - All milestone acceptance criteria met

2. Financial Closure: - Final invoice submitted (M4 payment: 10% or $67.5K for 6-month) - All payments received from TMNAS - Budget reconciliation (actual cost vs. baseline)

3. Administrative Closure: - Final project report (summary of accomplishments, lessons learned, KPIs achieved) - Archive project documents (Project Charter, baselines, RAID log, CR log, status reports) - Close contracts (if separate contracts for subcontractors or vendors)

4. Knowledge Transfer: - Technical documentation delivered to TMNAS (architecture, API docs, deployment runbooks) - Knowledge transfer sessions with TMNAS team (code walkthrough, operational training) - Support documentation (FAQ, troubleshooting guides)

5. Lessons Learned: - Lessons learned workshop with EPAM team and TMNAS stakeholders - Document successes (what went well, best practices) - Document challenges (what went wrong, root causes, how to prevent in future) - Share lessons with EPAM knowledge base (for future projects)

6. Team Transition: - EPAM team ramp-down (Sprint 10+, warranty period) - Celebrate success (team recognition, awards) - Transition to MSP team (if applicable for 9-month Phase 3 or post-project)

### 15.2 Project Success Criteria

Project is considered successful if:

✅ All deliverables accepted by TMNAS (16 user stories, 202 SP delivered and accepted)
✅ On-time delivery (within ±1 week of baseline end date: Sep 30 or Dec 31, 2026)
✅ On-budget delivery (within ±5% of baseline budget: $675K or $1.8M)
✅ Quality targets met (code coverage ≥85%, UAT pass rate ≥95%, zero P1/P2 defects for 30 days)
✅ AI adoption targets met (≥70% team adoption, ≥30% code review time reduction)
✅ Client satisfaction ≥4.5/5.0 (measured via monthly surveys)
✅ Zero critical escalations to executive level (or escalations resolved satisfactorily)
✅ Partnership trust established (TMNAS approves Phase 2 / MSP engagement)

### 15.3 Warranty Period

60-Day Warranty (Post Go-Live): - Scope: P1/P2 defects (Critical and High severity) only - Exclusions: New features, enhancements, environment issues, changes by TMNAS team - SLA: P1 (4-hour response, 24-hour resolution), P2 (24-hour response, 72-hour resolution) - Team: 3-5 EPAM team members on-demand (not full team) - Payment: Final 10% payment ($67.5K for 6-month) upon warranty completion

Warranty Success Criteria: - Zero P1/P2 defects for 30 consecutive days - Performance SLAs met for 30 consecutive days - Knowledge transfer complete - TMNAS accepts warranty closure

## 16. APPENDICES

### Appendix A: Project Document References

This Project Management Plan references the following documents:

- Project Charter v2.0 - Foundational project document (objectives, scope, budget, risks, assumptions)

- Scope Management Plan v1.0 - Detailed scope definition and control process

- Project Change Control Plan v1.0 - Change Request process (Type 1/2/3 CRs)

- Project Baseline Document v1.0 - Scope, schedule, cost baselines

- Product Backlog v2.0 - 16 user stories with detailed acceptance criteria, 202 SP

- Internal Workshop Agenda - 3-day workshop plan (March 17-19, 2026)

- Open Questions List v3.0 - 60 open questions for workshops

- DoD and DoR Slides - Definition of Done and Definition of Ready

- TMNAS RapidSure Architecture Diagrams - Current state architecture

- EPAM FF Delivery Framework - Fixed Fee delivery best practices

All documents stored in shared repository (Confluence, SharePoint, or similar) with version control.

### Appendix B: Project Acronyms & Glossary

| Acronym | Definition |
| --- | --- |
| AC | Actual Cost (EVM metric) |
| API | Application Programming Interface |
| BA | Business Analyst |
| CI/CD | Continuous Integration / Continuous Deployment |
| CPI | Cost Performance Index (EVM metric: EV / AC) |
| CR | Change Request |
| CV | Cost Variance (EVM metric: EV - AC) |
| DM | Delivery Manager |
| DoD | Definition of Done |
| DoR | Definition of Ready |
| EV | Earned Value (EVM metric) |
| EVM | Earned Value Management |
| FAC | Forecast at Completion |
| FF | Fixed Fee |
| FTE | Full-Time Equivalent |
| KPI | Key Performance Indicator |
| MSP | Managed Services Provider |
| NFR | Non-Functional Requirement |
| PMP | Project Management Plan (this document) |
| PO | Product Owner |
| PV | Planned Value (EVM metric) |
| RAID | Risks, Assumptions, Issues, Dependencies |
| SLA | Service Level Agreement |
| SME | Subject Matter Expert |
| SP | Story Points |
| SPI | Schedule Performance Index (EVM metric: EV / PV) |
| SV | Schedule Variance (EVM metric: EV - PV) |
| UAT | User Acceptance Testing |
| US | User Story |
| VDI | Virtual Desktop Infrastructure |
| WBS | Work Breakdown Structure |

### Appendix C: Project Management Plan Approval

This Project Management Plan (Version 3.0) is approved by:

| Role | Name | Title | Signature | Date |
| --- | --- | --- | --- | --- |
| TMNAS Executive Sponsor | Lana | Chief Information Officer (CIO) | _________________ | ________ |
| TMNAS Project Sponsor | Prashant | Chief Technology Officer (CTO) | _________________ | ________ |
| TMNAS Product Owner | TBD | Product Owner - RapidSure | _________________ | ________ |
| EPAM Delivery Manager | TBD | Delivery Manager - Project Rambo | _________________ | ________ |
| EPAM Account Manager | TBD | Account Manager - TMNAS | _________________ | ________ |

Approval Date: April 1, 2026 (Target - Project Kickoff)

This Project Management Plan serves as the authoritative guide for managing and executing TMNAS - Project Rambo. All project team members and stakeholders are expected to follow the processes, standards, and governance defined herein.