## TMNAS - PROJECT RAMBO

## SCOPE MANAGEMENT PLAN

Version: 1.0
Date: March 12, 2026
Status: Draft - For Internal Workshop Review

### VERSION CONTROL

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | March 12, 2026 | EPAM Team | Initial scope management plan |

## 1. SCOPE MANAGEMENT OVERVIEW

### 1.1 Purpose

This Scope Management Plan defines how project scope will be defined, validated, controlled, and managed throughout the TMNAS Project Rambo Fixed Fee engagement. It establishes processes to ensure:

- Clear scope boundaries (in-scope vs. out-of-scope)

- Stakeholder agreement on deliverables

- Controlled scope changes through formal Change Request process

- Prevention of scope creep

- Alignment with Fixed Fee contract constraints

### 1.2 Scope Management Process

The scope management process consists of:

- Scope Planning - Define scope baseline (this document)

- Scope Definition - Detail requirements through user stories and acceptance criteria

- Scope Validation - Obtain stakeholder acceptance of deliverables

- Scope Control - Manage changes through formal Change Request process

## 2. SCOPE BASELINE

### 2.1 Project Scope Statement

Project Rambo will deliver a modernized RapidSure platform foundation that enables:

- Rapid product launches (target: 40% reduction in time-to-market)

- Scalable architecture supporting business growth

- Modern user experience through UI modernization

- Improved developer productivity through AI adoption

- Mature delivery processes and governance frameworks

Key Deliverables:

- Business Layer API (RESTful, Spring Boot, ≥85% test coverage)

- Database optimization (performance targets TBD with client)

- UI modernization (JSF/IceFaces → React/Angular for in-scope modules)

- CI/CD pipeline automation (build-to-deploy <30 min)

- Governance frameworks (strategic planning, delivery framework, change control)

- AI agent deployment (Code Analysis, Knowledge Base, Coverage Analysis)

- Technical debt management system

- Comprehensive technical documentation

### 2.2 In-Scope Summary

Total Scope: 16 User Stories, 202 Story Points (subject to refinement in internal workshop)

#### Epic 1: Governance & SDLC (34 SP)

- US-001: Strategic Planning & Roadmap Implementation (13 SP)

- US-002: Unified Delivery Framework Rollout (13 SP)

- US-003: AI-Enhanced Estimation & Change Control (8 SP)

#### Epic 2: Requirements & Solutioning (16 SP)

- US-004: Requirements Quality Improvement Framework (8 SP)

- US-005: Centralized Knowledge Library (8 SP)

#### Epic 3: Development & QA (21 SP)

- US-006: QA Shift-Left with AI Test Generation (13 SP)

- US-007: Technical Debt Management System (8 SP)

#### Epic 4: Deployment & Infrastructure (21 SP)

- US-017: Automated CI/CD Pipeline with AI Optimization (13 SP)

- US-018: Environment Automation and Management (8 SP)

#### Epic 5: Platform Modernization (76 SP) - CRITICAL

- US-008: Business Layer API Implementation (21 SP) - CRITICAL PATH

- US-009: Product Configuration API Standardization (13 SP)

- US-010: Database Optimization for High Concurrency (21 SP) - CRITICAL PATH

- US-011: UI Technology Modernization (JSF → React/Angular) (21 SP)

#### Epic 6: AI Adoption (34 SP)

- US-012: Code Analysis Agent Implementation (13 SP)

- US-013: Knowledge Base Agent for Documentation (13 SP)

- US-014: Coverage and Rating Analysis Agent (8 SP)

### 2.3 Out-of-Scope (Explicit Exclusions)

The following items are EXPLICITLY OUT OF SCOPE for this Fixed Fee contract. Any request for these items requires a formal Change Request (Type 3 - Major) with budget and timeline impact assessment.

#### Product Implementation:

❌ SV Product implementation - The actual development of SV product line features, business logic, workflows, and screens is handled by a separate TMNAS team on the existing architecture. This project provides the modernized platform foundation for future SV migration only.

❌ CCD Integration - Integration with CCD system (definition TBD with client) has been removed from project scope.

#### Data Migration:

❌ Historical data migration - Migration of historical policy, claims, customer, and transaction data from legacy systems to modernized RapidSure. This may be included in Phase 2 (9-month option) pending client workshop discussions.

❌ Data quality assessment and cleanup - Analysis and correction of data quality issues in legacy systems before migration.

#### Training & Support:

❌ End-user training programs - Training for insurance agents, underwriters, claims adjusters, and business users on application functionality. TMNAS is responsible for end-user training.

❌ Training materials creation - User manuals, quick reference guides, video tutorials, e-learning modules for end users.

❌ Production L1/L2/L3 support post-warranty - Ongoing production support after 60-day warranty period. Building an MSP support team may be included in Phase 2 (9-month option).

#### Testing Execution:

❌ Performance test execution - TMNAS is responsible for executing performance and load testing, likely with external vendor support. EPAM provides ad-hoc support for troubleshooting and performance tuning as needed.

❌ Performance test script creation - Creation of load test scripts, performance test scenarios, and test data for performance testing.

❌ Security testing execution and penetration testing - TMNAS is responsible for security assessments, vulnerability scans, and penetration testing. EPAM ensures code follows secure coding practices (OWASP guidelines).

❌ UAT test execution - TMNAS coordinates UAT activities with their designated 3rd party testing vendor. EPAM provides defect triage support and prioritization guidance during UAT.

#### Infrastructure & Operations:

❌ Infrastructure provisioning and management - TMNAS is responsible for all production, UAT, QA, and DEV infrastructure, including servers, databases, networks, load balancers, firewalls, and cloud resources.

❌ License procurement - All development tools, testing tools, IDE licenses, and software licenses are provided by TMNAS via VDI environments. No additional license procurement by EPAM.

❌ Production deployment execution - TMNAS operations team executes production deployments following their change management procedures. EPAM provides deployment runbooks, support during deployment windows, and post-deployment validation.

❌ Production monitoring and alerting setup - Setup and configuration of production monitoring tools (Dynatrace, Splunk, etc.), alerting rules, and dashboards. EPAM provides monitoring requirements and recommendations only.

❌ Disaster recovery planning and testing - Creation and testing of disaster recovery plans, failover procedures, and backup/restore processes for production.

#### External Integrations:

❌ Integration with systems beyond those specified in backlog - Only integrations explicitly called out in the 16 user stories are in scope (e.g., Azure API Management, Salesforce RS Sync via existing interfaces). New integration requests require Change Requests.

❌ Salesforce customization or development - Integration with Salesforce is via existing RS Sync interface only; no Salesforce platform customizations, Apex development, or Lightning component development.

❌ Third-party vendor system modifications - EPAM does not modify systems owned by third-party vendors (e.g., Common Services, Image Right, Path, RePas, Xpression, Email Server). Integration is via published APIs and contracts only.

❌ API contract creation for external systems - EPAM develops against provided API contracts; creation of API contracts for external systems is TMNAS or vendor responsibility.

#### Business & Organizational:

❌ Business process reengineering - Analysis and redesign of TMNAS business processes (underwriting, claims, policy administration workflows). EPAM delivers technical platform; business process changes are TMNAS responsibility.

❌ Organizational change management - Change management activities to help TMNAS employees adopt new processes, tools, or ways of working. EPAM provides technical training for EPAM tools/platforms only.

❌ Regulatory compliance consulting - Advice or implementation of state-specific insurance regulatory requirements. EPAM follows TMNAS-provided compliance requirements but does not provide regulatory consulting.

❌ Business analytics and reporting - Creation of business intelligence dashboards, reports, or analytics beyond what exists in current RapidSure platform.

### 2.4 Scope Assumptions

The scope baseline is based on the following assumptions:

- Requirements are 70-80% defined at project start; remaining 20-30% will be refined during sprints through backlog grooming and rolling wave planning.

- User stories (16 stories, 202 SP) represent MVP for 6-month option; scope is sufficient to achieve business objectives (validate in client workshop).

- TMNAS provides timely inputs for requirements clarification (2 business day response time); delays in TMNAS input may reduce delivered scope to stay within timeline.

- No major scope expansions beyond 16 user stories without formal Change Request; minor clarifications (Type 1 CRs) are expected and absorbed in project.

- Third-party systems are available for integration testing with reasonable SLAs; extended unavailability of third-party systems may result in deferring integration testing or using mocks only.

- Architecture decisions made in internal workshop are validated and approved by TMNAS in client workshop; major architectural changes post-client workshop may require scope adjustments.

- EPAM team has required skills (Java, Spring Boot, React/Angular, MS SQL Server, Azure) to deliver scope; significant skill gaps may require training time or resource changes.

### 2.5 Scope Constraints

The following constraints limit project scope:

- Fixed Budget: $675,000 (6-month) or $1,800,000 (9-month) - Scope must fit within budget; scope expansion requires budget increase.

- Fixed Timeline: April 1 - September 30, 2026 (6-month) or April 1 - December 31, 2026 (9-month) - Scope must fit within timeline; scope expansion may require timeline extension.

- Fixed Team Size: 17 FTE across 4 pods - Scope is sized for this team; significant scope increase requires team size increase (which impacts budget).

- Technology Stack: Must work within existing TMNAS technology constraints (JBoss, MS SQL Server, Azure API Management) unless TMNAS approves modernization proposals.

- SV Product Release Schedule: Platform changes must align with SV product release schedule (6-week cadence); this constraint may limit deployment flexibility.

- TMNAS Stakeholder Availability: Limited Product Owner availability (assume 50% allocation); extensive requirements workshops or decision-making may not be feasible.

## 3. SCOPE DEFINITION PROCESS

### 3.1 Requirements Gathering

Process:

- Internal Workshop (March 17-19, 2026): EPAM team refines 16 user stories, validates scope completeness, identifies gaps.

- Client Workshop (TBD - Late March/Early April 2026): Present scope to TMNAS stakeholders, gather feedback, answer open questions, validate business objectives alignment.

- Backlog Grooming (Weekly): EPAM BA + TMNAS Product Owner refine upcoming user stories (3 sprints ahead), clarify requirements, define acceptance criteria, validate Definition of Ready.

- Sprint Planning (Bi-weekly): Team selects user stories for sprint, decomposes into tasks, commits to sprint goal.

Artifacts:

- User story template (As a [role], I want [feature], So that [benefit])

- Acceptance criteria (Given-When-Then format)

- Functional flows (happy path, alternative paths, negative paths)

- Technical requirements (APIs, integrations, architecture)

- Non-functional requirements (performance, security, scalability)

- Dependencies (external systems, other user stories)

### 3.2 Work Breakdown Structure (WBS)

Level 1: Project Rambo

- Level 2: Epics (6 epics)

  - Level 3: User Stories (16 stories)

    - Level 4: Tasks (defined during sprint planning)

      - Level 5: Sub-tasks (as needed for complex tasks)

Example WBS for US-008 (Business Layer API):

1.0 Project Rambo

5.0 Epic 5: Platform Modernization

5.1 US-008: Business Layer API Implementation (21 SP)

5.1.1 Design API architecture and contracts

5.1.1.1 Define business capabilities to expose

5.1.1.2 Create OpenAPI/Swagger specifications

5.1.1.3 Design authentication/authorization approach

5.1.1.4 Architecture review and approval

5.1.2 Implement API endpoints

5.1.2.1 Policy Management APIs (create, update, cancel, renew)

5.1.2.2 Rating APIs (get quote, calculate premium)

5.1.2.3 Customer Management APIs (create, update, search)

5.1.3 Implement API security

5.1.3.1 OAuth2/JWT authentication

5.1.3.2 Role-based authorization

5.1.3.3 API rate limiting and throttling

5.1.4 Testing

5.1.4.1 Unit tests (≥85% coverage)

5.1.4.2 Integration tests (API contract tests)

5.1.4.3 Performance testing (response time, throughput)

5.1.5 Documentation

5.1.5.1 API documentation (Swagger UI)

5.1.5.2 Integration guide for consumers

5.1.5.3 Deployment runbook

5.1.6 Deployment

5.1.6.1 Deploy to DEV environment

5.1.6.2 Deploy to QA environment

5.1.6.3 Smoke tests and validation

### 3.3 Deliverables

Deliverable Types:

1. Code Deliverables:

- Source code (Java, JavaScript, SQL) committed to version control (Git)

- Unit tests and integration tests

- Build scripts and configuration files

- Database migration scripts

2. Documentation Deliverables:

- Technical architecture diagrams (current state, future state, component diagrams)

- API documentation (Swagger/OpenAPI specifications, integration guides)

- Database schema documentation (ERD, data dictionary)

- Deployment runbooks (step-by-step deployment instructions, rollback procedures)

- User story documentation (requirements, acceptance criteria, test cases)

3. Process Deliverables:

- Strategic planning framework and product roadmap (US-001)

- Unified delivery framework documentation (US-002)

- Change Request process and templates (US-003)

- Definition of Ready (DoR) and Definition of Done (DoD) (US-004)

- Technical debt backlog and management process (US-007)

4. Infrastructure Deliverables:

- CI/CD pipeline configuration (Jenkins/GitLab CI scripts, automated tests)

- Infrastructure-as-Code scripts (Terraform/Ansible for environment provisioning)

- Monitoring dashboards and alerting configurations (recommendations)

5. Training Deliverables:

- AI agent training materials (workshops, hands-on labs for CodeMie adoption)

- Technical training for TMNAS team (knowledge transfer sessions, documentation)

### 3.4 Acceptance Criteria

Deliverable Acceptance Process:

1. Sprint-Level Acceptance (Every 2 Weeks):

- Sprint Review: EPAM team demonstrates completed user stories to TMNAS Product Owner

- Acceptance Decision: Product Owner accepts or rejects based on Definition of Done

- Outcome: Accepted stories = done; Rejected stories = carried to next sprint with clarifications

2. Milestone-Level Acceptance (M1, M2, M3, M4):

- Milestone Review: EPAM Delivery Manager presents milestone deliverables to TMNAS Sponsors (CTO/CIO)

- Quality Gate Validation: Confirm all quality gates passed (code coverage ≥85%, no P1/P2 defects, technical documentation complete)

- Acceptance Sign-Off: TMNAS Sponsors sign milestone acceptance document

- Outcome: Payment released upon acceptance

3. UAT-Level Acceptance:

- UAT Entry: EPAM delivers to UAT after passing quality gates

- UAT Execution: TMNAS + 3rd party vendor execute UAT test cases

- Defect Resolution: EPAM fixes P1/P2 defects found in UAT

- UAT Exit: UAT exit criteria met (≥95% pass rate, all P1/P2 defects resolved)

- Go-Live Approval: TMNAS CIO/CTO approve production deployment

Acceptance Criteria Standards:

- All user stories must have clear, testable acceptance criteria in Given-When-Then format

- All acceptance criteria must be validated before story is marked "Done"

- Product Owner has final authority on acceptance (unless escalated to CR Board or Steering Committee)

## 4. SCOPE VALIDATION

### 4.1 Validation Checkpoints

1. Sprint Review (Every 2 Weeks):

- Participants: EPAM Team + TMNAS Product Owner + Stakeholders

- Purpose: Validate completed user stories meet acceptance criteria

- Outcome: Product Owner accepts/rejects stories

2. Milestone Review (M1, M2, M3, M4):

- Participants: EPAM Delivery Manager + Solution Architect + TMNAS Sponsors (CTO/CIO)

- Purpose: Validate milestone deliverables meet quality gates and contractual commitments

- Outcome: Milestone acceptance and payment release

3. Quality Gate Review (Before UAT):

- Participants: EPAM QA Lead + Delivery Manager + TMNAS UAT Lead

- Purpose: Validate quality gates passed before UAT handoff

- Outcome: Go/No-Go decision for UAT

4. UAT Exit Review:

- Participants: TMNAS UAT Lead + EPAM Delivery Manager + TMNAS CTO

- Purpose: Validate UAT exit criteria met, approve go-live

- Outcome: Production deployment approval

### 4.2 Scope Verification Tools

1. Sprint Burndown Chart:

- Tracks remaining story points in sprint

- Validates team is on track to complete sprint commitment

- Early warning if sprint is at risk

2. Release Burnup Chart:

- Tracks cumulative story points completed vs. total scope

- Validates project is on track to complete 202 SP within 6 or 9 months

- Shows scope changes over time (if Change Requests add/remove scope)

3. Scope Traceability Matrix:

- Maps user stories → acceptance criteria → test cases → code modules

- Validates all requirements are implemented and tested

- Identifies any gaps or untested requirements

4. Definition of Done (DoD) Checklist:

- Validates each user story meets all DoD criteria before marking "Done"

- Prevents incomplete work from being accepted

## 5. SCOPE CONTROL

### 5.1 Change Request (CR) Process

Purpose: Manage all scope changes through a formal, controlled process to prevent scope creep and protect Fixed Fee contract.

Change Request Types:

| CR Type | Impact | Approval Process | Budget Impact |
| --- | --- | --- | --- |
| Type 1 - Clarification | No impact on scope, schedule, or cost | EPAM Delivery Manager approval only | None (absorbed in project) |
| Type 2 - Minor Change | <5% budget impact (<$33.75K for 6-month) | Change Control Board approval | Absorbed in 20% contingency |
| Type 3 - Major Change | >5% budget impact (>$33.75K for 6-month) | Change Control Board + Executive Sponsors (CTO/CIO) + Contract Amendment | Additional budget required |

### 5.2 Change Request Workflow

Step 1: CR Submission

- Who: TMNAS stakeholder or EPAM team member submits CR via template

- Template Includes:

  - CR Title and Description

  - Business Justification (why is change needed?)

  - Proposed Solution

  - Impact if CR is not approved (risks, business consequences)

- Timeline: Submit any time; CR Board reviews weekly

Step 2: Impact Assessment (EPAM Delivery Manager)

- Timeline: Within 3 business days of CR submission

- Assessment Includes:

  - Scope Impact: What work is added, changed, or removed? How many story points?

  - Schedule Impact: Does this delay milestones? How many sprints affected?

  - Cost Impact: What is the cost ($ or % of budget)?

  - Risk Impact: Does this introduce new risks or mitigate existing risks?

  - Quality Impact: Does this affect quality, technical debt, or architecture?

- Classification: Classify as Type 1, 2, or 3 based on budget impact

- Recommendation: Approve, Reject, or Defer (with rationale)

Step 3: CR Board Review

- Participants: EPAM (DM, BA) + TMNAS (Product Owner, Prashant/CTO, BA)

- Frequency: Weekly (30 min meeting) or as-needed for urgent CRs

- Agenda:

  - Review all new CRs (EPAM DM presents impact assessment)

  - Discuss business justification vs. impact

  - Vote: Approve, Reject, or Defer

  - For Type 3 CRs: Recommend to Executive Sponsors

- Decision Authority:

  - Type 1: EPAM DM approval (no CR Board needed)

  - Type 2: CR Board majority vote

  - Type 3: CR Board recommends; Executive Sponsors approve

- Timeline: Decision within 1 week of CR submission

Step 4: Executive Sponsor Approval (Type 3 Only)

- Participants: TMNAS CIO (Lana) + CTO (Prashant) + EPAM Account Manager

- Process: CR Board presents Type 3 CR with recommendation

- Decision: Approve (requires contract amendment), Reject, or Defer

- Timeline: Within 2 weeks of CR Board recommendation

Step 5: CR Implementation

- If Approved:

  - EPAM BA adds/changes user stories in backlog with new priority

  - If Type 3: Contract amendment executed before work begins

  - EPAM team implements change in upcoming sprint(s)

- If Rejected:

  - EPAM DM communicates decision and rationale to CR submitter

  - No further action

- If Deferred:

  - CR moved to "parking lot" for future consideration (e.g., Phase 2, post-project)

Step 6: CR Tracking

- CR Log: All CRs tracked in shared log (Excel, Jira, or similar)

- CR Log Fields:

  - CR ID, Title, Submitter, Date Submitted

  - Type (1/2/3), Impact Assessment (scope, schedule, cost)

  - Status (Submitted, Under Review, Approved, Rejected, Deferred, Implemented)

  - Decision Date, Approver(s), Implementation Sprint

- Reporting: CR Log reviewed in weekly status report and monthly Steering Committee

### 5.3 Baseline Change Control

Scope Baseline: Defined in this Scope Management Plan (16 user stories, 202 SP)

Baseline Change Process:

- Minor Baseline Changes (Type 2 CRs, <5% impact): Update baseline with CR Board approval; no contract amendment

- Major Baseline Changes (Type 3 CRs, >5% impact): Requires formal contract amendment; new baseline version created

Baseline Versioning:

- Version 1.0: Initial baseline (March 2026, pre-project start)

- Version 1.1, 1.2, etc.: Minor updates (Type 2 CRs absorbed in contingency)

- Version 2.0, 3.0, etc.: Major updates (Type 3 CRs with contract amendments)

Baseline Communication:

- All baseline changes communicated to EPAM team and TMNAS stakeholders via:

  - Updated Scope Management Plan document

  - Weekly status report

  - CR Board meeting minutes

  - Steering Committee presentation (for major changes)

### 5.4 Scope Creep Prevention

Strategies to Prevent Scope Creep:

1. Clear Scope Documentation:

- 16 user stories with detailed acceptance criteria

- Explicit out-of-scope list (Section 2.3)

- TMNAS stakeholder agreement on scope baseline (client workshop)

2. Formal Change Control:

- All scope changes require CR (no "informal" requests)

- Impact assessment before any work begins

- CR Board approval required (no unilateral decisions)

3. Definition of Ready (DoR):

- User stories must meet DoR before entering sprint

- Prevents vague, incomplete stories from consuming sprint capacity

4. Rolling Wave Planning:

- Plan only 3 sprints ahead in detail

- Prevents over-commitment to far-future work that may change

5. Weekly Backlog Grooming:

- EPAM BA + TMNAS PO clarify requirements continuously

- Reduces misunderstandings that lead to rework (which looks like scope increase)

6. Sprint Commitment Protection:

- Once sprint starts, no new stories added (except critical production issues)

- TMNAS requests must wait for next sprint or follow CR process

7. Executive Sponsor Oversight:

- Monthly Steering Committee reviews scope, CRs, and risks

- Executive visibility prevents "hidden" scope creep

8. Transparent Reporting:

- Weekly status report includes: scope completed, scope remaining, scope added via CRs, scope at risk

- Stakeholders see scope trends and can intervene early

## 6. SCOPE MONITORING & REPORTING

### 6.1 Scope Metrics

Track and report the following metrics:

1. Scope Completion Metrics:

- Story Points Completed: Cumulative SP completed vs. 202 SP total

- User Stories Completed: # of stories done vs. 16 total

- Sprint Velocity: SP completed per sprint (target: 20-22 SP/sprint for 17 FTE team)

- Burnup Chart: Visual trend of scope completion over time

2. Scope Change Metrics:

- # of Change Requests: Total CRs submitted (by Type 1/2/3)

- CR Approval Rate: % of CRs approved vs. rejected

- Scope Added via CRs: Additional SP added through approved CRs

- Scope Removed via CRs: SP removed or descoped through CRs

- Net Scope Change: Scope added - scope removed (should be ~0 for Fixed Fee)

3. Scope Risk Metrics:

- Stories at Risk: # of stories that may not be completed on time

- Scope Gaps: # of identified requirements not captured in user stories

- Rework %: % of SP spent on rework due to requirements clarification

### 6.2 Scope Reporting

Weekly Status Report:

- Scope Completed This Week: X SP completed (cumulative: Y SP of 202 SP)

- Sprint Progress: Sprint X - Day Y - Z SP remaining in sprint

- Change Requests: X new CRs submitted, Y CRs approved this week, Z total CRs active

- Scope Risks: List stories at risk of not completing on time with mitigation plans

Monthly Steering Committee Report:

- Scope Completion Trend: Burnup chart showing progress toward 202 SP

- Milestone Progress: % complete toward next milestone (M1, M2, M3, M4)

- Change Request Summary: Total CRs by type, cumulative scope impact ($, %)

- Scope Forecast: Based on current velocity, will we complete 202 SP on time? Any risks?

Milestone Report (M1, M2, M3, M4):

- Milestone Scope: List all user stories included in milestone

- Acceptance Criteria Status: All acceptance criteria met? (Yes/No with details)

- Quality Gates Status: All quality gates passed? (Code coverage, defects, documentation)

- Scope Variances: Any deviations from baseline scope? (CRs, descopes, deferrals)

- Recommendation: Accept milestone? (Yes/No with rationale)

## 7. ROLES & RESPONSIBILITIES

### 7.1 Scope Management Roles

| Role | Scope Management Responsibilities |
| --- | --- |
| EPAM Delivery Manager | - Overall accountability for scope management - Conduct impact assessments for Change Requests - Chair Change Control Board meetings - Escalate scope risks to Steering Committee - Report scope metrics in weekly status report |
| EPAM Business Analyst | - Maintain product backlog (user stories, acceptance criteria) - Facilitate backlog grooming with TMNAS Product Owner - Track scope completion (story points, burnup chart) - Document Change Requests and track CR log - Ensure user stories meet Definition of Ready |
| TMNAS Product Owner | - Define and prioritize product backlog - Accept or reject user stories in Sprint Review - Approve/reject Change Requests in CR Board - Clarify requirements during backlog grooming - Represent business stakeholders for scope decisions |
| EPAM Solution Architect | - Assess technical impact of scope changes - Validate technical feasibility of new requirements - Ensure architecture accommodates scope - Identify technical risks related to scope |
| TMNAS CTO / Prashant | - Approve Type 2 Change Requests in CR Board - Recommend Type 3 CRs to Executive Sponsors - Validate technical scope aligns with TMNAS architecture standards |
| TMNAS CIO / Lana | - Approve Type 3 Change Requests (major scope changes) - Review scope progress in monthly Steering Committee - Escalation point for scope disputes |
| Change Control Board | - Review and approve/reject Change Requests (Type 2 and recommend Type 3) - Meet weekly to discuss CRs - Ensure scope changes are controlled and documented |
| Steering Committee | - Review scope progress monthly - Approve strategic scope changes (Type 3 CRs) - Resolve scope disputes escalated by CR Board |

## 8. SCOPE MANAGEMENT TOOLS

### 8.1 Tools for Scope Management

1. Product Backlog Tool:

- Tool: Jira (assumed - TBD in client workshop) or Azure DevOps

- Purpose: Manage user stories, track story points, sprint planning, burndown/burnup charts

- Owner: EPAM Business Analyst

2. Change Request Log:

- Tool: Excel, Jira, or dedicated CR management tool

- Purpose: Track all CRs (submission, impact assessment, approval status, implementation)

- Owner: EPAM Business Analyst

3. Requirements Traceability Matrix:

- Tool: Excel or specialized requirements management tool

- Purpose: Trace requirements → user stories → acceptance criteria → test cases → code

- Owner: EPAM Business Analyst

4. Scope Reporting Dashboards:

- Tool: Jira dashboards, Power BI, or custom reports

- Purpose: Visualize scope completion, velocity, CR trends, risks

- Owner: EPAM Delivery Manager

## 9. APPENDICES

### Appendix A: User Story Template

User Story ID: US-XXX

Title: [Short descriptive title]

Epic: [Epic name]

Priority: Critical / High / Medium / Low

Story Points: [X SP]

Sprint: [Sprint number]

User Story:

As a [role/persona],

I want [feature/capability],

So that [business benefit/value].

Acceptance Criteria:

1. Given [precondition], When [action], Then [expected result]

2. Given [precondition], When [action], Then [expected result]

3. [Additional acceptance criteria as needed]

Functional Flows:

- Happy Path: [Step-by-step]

- Alternative Path: [Step-by-step]

- Negative Path (Error Handling): [Step-by-step]

Technical Requirements:

- [APIs, integrations, database changes, architecture]

Non-Functional Requirements:

- Performance: [Response time, throughput]

- Security: [Authentication, authorization, data protection]

- Scalability: [Concurrent users, data volume]

Dependencies:

- [Other user stories, external systems, infrastructure]

Definition of Ready Checklist:

☐ Clear acceptance criteria (Given-When-Then)

☐ Dependencies identified

☐ Story sized (fits in one sprint)

☐ Technical design approach agreed

☐ Test approach defined

☐ No open questions

Definition of Done Checklist:

☐ Code complete and peer-reviewed

☐ Unit tests (≥85% coverage)

☐ Integration tests passed

☐ Merged to main branch

☐ Technical documentation updated

☐ Acceptance criteria validated

☐ No P1/P2 defects

☐ Deployed to QA

☐ Product Owner acceptance

### Appendix B: Change Request Template

Change Request ID: CR-XXX

Submission Date: [Date]

Submitter: [Name, Role, Organization]

CR Title: [Short descriptive title]

CR Type: ☐ Type 1 (Clarification) ☐ Type 2 (Minor) ☐ Type 3 (Major)

Business Justification:

[Why is this change needed? What business problem does it solve?]

Current State:

[What is the current functionality or scope?]

Proposed Change:

[What is the requested change? Be specific.]

Impact if CR is NOT Approved:

[What are the risks or business consequences if this CR is rejected?]

--- EPAM IMPACT ASSESSMENT (Completed by EPAM DM) ---

Scope Impact:

- User Stories Added/Changed/Removed: [List]

- Story Points Added: [X SP]

- Story Points Removed: [Y SP]

- Net Scope Change: [X - Y = Z SP]

Schedule Impact:

- Sprints Affected: [Sprint numbers]

- Milestone Delays: [M1/M2/M3/M4 delayed by X weeks?]

- Critical Path Impact: [Yes/No - explain]

Cost Impact:

- Estimated Cost: $[amount] or [%] of budget

- Type Classification: [Type 1 / Type 2 / Type 3]

Risk Impact:

- New Risks Introduced: [List]

- Existing Risks Mitigated: [List]

Quality Impact:

- Technical Debt Impact: [Increase/Decrease/No Change]

- Architecture Impact: [Significant/Minor/None]

EPAM Recommendation: ☐ Approve ☐ Reject ☐ Defer

Rationale: [Explain recommendation]

--- CR BOARD DECISION ---

CR Board Meeting Date: [Date]

CR Board Members Present: [Names]

Discussion Summary:

[Key points discussed]

Decision: ☐ Approved ☐ Rejected ☐ Deferred

Vote: [X for, Y against, Z abstain]

Approval Conditions (if any):

[Conditions that must be met for implementation]

Implementation Sprint: [Sprint number if approved]

--- EXECUTIVE SPONSOR APPROVAL (Type 3 Only) ---

Executive Sponsor: [Name, Title]

Approval Date: [Date]

Signature: _______________________

Contract Amendment Required: ☐ Yes ☐ No

Contract Amendment ID: [If applicable]