# TMNAS - Project Rambo

# Product Backlog - Updated v2.0

Document Version: 2.0

Last Updated: January 2025

Status: Draft for Internal Workshop

# Executive Summary

This document contains the updated product backlog for the TMNAS RapidSure Platform Modernization project. All user stories meet the Definition of Ready (DoR) criteria and are organized for parallel execution across 4 specialized pods.

## Key Changes in v2.0

• Removed SV Product Implementation stories (US-015, US-016)
• Removed Pod 2: SV Product Launch (5 people)
• Updated story count: 18 → 16 user stories
• Updated story points: 236 SP → 202 SP
• Updated team size: 22 → 17 people (4 pods)
• Updated budget alignment: 6-month ($675K), 9-month ($1.8M)

## Scope Clarification

Note: SV Product implementation is out of scope for this project. Platform modernization will create the foundation to support future SV product releases, but the actual SV product development will be handled by a separate team. This project includes platform upgrades necessary to enable SV product migration to the modernized architecture.

# Backlog Summary

| Epic | Stories | Story Points | % of Total |
| --- | --- | --- | --- |
| Governance & SDLC | 3 | 34 | 17% |
| Requirements & Solutioning | 2 | 16 | 8% |
| Development & QA | 2 | 21 | 10% |
| Deployment & Infrastructure | 2 | 21 | 10% |
| Platform Modernization | 4 | 76 | 38% |
| AI Adoption | 3 | 34 | 17% |
| TOTAL | 16 | 202 | 100% |

# Updated Team Structure (4 Pods, 17 People)

| Pod | Focus Area | Team Size | User Stories | Story Points |
| --- | --- | --- | --- | --- |
| Pod 1: Platform Modernization | Business API, DB Optimization, Tech Debt | 6 people | US-008, US-009, US-010, US-007 | 63 SP |
| Pod 3: UI & Frontend | UI Technology Modernization | 4 people | US-011 | 21 SP |
| Pod 4: Process & AI | Governance, Requirements, AI Agents | 4 people | US-001-005, US-012-014 | 63 SP |
| Pod 5: Infrastructure | CI/CD, QA Shift-Left, Environments | 3 people | US-006, US-017, US-018 | 34 SP |
| TOTAL |  | 17 people | 16 stories | 202 SP |

# Removed Stories (Out of Scope)

US-015: SV Product G1, G2, G4 States Implementation
• Story Points: 21 SP
• Reason: SV product implementation handled by separate team
• Status: Out of scope for Project Rambo

US-016: CCD Integration into RapidSure
• Story Points: 13 SP
• Reason: Dependent on SV product implementation
• Status: Out of scope for Project Rambo

# Project Timeline

6-Month Option:
• Duration: April 1 - September 30, 2026 (10 sprints)
• Scope: 202 story points (16 user stories)
• Budget: $675K
• Team: 17 people across 4 pods

9-Month Option:
• Duration: April 1 - December 31, 2026 (18 sprints)
• Scope: ~350 story points (additional scope TBD)
• Budget: $1.8M ($600K per 4-month phase)
• Team: 17 people across 4 pods

# Updated Critical Path

Previous Critical Path (with SV):
US-008 (Business API) → US-015 (SV Product) → US-016 (CCD Integration)

New Critical Path:
US-008 (Business Layer API) → US-009 (Product Config API) → US-011 (UI Modernization)

Key Dependencies:
• US-008 must complete before US-009 can start (API foundation)
• US-010 (DB Optimization) should complete before high-volume features
• US-011 (UI Modernization) benefits from US-008 completion

# Detailed User Stories (16 Stories, 202 SP)

## US-001: Strategic Planning & Roadmap Implementation

| Epic | Governance & SDLC |
| --- | --- |
| Priority | High |
| Story Points | 13 |
| Assigned Pod | Pod 4: Process & AI |
| Sprint | Sprint 1-2 |

### User Story:

As a Program Manager, I want to establish a strategic planning framework and product roadmap so that we can align delivery with business objectives and manage stakeholder expectations effectively.

### Acceptance Criteria:

✓ Strategic planning framework documented and approved

✓ Product roadmap created for 12-month horizon

✓ Stakeholder communication plan established

✓ Quarterly planning process defined

## US-002: Unified Delivery Framework Rollout

| Epic | Governance & SDLC |
| --- | --- |
| Priority | High |
| Story Points | 13 |
| Assigned Pod | Pod 4: Process & AI |
| Sprint | Sprint 2-3 |

### User Story:

As a Delivery Manager, I want to implement a unified delivery framework (Hybrid Agile) so that we can standardize processes across teams and improve delivery predictability.

### Acceptance Criteria:

✓ Hybrid Agile framework documented (Agile execution + Waterfall governance)

✓ Sprint ceremonies defined and scheduled

✓ Quality gates established at milestones

✓ Team trained on new framework

## US-003: AI-Enhanced Estimation & Change Control

| Epic | Governance & SDLC |
| --- | --- |
| Priority | Medium |
| Story Points | 8 |
| Assigned Pod | Pod 4: Process & AI |
| Sprint | Sprint 3-4 |

### User Story:

As a Delivery Manager, I want to implement AI-enhanced estimation tools and formal change control process so that we can improve estimation accuracy and manage scope changes effectively.

### Acceptance Criteria:

✓ AI estimation tool integrated with backlog

✓ Change Request (CR) process documented and approved

✓ CR Board established with defined members

✓ CR tracking system operational

## US-004: Requirements Quality Improvement Framework

| Epic | Requirements & Solutioning |
| --- | --- |
| Priority | High |
| Story Points | 8 |
| Assigned Pod | Pod 4: Process & AI |
| Sprint | Sprint 2-3 |

### User Story:

As a Business Analyst, I want to establish a requirements quality framework so that all user stories meet Definition of Ready before sprint planning.

### Acceptance Criteria:

✓ Requirements quality checklist created

✓ DoR criteria enforced in backlog grooming

✓ BA review process established

✓ Requirements templates created and adopted

## US-005: Centralized Knowledge Library

| Epic | Requirements & Solutioning |
| --- | --- |
| Priority | Medium |
| Story Points | 8 |
| Assigned Pod | Pod 4: Process & AI |
| Sprint | Sprint 4-5 |

### User Story:

As a Team Member, I want access to a centralized knowledge library so that I can quickly find documentation, best practices, and technical guides.

### Acceptance Criteria:

✓ Knowledge library platform selected and configured

✓ Existing documentation migrated

✓ Search functionality operational

✓ Contribution process defined

## US-006: QA Shift-Left with AI Test Generation

| Epic | Development & QA |
| --- | --- |
| Priority | High |
| Story Points | 13 |
| Assigned Pod | Pod 5: Infrastructure |
| Sprint | Sprint 3-5 |

### User Story:

As a QA Engineer, I want to implement shift-left testing practices with AI-powered test generation so that we can catch defects earlier and improve code quality.

### Acceptance Criteria:

✓ Unit test coverage ≥85% for new code

✓ AI test generation tool integrated

✓ Automated test execution in CI/CD pipeline

✓ Test results dashboard operational

## US-007: Technical Debt Management System

| Epic | Development & QA |
| --- | --- |
| Priority | Medium |
| Story Points | 8 |
| Assigned Pod | Pod 1: Platform Modernization |
| Sprint | Sprint 8-9 |

### User Story:

As a Technical Lead, I want a technical debt management system so that we can track, prioritize, and systematically reduce technical debt.

### Acceptance Criteria:

✓ Technical debt inventory completed

✓ Debt items categorized and prioritized

✓ Debt reduction plan created

✓ Tracking dashboard operational

## US-008: Business Layer API Implementation

| Epic | Platform Modernization |
| --- | --- |
| Priority | Critical |
| Story Points | 21 |
| Assigned Pod | Pod 1: Platform Modernization |
| Sprint | Sprint 1-3 |

### User Story:

As a Solution Architect, I want to implement a Business Layer API so that we can expose business capabilities via modern REST APIs and enable future microservices architecture.

### Acceptance Criteria:

✓ REST API framework implemented (Spring Boot)

✓ Core business capabilities exposed (Policy, Rating, Underwriting)

✓ API documentation (Swagger/OpenAPI) published

✓ Unit test coverage ≥85%

✓ Integration tests passing

## US-009: Product Configuration API Standardization

| Epic | Platform Modernization |
| --- | --- |
| Priority | High |
| Story Points | 13 |
| Assigned Pod | Pod 1: Platform Modernization |
| Sprint | Sprint 4-5 |

### User Story:

As a Product Manager, I want standardized Product Configuration APIs so that product setup and changes can be managed efficiently across all product lines.

### Acceptance Criteria:

✓ Product Configuration API endpoints implemented

✓ Configuration data model standardized

✓ API integrated with Configurator system

✓ Migration scripts for existing configurations

✓ API documentation complete

## US-010: Database Optimization for High Concurrency

| Epic | Platform Modernization |
| --- | --- |
| Priority | Critical |
| Story Points | 21 |
| Assigned Pod | Pod 1: Platform Modernization |
| Sprint | Sprint 1-4 |

### User Story:

As a DBA, I want to optimize the database for high concurrency so that the platform can support increased user load and new product launches.

### Acceptance Criteria:

✓ Database performance baseline established

✓ Query optimization completed (top 20 slow queries)

✓ Indexing strategy implemented

✓ Connection pooling optimized

✓ Performance improvement ≥30% for critical queries

## US-011: UI Technology Modernization

| Epic | Platform Modernization |
| --- | --- |
| Priority | High |
| Story Points | 21 |
| Assigned Pod | Pod 3: UI & Frontend |
| Sprint | Sprint 4-10 |

### User Story:

As an End User, I want a modern, responsive UI so that I can access the platform efficiently from any device with improved performance and user experience.

### Acceptance Criteria:

✓ UI framework migrated from JSF/IceFaces to React/Angular

✓ Responsive design implemented (desktop, tablet, mobile)

✓ Page load time reduced by ≥50%

✓ Accessibility standards met (WCAG 2.1 AA)

✓ User acceptance testing passed

## US-012: Code Analysis Agent Implementation

| Epic | AI Adoption |
| --- | --- |
| Priority | Medium |
| Story Points | 13 |
| Assigned Pod | Pod 4: Process & AI |
| Sprint | Sprint 2-4 |

### User Story:

As a Developer, I want an AI-powered code analysis agent so that I can receive automated code review feedback and improve code quality.

### Acceptance Criteria:

✓ AI code analysis agent deployed

✓ Integration with Git/CI/CD pipeline

✓ Code quality metrics dashboard

✓ Automated code review comments in PRs

✓ Team trained on using the agent

## US-013: Knowledge Base Agent for Documentation

| Epic | AI Adoption |
| --- | --- |
| Priority | Medium |
| Story Points | 13 |
| Assigned Pod | Pod 4: Process & AI |
| Sprint | Sprint 5-7 |

### User Story:

As a Team Member, I want an AI knowledge base agent so that I can quickly find answers to technical questions and access relevant documentation.

### Acceptance Criteria:

✓ AI knowledge base agent deployed

✓ Integration with centralized knowledge library

✓ Natural language query interface

✓ Response accuracy ≥80%

✓ Usage analytics dashboard

## US-014: Coverage and Rating Analysis Agent

| Epic | AI Adoption |
| --- | --- |
| Priority | Medium |
| Story Points | 8 |
| Assigned Pod | Pod 4: Process & AI |
| Sprint | Sprint 7-8 |

### User Story:

As an Underwriter, I want an AI agent to analyze coverage and rating scenarios so that I can make faster, data-driven decisions.

### Acceptance Criteria:

✓ AI coverage/rating analysis agent deployed

✓ Integration with RapidSure rating engine

✓ Scenario analysis capabilities

✓ Recommendation accuracy validated

✓ User training completed

## US-017: Automated CI/CD Pipeline with AI Optimization

| Epic | Deployment & Infrastructure |
| --- | --- |
| Priority | High |
| Story Points | 13 |
| Assigned Pod | Pod 5: Infrastructure |
| Sprint | Sprint 1-3 |

### User Story:

As a DevOps Engineer, I want an automated CI/CD pipeline with AI optimization so that we can deploy code faster with higher quality and fewer failures.

### Acceptance Criteria:

✓ CI/CD pipeline implemented (Jenkins/GitLab CI)

✓ Automated build, test, and deployment

✓ AI-powered build optimization

✓ Deployment success rate ≥95%

✓ Deployment time reduced by ≥40%

## US-018: Environment Automation and Management

| Epic | Deployment & Infrastructure |
| --- | --- |
| Priority | Medium |
| Story Points | 8 |
| Assigned Pod | Pod 5: Infrastructure |
| Sprint | Sprint 3-4 |

### User Story:

As a DevOps Engineer, I want automated environment provisioning and management so that we can quickly spin up test environments and reduce manual effort.

### Acceptance Criteria:

✓ Infrastructure as Code (IaC) implemented

✓ Automated environment provisioning

✓ Environment configuration management

✓ Environment cost tracking and optimization

✓ Documentation and runbooks complete

# Appendix: Definition of Ready (DoR)

All user stories in this backlog meet the following Definition of Ready criteria:

✓ User story follows INVEST principles (Independent, Negotiable, Valuable, Estimable, Small, Testable)

✓ Acceptance criteria clearly defined (Given-When-Then format)

✓ Dependencies identified and documented

✓ Story points estimated by the team

✓ No open questions or blockers

✓ Technical approach discussed and agreed

✓ Non-functional requirements identified

✓ Test strategy defined

✓ Sprint assignment confirmed

# Glossary

SP: Story Points - Unit of effort estimation

DoR: Definition of Ready - Criteria for stories to enter sprint

DoD: Definition of Done - Criteria for stories to be considered complete

CR: Change Request - Formal request to change project scope

CI/CD: Continuous Integration/Continuous Deployment

API: Application Programming Interface

UI: User Interface

QA: Quality Assurance

NFR: Non-Functional Requirement

POC: Proof of Concept